## Adding or Updating PTS (hidden)
HOME | INSTRUCTIONS FOR UPDATING, ADDING, AND ARCHIVING VARIOUS PTS TABS
1 | When making periodic Updates to projects
2 | There are a couple of good rules to know when to update and repost the PTS. 1. Two weeks before a PMOS or SC meeting and following actions of a PMOS or SC meeting. 2. When a NERC Announcement is made (e.g., Standard posting, drafting team solicitation, etc.) 3. When the data freshness column (far right) of the HOME tab becomes YELLOW and definitely when it becomes RED.
3 | Communicate with the various developers and/or the liaisons to get the needed updates.
4 | Ensure the following essential items are accurate and up to date: 1. Status; 2. Comments (usually notes three areas - what was recently accomplished, current activities, and next steps; and 3. Check that the posting dates make sense (e.g., the final ballot is not occuring before a regular posting, etc.) This can be visualized on the HOME tab by looking at the colors for even spacing.
5 | If a major update occurs (e.g., change in developer, liaison, number of standards, etc.), record that in the PTS Change Control.
6 | Update the cell for "Last Updated" with the appropriate date. This triggers the data freshness column on the HOME tab.
7 | Before releasing the PTS for posting externally, click on each projec and ensure the zoom setting is normal (e.g., 100%), that each project is scrolled to the top of the project information. If not, adjust so Rows 1, 2, 3, etc. are showing, then click in one of the rows to lock the viewing position. Otherwise, it will return to the previous state when clicking onto another tab.
8 | Update the "Updated" cell to the appropiate date.
9 | Lastly, click on the HOME tab. Adjust the Gannt Chart by hiding columns so that only about two weeks prior to the red line show to the left. The color legend at the top may need to be copied and shifted to the right so it follows the timeline.
10 | Save the file and check it in, if necessary. As a rule, after major updates (e.g., following a PMOS meeting), consider publishing a major version to capture that in the version history (e.g., Update following PMOS in-person). This helps with understanding milestones in the PTS.
11 | Instructions for Creating a New Project Tab
12 | If not already shown, unhide the latest project to preserve project order. Using the menu Create/insert a new tab and name it appropriately (e.g., YYYY-##). Color the tab the default MS color blue to show the project is active, if not already blue and move tab to correct postion/order.
13 | Unhide the tab "Complexity Template," select the entire contents, copy, and paste it into cell A1 of the new tab created/inserted the above step. (Do not enter any data yet.)
14 | Re-hide "Completity Template" for future use.
15 | Goto the "Home" tab and unhide all columns by clicking the triangle in the upper left corner of cell A1 to select all record and right clicking unhide (including old date columns A-CTZ, etc.). By clicking the triangle again to select all records and using the "editing" menu and "unclear" all filters.
16 | On the home tab, goto the last project pairs (e.g. baseline/Complexity) in the list. Select both rows using the grey row numbers along the left edge. Copy both rows (cntrl + c).
17 | Click and select the next two empty pairs of rows in the far left grey area and paste (cntrl + v), no special paste.
18 | In both of new pairs, carefully select each cell individually in columns B-E and change the project number listed in the formula to the desired project number. Note that it may appear more than once. DO NOT copy one row, update and copy to the next row to save time. This will make a mess of the conditional formatting that has to do with the record pairs.
19 | For each of the hyperlinked cells, hover over the cell and right click revealing the contextual menu. Click "Edit Hyperlink" and using the scroll feature, scroll up slightly to reveal the correct/current project tab. Select and click "Okay". Do this for each of the hyperlinked row pairs and columns for their respective project.
20 | Click the hyper link and confirm it goes to the correct project page. While on the project, update Row 1 to the project number and Row 2 to the project name. Note: The hyperlink defaults to the Standards Under Development. If the project page is active copy its URL address and update the hyperlink.
21 | From the project page, make sure that the basic project dates are filled in (from the template) for both the planned/actual and baseline/complexity factor columns. Note: The proposed/actual may be adjusted by the developer based on their team's recommendation.
22 | This next step is the most tedious, time consuming, and opportunity for mistakes. From the homepage, click in the date/timeline area (i.e., Gantt Chart) of the first row of the pair being worked on. From the Excel "Home" tab on the ribbon at the top of the screen, locate the "Styles" group and the tool called "Conditional Formatting." Click the down arrow to reveal more tools, select "Manage Rules." Make sure "Current Selection" is shown and a list of colored rules should be shown. These colors coorespond to the color scheme on each project page tab. Check to see that you have the same number of colors shown in the Conditional Formatting as on a project tab. (If not, these instructions do not go over how to troubleshoot or fix - that's for someone well versed with Excel.)
23 | Now that the colors are confirmed, each color will be selected individually and under the formula, update the current project number to the correct number, then click okay. Note: Use the mouse to select the values for editing, because the arrow keys will introduce invalid data. The most common mistake is accidently deleting the apostrope character. If something goes wrong, click "Cancel" to start over. Select each conditional formatting rule for all colors EXCEPT RED, which has no project number associated with it. Be sure to click "Apply" when done. Do this for both row pairs.
24 | Once both row pairs have their conditional formatting updated, scroll to the right in the date area of the HOME tab and find the current date. There should be a colored bar for each of the formula rules that were updated AND each of the rows should be offset by a few days. If so, everything went well and no errors. If a color bar is missing or overlaps with another color, something is wrong with the conditional formatting. Try and determine which color bar is problematic in order to determine which color formatting needs correcting. Remember they are in order because the template was used.
25 | In column "F", set the first pair to a status of "Complexity Factor" or other appropriate status, then set the second pair to a status of "Open-Current" until the developer gives the proposed schedule.
26 | Check the hyperlink for each new project and confirm it goes to the correct project page. While on that page, scroll down to the PTS Change Control and add an entry documenting when the project was added to the PTS.
27 | You are now done on the "HOME" page.
28 | Instructions for Updating the Summary Tab
29 | This one is a bit easier. There should not be any hidden columns in this tab, but check to be sure.
30 | Remove all column filtering. Note: That when a project is "Archived" it will be filtered off of this page, but that only happens by going to the page, clicking the filter and then okay to "refresh" the filtering.
31 | Like adding project rows, select the very last project by clicking the "row" number on the very left. Then click the next "row" number and paste (i.e., cntrl-v or right click paste). Note: Do not paste with any special pasting.
32 | In the desired project row, RIGHT click the hyperlinked cell in column A. When the dialog box opens, navigate up using the up arrow only a few items to find the desired project name (i.e., worksheet/tab). Double click the desired project to link it to the cell or click it once to highlight it and then click the okay button.
33 | While still on that cell, look below the ribbon where the cell contents are in the text box. Replace that text with the appropriate project number (e.g., YYYY-##).
34 | Now in columns B through O, update the formula in each cell to properly reference the desired project (e.g., YYYY-##). Note: If you get an error, check to see that the YYYY-## has an ' on each end (common error when editing).
35 | Repeat the process for any additional projects.
36 | Once all the desired projects have been added, it time to update the conditional formatting in column O. Before formatting, note the row number of the last project entered, you'll need it for formatting. Click anywhere in the column O and then go up to the ribbon on the "Home" tab, find the group "Styles." The first button in the Styles group should be "Conditional Formatting." Click the tool button show the entire menu, then select the very last item "Manage Rules."
37 | There are three color rules. In the "Applied as" column of each rule, update the last part of the formula with the row number of last project entered on the Summary page. For example, if the formula is =$O$39 and the new last row number is 42, then the formula should read =$O$42.
38 | To finish, go to the column "C" (Status) filter and unselect the two boxes for "Archived" projects and the one for "Voided" projects. Then click okay.
39 | Instructions for Adding Projects to the Roster Tab
40 | This one is a bit easier also. There should not be any hidden columns in this tab, but check to be sure.
41 | Select the column on the far right that has "HOME" in the first row. Right click and select "Insert" from the pop up menu. This will insert a new column in the correct spot with the proper formatting.
42 | Within Row 2 of the new column, enter the desired project number (e.g., YYYY-##). Press enter.
43 | On the same cell in Row 2 of the desired project number, RIGHT click the cell to show the pop up menu. Select "Hyperlink." When the dialog box opens, navigate up using the up arrow only a few items to find the desired project name (i.e., worksheet/tab). Double click the desired project to link it to the cell or click it once to highlight it and then click the okay button.
44 | If a project has multiple parts, consider adding shading or a pattern to draw attention that there are multiple components.
45 | Since this information is fairly static, the number of standards shown in the grid requires manual updating. It's a good idea to check it from time to time.
46 | Instructions for Removing a Project on the Roster Tab
47 | To remove a project, simply RIGHT click the column header of the desired project to reveal the pop up menu. Click on "Delete." to remove the column.
48 | The good news is that this tab will adjust the conditional formatting automatically, but verify it worked correctly before moving on.
49 | Instructions for Removing an Individual on the Roster Tab
50 | To remove an individual, simply RIGHT click the Row header of the desired person to reveal the pop up menu. Click on "Delete." to remove the row.
51 | The good news is that this tab will adjust the conditional formatting automatically, but verify it worked correctly before moving on.
52 | Update the PTS Change Control history when a member is removed.
53 | Instructions for Adding an Individual on the Roster Tab
54 | To add an individual at the end of the list or somewhere in between, simply RIGHT click the Row header of the row below where you want to add the individual to reveal the pop up menu. Click on "Insert." to create a new the row.
55 | The good news is that this tab will adjust the conditional formatting automatically, but verify it worked correctly before moving on.
56 | Update the PTS Change Control history when a member is added.
57 | Instructions for Archiving a Project
58 | The PMOS generally moves to "Archive" a project once it has been filed rather than approved. The reason is that once filed, the project has completed the process under the SPM. Also, should there be a directive to make an addition or change to a standard in the project once approved by regulatory authorities, a new project would be initiated (generally).
59 | Set the "Status" on the project to "Archived."
60 | Update the PTS change control to when the PMOS archived the project. Note any last thoughts on how the project timing went (e.g., based on complexity factors, etc.) Be sure the page is set to the top of the screen by clicking anywhere in the second Row.
61 | Change the project tab color from BLUE to RED and then "hide" the project. Changing the tab to red creates a visual in case the project is unhidden later and the user forgets to re-hide it. No red tabs should be showing for posting.
62 | Go to the "Roster" tab and remove the project that has been archived. No need to update the PTS Change Control. Be sure the page is set to the top of the screen by clicking anywhere in the second Row.
63 | Go to the "Summary" tab and select the filter for "Status." Since a number of updates may have been done during this setting, make sure ALL items are selected, EXCEPT the two "archived" items and the one "voided" item. Click "okay" to set the Summary tab. Be sure the page is set to the top of the screen by clicking anywhere in the second Row.
64 | Go to the "HOME" tab and set the Baseline/Current (Column F) cell value for the project being archived to "Archived Baseline," or "Archived Complexity Factor," or "Archived Current," as the case may be. Click okay.
65 | While on the HOME tab, save the file and close. It' ready for posting.

## Complexity Template (hidden)
Project | Standard Developer Baseline Template | [5 empty] | Home
Project Name | Complexity Factor Example
Status | Other
Comments | This is a test project for the PMOS to test and consider the use of complexity factors related to project scheduling.
Deliverable | Apply complexity factors to active projects and to project template going forward
Deadline | 2025-04-15 15:19 |  |  |  | 12 | Months to deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | Enter # in column B and description here. This value is 1 of 2 items that calculate the project baseline. If zero, delete this text.
Reserved for Future Use | N/A
Reserved for Future Use | N/A
Developer | TBD
PMOS Liaison | TBD
Affected Standards | 1 | Enter number of Affected Standards in column B and the Standard here (e.g. TOP-001-4). This value is 2 of 2 items that calculate the project baseline.
Last Updated
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | N/A | 0 | 1
AS2 - Additional SAR 2 | [5 empty] | N/A | 0 | 2
QR - Quality Review | [5 empty] | N/A | 0 | 3
SP1 - SAR/PR/WP Posting 1 | 2024-04-15 15:19 | 2024-05-15 15:19 | 2024-04-15 15:19 | 2024-05-15 15:19 | 0 | N/A | 0 | 4
SAR - SAR Revise/Response |  |  | 2024-07-14 15:19 | 2024-09-12 15:19
SDT - Dev Time | 2024-10-12 15:19 | 2025-01-10 15:19 | 2024-10-12 15:19 | 2025-01-10 15:19 | 0 | N/A | 0 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2025-02-24 15:19 | 2025-04-10 15:19 | 2025-02-24 15:19 | 2025-04-10 15:19 | 0 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2025-07-09 15:19 | 2025-08-23 15:19 | 2025-07-09 15:19 | 2025-08-23 15:19 | 0 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2025-09-22 15:19 | 2025-10-02 15:19 | 2025-09-22 15:19 | 2025-10-02 15:19 | 0 | N/A | 0 | 13
PTB - Present to BOT | [5 empty] | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
[6 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | 0 | Calculated CF Date: | 2025-10-02 15:19
PTS Change Control
Reason for Update | Date | Notes
SC Action |  | SC authorized SAR posting and solicitation of the SAR DT.
Formulas:
Standard Developer Baseline Template = +[Calculated Start]
Projected or Actual End = +[Standard Developer Baseline Template]+30
Projected or Actual End = +[Calculated End]
Calculated Start = [Calculated End, row above]+60
Calculated Start = +[Calculated End, row above]+30
Calculated End = +[Calculated Start]+30
Calculated End = [Calculated Start]+60
Home = D22+(E32-D22)+SUM(H19:[Home, row above])
Note on D22: Enter SC SAR date here
Note on A23: Chris Larson: PROPOSED ADD for SAR DT phase
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## Lookup Lists (hidden)
LOOKUP LISTS |  |  |  |  | Home
Delays | Status | Periods | Period Days | Complexity_Factor | CF_Days
Additional Outreach | Approved | Nominations - SAR / PR | 60 | Action Deferred | 30
Baseline Reset | Archived | SP1 - SAR/PR/WP Posting 1 | 60 | Additional Comment/Ballot | 60
Change in Approach | Archived-Not for Metrics | SP2 - SAR/PR/WP Posting 2 | 60 | Additional Outreach | 30
Expanded Scope | Filed | Nominations - DT | 60 | Change in Approach | 90
Missed SC Delivery | Inactive | CP1 - Comment Period 1 | 45 | Change in Developer | 30
Not needed | Metrics | CP2 - Comment Period 2 | 45 | Cross-Coordination (Finish-Start) | 90
Other | Metrics-Pre 2009 | QR - Quality Review | 30 | Cross-Coordination (Parallel) | 90
Regulatory Meeting | Metrics-Pre 2013 | CIB - Com/Ballot 1 (Initial) | 80 | Directive Added to Scope | 60
Schedule too Constrictive | Nominations | CAB - Com/Add Ballot 2 | 80 | Eliminated Comment Period | -60
Team Availability | Nominations & SAR | CAB - Com/Add Ballot 3 |  | Field Test | 365
x-Future | On Hold | CAB - Com/Add Ballot 4 |  | Highly Technical | 90
x-Future | Other | CAB - Com/Add Ballot 5 |  | Industry Survey | 30
x-Future | Pending Board Adoption | FB - Final Ballot | 30 | Intentional Hold/Delay | 30
x-Future | Pending Regulatory Approval | PTB - Present to BOT |  | N/A | 0
| Pending Regulatory Filing | Filing - Filing with Regulators |  | Pandemic | 90
| Pending SC Action | PT - Post Approval Training |  | Posting Conflict | 7
| Posted |  | 550 | Project Split or Phased | -60
| Responding to Comment |  |  | Research Required | 180
| SAR / PR / WP |  |  | RSDP Priority Decrease | 60
| SDT Development |  |  | RSDP Priority Increase | -60
| Standing Review Team |  |  | SAR - Revised/Additional Posting | 60
| Void |  |  | SAR - Supplemental | 60
| Working to Additional Ballot |  |  | SC Appoints SAR Team as SDT | -60
| Working to Comment Posting |  |  | Schedule Too Aggressive | 90
| Working to Final Ballot |  |  | Schedule Too Conservative | -90
| Working to Initial Ballot |  |  | Standard Added to Scope | 60
|  |  |  | Standard Developer Change | 30
|  |  |  | Supplemental members | 60
|  |  |  | Team Augmented | 60
|  |  |  | Team Coordination (e.g., Weather) | 30
|  |  |  | Team Coordination/Availability | 30
|  |  |  | Technical Work Required | 180
|  |  |  | Unplanned Team Meeting | 30
|  |  |  | Unplanned Technical Workshop | 30

## Home
|  |  |  | Updated: | 2024-04-15 | [2556 empty] | Add SAR | [29 empty] | QR | [14 empty] | SAR/SDT | [39 empty] | Std Dev | [38 empty] | Comment Only | [48 empty] | Comm & Ballot | [58 empty] | Final Ballot | [45 empty] | BOT | [23 empty] | Filing | [436 empty] | Add SAR | [29 empty] | QR | [14 empty] | SAR/SDT | [39 empty] | Std Dev | [38 empty] | Comment Only | [48 empty] | Comm & Ballot | [58 empty] | Final Ballot
[5 empty] | Baseline / Complexity |  | 2015 | [364 empty] | 2016 | [365 empty] | 2017 | [364 empty] | 2018 | [364 empty] | 2019 | [364 empty] | 2020 | [365 empty] | 2021 | [364 empty] | 2022 | [364 empty] | 2023 | [364 empty] | 2024
| Status | HOME | DO NOT SORT (Filtering Ok) | Early/(Late) | Factor / Status | <future> | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [28 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | June | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [28 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec
Index | Update | List of Approved Projects (Filter) | Deliverables (Filter) | Days (Filter) | (Filter) | Filter | 2015-01-01 | 2015-01-02 | 2015-01-03 | 2015-01-04 | 2015-01-05 | 2015-01-06 | 2015-01-07 | 2015-01-08 | 2015-01-09 | 2015-01-10 | 2015-01-11 | 2015-01-12 | 2015-01-13 | 2015-01-14 | 2015-01-15 | 2015-01-16 | 2015-01-17 | 2015-01-18 | 2015-01-19 | 2015-01-20 | 2015-01-21 | 2015-01-22 | 2015-01-23 | 2015-01-24 | 2015-01-25 | 2015-01-26 | 2015-01-27 | 2015-01-28 | 2015-01-29 | 2015-01-30 | 2015-01-31 | 2015-02-01 | 2015-02-02 | 2015-02-03 | 2015-02-04 | 2015-02-05 | 2015-02-06 | 2015-02-07 | 2015-02-08 | 2015-02-09 | 2015-02-10 | 2015-02-11 | 2015-02-12 | 2015-02-13 | 2015-02-14 | 2015-02-15 | 2015-02-16 | 2015-02-17 | 2015-02-18 | 2015-02-19 | 2015-02-20 | 2015-02-21 | 2015-02-22 | 2015-02-23 | 2015-02-24 | 2015-02-25 | 2015-02-26 | 2015-02-27 | 2015-02-28 | 2015-03-01 | 2015-03-02 | 2015-03-03 | 2015-03-04 | 2015-03-05 | 2015-03-06 | 2015-03-07 | 2015-03-08 | 2015-03-09 | 2015-03-10 | 2015-03-11 | 2015-03-12 | 2015-03-13 | 2015-03-14 | 2015-03-15 | 2015-03-16 | 2015-03-17 | 2015-03-18 | 2015-03-19 | 2015-03-20 | 2015-03-21 | 2015-03-22 | 2015-03-23 | 2015-03-24 | 2015-03-25 | 2015-03-26 | 2015-03-27 | 2015-03-28 | 2015-03-29 | 2015-03-30 | 2015-03-31 | 2015-04-01 | 2015-04-02 | 2015-04-03 | 2015-04-04 | 2015-04-05 | 2015-04-06 | 2015-04-07 | 2015-04-08 | 2015-04-09 | 2015-04-10 | 2015-04-11 | 2015-04-12 | 2015-04-13 | 2015-04-14 | 2015-04-15 | 2015-04-16 | 2015-04-17 | 2015-04-18 | 2015-04-19 | 2015-04-20 | 2015-04-21 | 2015-04-22 | 2015-04-23 | 2015-04-24 | 2015-04-25 | 2015-04-26 | 2015-04-27 | 2015-04-28 | 2015-04-29 | 2015-04-30 | 2015-05-01 | 2015-05-02 | 2015-05-03 | 2015-05-04 | 2015-05-05 | 2015-05-06 | 2015-05-07 | 2015-05-08 | 2015-05-09 | 2015-05-10 | 2015-05-11 | 2015-05-12 | 2015-05-13 | 2015-05-14 | 2015-05-15 | 2015-05-16 | 2015-05-17 | 2015-05-18 | 2015-05-19 | 2015-05-20 | 2015-05-21 | 2015-05-22 | 2015-05-23 | 2015-05-24 | 2015-05-25 | 2015-05-26 | 2015-05-27 | 2015-05-28 | 2015-05-29 | 2015-05-30 | 2015-05-31 | 2015-06-01 | 2015-06-02 | 2015-06-03 | 2015-06-04 | 2015-06-05 | 2015-06-06 | 2015-06-07 | 2015-06-08 | 2015-06-09 | 2015-06-10 | 2015-06-11 | 2015-06-12 | 2015-06-13 | 2015-06-14 | 2015-06-15 | 2015-06-16 | 2015-06-17 | 2015-06-18 | 2015-06-19 | 2015-06-20 | 2015-06-21 | 2015-06-22 | 2015-06-23 | 2015-06-24 | 2015-06-25 | 2015-06-26 | 2015-06-27 | 2015-06-28 | 2015-06-29 | 2015-06-30 | 2015-07-01 | 2015-07-02 | 2015-07-03 | 2015-07-04 | 2015-07-05 | 2015-07-06 | 2015-07-07 | 2015-07-08 | 2015-07-09 | 2015-07-10 | 2015-07-11 | 2015-07-12 | 2015-07-13 | 2015-07-14 | 2015-07-15 | 2015-07-16 | 2015-07-17 | 2015-07-18 | 2015-07-19 | 2015-07-20 | 2015-07-21 | 2015-07-22 | 2015-07-23 | 2015-07-24 | 2015-07-25 | 2015-07-26 | 2015-07-27 | 2015-07-28 | 2015-07-29 | 2015-07-30 | 2015-07-31 | 2015-08-01 | 2015-08-02 | 2015-08-03 | 2015-08-04 | 2015-08-05 | 2015-08-06 | 2015-08-07 | 2015-08-08 | 2015-08-09 | 2015-08-10 | 2015-08-11 | 2015-08-12 | 2015-08-13 | 2015-08-14 | 2015-08-15 | 2015-08-16 | 2015-08-17 | 2015-08-18 | 2015-08-19 | 2015-08-20 | 2015-08-21 | 2015-08-22 | 2015-08-23 | 2015-08-24 | 2015-08-25 | 2015-08-26 | 2015-08-27 | 2015-08-28 | 2015-08-29 | 2015-08-30 | 2015-08-31 | 2015-09-01 | 2015-09-02 | 2015-09-03 | 2015-09-04 | 2015-09-05 | 2015-09-06 | 2015-09-07 | 2015-09-08 | 2015-09-09 | 2015-09-10 | 2015-09-11 | 2015-09-12 | 2015-09-13 | 2015-09-14 | 2015-09-15 | 2015-09-16 | 2015-09-17 | 2015-09-18 | 2015-09-19 | 2015-09-20 | 2015-09-21 | 2015-09-22 | 2015-09-23 | 2015-09-24 | 2015-09-25 | 2015-09-26 | 2015-09-27 | 2015-09-28 | 2015-09-29 | 2015-09-30 | 2015-10-01 | 2015-10-02 | 2015-10-03 | 2015-10-04 | 2015-10-05 | 2015-10-06 | 2015-10-07 | 2015-10-08 | 2015-10-09 | 2015-10-10 | 2015-10-11 | 2015-10-12 | 2015-10-13 | 2015-10-14 | 2015-10-15 | 2015-10-16 | 2015-10-17 | 2015-10-18 | 2015-10-19 | 2015-10-20 | 2015-10-21 | 2015-10-22 | 2015-10-23 | 2015-10-24 | 2015-10-25 | 2015-10-26 | 2015-10-27 | 2015-10-28 | 2015-10-29 | 2015-10-30 | 2015-10-31 | 2015-11-01 | 2015-11-02 | 2015-11-03 | 2015-11-04 | 2015-11-05 | 2015-11-06 | 2015-11-07 | 2015-11-08 | 2015-11-09 | 2015-11-10 | 2015-11-11 | 2015-11-12 | 2015-11-13 | 2015-11-14 | 2015-11-15 | 2015-11-16 | 2015-11-17 | 2015-11-18 | 2015-11-19 | 2015-11-20 | 2015-11-21 | 2015-11-22 | 2015-11-23 | 2015-11-24 | 2015-11-25 | 2015-11-26 | 2015-11-27 | 2015-11-28 | 2015-11-29 | 2015-11-30 | 2015-12-01 | 2015-12-02 | 2015-12-03 | 2015-12-04 | 2015-12-05 | 2015-12-06 | 2015-12-07 | 2015-12-08 | 2015-12-09 | 2015-12-10 | 2015-12-11 | 2015-12-12 | 2015-12-13 | 2015-12-14 | 2015-12-15 | 2015-12-16 | 2015-12-17 | 2015-12-18 | 2015-12-19 | 2015-12-20 | 2015-12-21 | 2015-12-22 | 2015-12-23 | 2015-12-24 | 2015-12-25 | 2015-12-26 | 2015-12-27 | 2015-12-28 | 2015-12-29 | 2015-12-30 | 2015-12-31 | 2016-01-01 | 2016-01-02 | 2016-01-03 | 2016-01-04 | 2016-01-05 | 2016-01-06 | 2016-01-07 | 2016-01-08 | 2016-01-09 | 2016-01-10 | 2016-01-11 | 2016-01-12 | 2016-01-13 | 2016-01-14 | 2016-01-15 | 2016-01-16 | 2016-01-17 | 2016-01-18 | 2016-01-19 | 2016-01-20 | 2016-01-21 | 2016-01-22 | 2016-01-23 | 2016-01-24 | 2016-01-25 | 2016-01-26 | 2016-01-27 | 2016-01-28 | 2016-01-29 | 2016-01-30 | 2016-01-31 | 2016-02-01 | 2016-02-02 | 2016-02-03 | 2016-02-04 | 2016-02-05 | 2016-02-06 | 2016-02-07 | 2016-02-08 | 2016-02-09 | 2016-02-10 | 2016-02-11 | 2016-02-12 | 2016-02-13 | 2016-02-14 | 2016-02-15 | 2016-02-16 | 2016-02-17 | 2016-02-18 | 2016-02-19 | 2016-02-20 | 2016-02-21 | 2016-02-22 | 2016-02-23 | 2016-02-24 | 2016-02-25 | 2016-02-26 | 2016-02-27 | 2016-02-28 | 2016-02-29 | 2016-03-01 | 2016-03-02 | 2016-03-03 | 2016-03-04 | 2016-03-05 | 2016-03-06 | 2016-03-07 | 2016-03-08 | 2016-03-09 | 2016-03-10 | 2016-03-11 | 2016-03-12 | 2016-03-13 | 2016-03-14 | 2016-03-15 | 2016-03-16 | 2016-03-17 | 2016-03-18 | 2016-03-19 | 2016-03-20 | 2016-03-21 | 2016-03-22 | 2016-03-23 | 2016-03-24 | 2016-03-25 | 2016-03-26 | 2016-03-27 | 2016-03-28 | 2016-03-29 | 2016-03-30 | 2016-03-31 | 2016-04-01 | 2016-04-02 | 2016-04-03 | 2016-04-04 | 2016-04-05 | 2016-04-06 | 2016-04-07 | 2016-04-08 | 2016-04-09 | 2016-04-10 | 2016-04-11 | 2016-04-12 | 2016-04-13 | 2016-04-14 | 2016-04-15 | 2016-04-16 | 2016-04-17 | 2016-04-18 | 2016-04-19 | 2016-04-20 | 2016-04-21 | 2016-04-22 | 2016-04-23 | 2016-04-24 | 2016-04-25 | 2016-04-26 | 2016-04-27 | 2016-04-28 | 2016-04-29 | 2016-04-30 | 2016-05-01 | 2016-05-02 | 2016-05-03 | 2016-05-04 | 2016-05-05 | 2016-05-06 | 2016-05-07 | 2016-05-08 | 2016-05-09 | 2016-05-10 | 2016-05-11 | 2016-05-12 | 2016-05-13 | 2016-05-14 | 2016-05-15 | 2016-05-16 | 2016-05-17 | 2016-05-18 | 2016-05-19 | 2016-05-20 | 2016-05-21 | 2016-05-22 | 2016-05-23 | 2016-05-24 | 2016-05-25 | 2016-05-26 | 2016-05-27 | 2016-05-28 | 2016-05-29 | 2016-05-30 | 2016-05-31 | 2016-06-01 | 2016-06-02 | 2016-06-03 | 2016-06-04 | 2016-06-05 | 2016-06-06 | 2016-06-07 | 2016-06-08 | 2016-06-09 | 2016-06-10 | 2016-06-11 | 2016-06-12 | 2016-06-13 | 2016-06-14 | 2016-06-15 | 2016-06-16 | 2016-06-17 | 2016-06-18 | 2016-06-19 | 2016-06-20 | 2016-06-21 | 2016-06-22 | 2016-06-23 | 2016-06-24 | 2016-06-25 | 2016-06-26 | 2016-06-27 | 2016-06-28 | 2016-06-29 | 2016-06-30 | 2016-07-01 | 2016-07-02 | 2016-07-03 | 2016-07-04 | 2016-07-05 | 2016-07-06 | 2016-07-07 | 2016-07-08 | 2016-07-09 | 2016-07-10 | 2016-07-11 | 2016-07-12 | 2016-07-13 | 2016-07-14 | 2016-07-15 | 2016-07-16 | 2016-07-17 | 2016-07-18 | 2016-07-19 | 2016-07-20 | 2016-07-21 | 2016-07-22 | 2016-07-23 | 2016-07-24 | 2016-07-25 | 2016-07-26 | 2016-07-27 | 2016-07-28 | 2016-07-29 | 2016-07-30 | 2016-07-31 | 2016-08-01 | 2016-08-02 | 2016-08-03 | 2016-08-04 | 2016-08-05 | 2016-08-06 | 2016-08-07 | 2016-08-08 | 2016-08-09 | 2016-08-10 | 2016-08-11 | 2016-08-12 | 2016-08-13 | 2016-08-14 | 2016-08-15 | 2016-08-16 | 2016-08-17 | 2016-08-18 | 2016-08-19 | 2016-08-20 | 2016-08-21 | 2016-08-22 | 2016-08-23 | 2016-08-24 | 2016-08-25 | 2016-08-26 | 2016-08-27 | 2016-08-28 | 2016-08-29 | 2016-08-30 | 2016-08-31 | 2016-09-01 | 2016-09-02 | 2016-09-03 | 2016-09-04 | 2016-09-05 | 2016-09-06 | 2016-09-07 | 2016-09-08 | 2016-09-09 | 2016-09-10 | 2016-09-11 | 2016-09-12 | 2016-09-13 | 2016-09-14 | 2016-09-15 | 2016-09-16 | 2016-09-17 | 2016-09-18 | 2016-09-19 | 2016-09-20 | 2016-09-21 | 2016-09-22 | 2016-09-23 | 2016-09-24 | 2016-09-25 | 2016-09-26 | 2016-09-27 | 2016-09-28 | 2016-09-29 | 2016-09-30 | 2016-10-01 | 2016-10-02 | 2016-10-03 | 2016-10-04 | 2016-10-05 | 2016-10-06 | 2016-10-07 | 2016-10-08 | 2016-10-09 | 2016-10-10 | 2016-10-11 | 2016-10-12 | 2016-10-13 | 2016-10-14 | 2016-10-15 | 2016-10-16 | 2016-10-17 | 2016-10-18 | 2016-10-19 | 2016-10-20 | 2016-10-21 | 2016-10-22 | 2016-10-23 | 2016-10-24 | 2016-10-25 | 2016-10-26 | 2016-10-27 | 2016-10-28 | 2016-10-29 | 2016-10-30 | 2016-10-31 | 2016-11-01 | 2016-11-02 | 2016-11-03 | 2016-11-04 | 2016-11-05 | 2016-11-06 | 2016-11-07 | 2016-11-08 | 2016-11-09 | 2016-11-10 | 2016-11-11 | 2016-11-12 | 2016-11-13 | 2016-11-14 | 2016-11-15 | 2016-11-16 | 2016-11-17 | 2016-11-18 | 2016-11-19 | 2016-11-20 | 2016-11-21 | 2016-11-22 | 2016-11-23 | 2016-11-24 | 2016-11-25 | 2016-11-26 | 2016-11-27 | 2016-11-28 | 2016-11-29 | 2016-11-30 | 2016-12-01 | 2016-12-02 | 2016-12-03 | 2016-12-04 | 2016-12-05 | 2016-12-06 | 2016-12-07 | 2016-12-08 | 2016-12-09 | 2016-12-10 | 2016-12-11 | 2016-12-12 | 2016-12-13 | 2016-12-14 | 2016-12-15 | 2016-12-16 | 2016-12-17 | 2016-12-18 | 2016-12-19 | 2016-12-20 | 2016-12-21 | 2016-12-22 | 2016-12-23 | 2016-12-24 | 2016-12-25 | 2016-12-26 | 2016-12-27 | 2016-12-28 | 2016-12-29 | 2016-12-30 | 2016-12-31 | 2017-01-01 | 2017-01-02 | 2017-01-03 | 2017-01-04 | 2017-01-05 | 2017-01-06 | 2017-01-07 | 2017-01-08 | 2017-01-09 | 2017-01-10 | 2017-01-11 | 2017-01-12 | 2017-01-13 | 2017-01-14 | 2017-01-15 | 2017-01-16 | 2017-01-17 | 2017-01-18 | 2017-01-19 | 2017-01-20 | 2017-01-21 | 2017-01-22 | 2017-01-23 | 2017-01-24 | 2017-01-25 | 2017-01-26 | 2017-01-27 | 2017-01-28 | 2017-01-29 | 2017-01-30 | 2017-01-31 | 2017-02-01 | 2017-02-02 | 2017-02-03 | 2017-02-04 | 2017-02-05 | 2017-02-06 | 2017-02-07 | 2017-02-08 | 2017-02-09 | 2017-02-10 | 2017-02-11 | 2017-02-12 | 2017-02-13 | 2017-02-14 | 2017-02-15 | 2017-02-16 | 2017-02-17 | 2017-02-18 | 2017-02-19 | 2017-02-20 | 2017-02-21 | 2017-02-22 | 2017-02-23 | 2017-02-24 | 2017-02-25 | 2017-02-26 | 2017-02-27 | 2017-02-28 | 2017-03-01 | 2017-03-02 | 2017-03-03 | 2017-03-04 | 2017-03-05 | 2017-03-06 | 2017-03-07 | 2017-03-08 | 2017-03-09 | 2017-03-10 | 2017-03-11 | 2017-03-12 | 2017-03-13 | 2017-03-14 | 2017-03-15 | 2017-03-16 | 2017-03-17 | 2017-03-18 | 2017-03-19 | 2017-03-20 | 2017-03-21 | 2017-03-22 | 2017-03-23 | 2017-03-24 | 2017-03-25 | 2017-03-26 | 2017-03-27 | 2017-03-28 | 2017-03-29 | 2017-03-30 | 2017-03-31 | 2017-04-01 | 2017-04-02 | 2017-04-03 | 2017-04-04 | 2017-04-05 | 2017-04-06 | 2017-04-07 | 2017-04-08 | 2017-04-09 | 2017-04-10 | 2017-04-11 | 2017-04-12 | 2017-04-13 | 2017-04-14 | 2017-04-15 | 2017-04-16 | 2017-04-17 | 2017-04-18 | 2017-04-19 | 2017-04-20 | 2017-04-21 | 2017-04-22 | 2017-04-23 | 2017-04-24 | 2017-04-25 | 2017-04-26 | 2017-04-27 | 2017-04-28 | 2017-04-29 | 2017-04-30 | 2017-05-01 | 2017-05-02 | 2017-05-03 | 2017-05-04 | 2017-05-05 | 2017-05-06 | 2017-05-07 | 2017-05-08 | 2017-05-09 | 2017-05-10 | 2017-05-11 | 2017-05-12 | 2017-05-13 | 2017-05-14 | 2017-05-15 | 2017-05-16 | 2017-05-17 | 2017-05-18 | 2017-05-19 | 2017-05-20 | 2017-05-21 | 2017-05-22 | 2017-05-23 | 2017-05-24 | 2017-05-25 | 2017-05-26 | 2017-05-27 | 2017-05-28 | 2017-05-29 | 2017-05-30 | 2017-05-31 | 2017-06-01 | 2017-06-02 | 2017-06-03 | 2017-06-04 | 2017-06-05 | 2017-06-06 | 2017-06-07 | 2017-06-08 | 2017-06-09 | 2017-06-10 | 2017-06-11 | 2017-06-12 | 2017-06-13 | 2017-06-14 | 2017-06-15 | 2017-06-16 | 2017-06-17 | 2017-06-18 | 2017-06-19 | 2017-06-20 | 2017-06-21 | 2017-06-22 | 2017-06-23 | 2017-06-24 | 2017-06-25 | 2017-06-26 | 2017-06-27 | 2017-06-28 | 2017-06-29 | 2017-06-30 | 2017-07-01 | 2017-07-02 | 2017-07-03 | 2017-07-04 | 2017-07-05 | 2017-07-06 | 2017-07-07 | 2017-07-08 | 2017-07-09 | 2017-07-10 | 2017-07-11 | 2017-07-12 | 2017-07-13 | 2017-07-14 | 2017-07-15 | 2017-07-16 | 2017-07-17 | 2017-07-18 | 2017-07-19 | 2017-07-20 | 2017-07-21 | 2017-07-22 | 2017-07-23 | 2017-07-24 | 2017-07-25 | 2017-07-26 | 2017-07-27 | 2017-07-28 | 2017-07-29 | 2017-07-30 | 2017-07-31 | 2017-08-01 | 2017-08-02 | 2017-08-03 | 2017-08-04 | 2017-08-05 | 2017-08-06 | 2017-08-07 | 2017-08-08 | 2017-08-09 | 2017-08-10 | 2017-08-11 | 2017-08-12 | 2017-08-13 | 2017-08-14 | 2017-08-15 | 2017-08-16 | 2017-08-17 | 2017-08-18 | 2017-08-19 | 2017-08-20 | 2017-08-21 | 2017-08-22 | 2017-08-23 | 2017-08-24 | 2017-08-25 | 2017-08-26 | 2017-08-27 | 2017-08-28 | 2017-08-29 | 2017-08-30 | 2017-08-31 | 2017-09-01 | 2017-09-02 | 2017-09-03 | 2017-09-04 | 2017-09-05 | 2017-09-06 | 2017-09-07 | 2017-09-08 | 2017-09-09 | 2017-09-10 | 2017-09-11 | 2017-09-12 | 2017-09-13 | 2017-09-14 | 2017-09-15 | 2017-09-16 | 2017-09-17 | 2017-09-18 | 2017-09-19 | 2017-09-20 | 2017-09-21 | 2017-09-22 | 2017-09-23 | 2017-09-24 | 2017-09-25 | 2017-09-26 | 2017-09-27 | 2017-09-28 | 2017-09-29 | 2017-09-30 | 2017-10-01 | 2017-10-02 | 2017-10-03 | 2017-10-04 | 2017-10-05 | 2017-10-06 | 2017-10-07 | 2017-10-08 | 2017-10-09 | 2017-10-10 | 2017-10-11 | 2017-10-12 | 2017-10-13 | 2017-10-14 | 2017-10-15 | 2017-10-16 | 2017-10-17 | 2017-10-18 | 2017-10-19 | 2017-10-20 | 2017-10-21 | 2017-10-22 | 2017-10-23 | 2017-10-24 | 2017-10-25 | 2017-10-26 | 2017-10-27 | 2017-10-28 | 2017-10-29 | 2017-10-30 | 2017-10-31 | 2017-11-01 | 2017-11-02 | 2017-11-03 | 2017-11-04 | 2017-11-05 | 2017-11-06 | 2017-11-07 | 2017-11-08 | 2017-11-09 | 2017-11-10 | 2017-11-11 | 2017-11-12 | 2017-11-13 | 2017-11-14 | 2017-11-15 | 2017-11-16 | 2017-11-17 | 2017-11-18 | 2017-11-19 | 2017-11-20 | 2017-11-21 | 2017-11-22 | 2017-11-23 | 2017-11-24 | 2017-11-25 | 2017-11-26 | 2017-11-27 | 2017-11-28 | 2017-11-29 | 2017-11-30 | 2017-12-01 | 2017-12-02 | 2017-12-03 | 2017-12-04 | 2017-12-05 | 2017-12-06 | 2017-12-07 | 2017-12-08 | 2017-12-09 | 2017-12-10 | 2017-12-11 | 2017-12-12 | 2017-12-13 | 2017-12-14 | 2017-12-15 | 2017-12-16 | 2017-12-17 | 2017-12-18 | 2017-12-19 | 2017-12-20 | 2017-12-21 | 2017-12-22 | 2017-12-23 | 2017-12-24 | 2017-12-25 | 2017-12-26 | 2017-12-27 | 2017-12-28 | 2017-12-29 | 2017-12-30 | 2017-12-31 | 2018-01-01 | 2018-01-02 | 2018-01-03 | 2018-01-04 | 2018-01-05 | 2018-01-06 | 2018-01-07 | 2018-01-08 | 2018-01-09 | 2018-01-10 | 2018-01-11 | 2018-01-12 | 2018-01-13 | 2018-01-14 | 2018-01-15 | 2018-01-16 | 2018-01-17 | 2018-01-18 | 2018-01-19 | 2018-01-20 | 2018-01-21 | 2018-01-22 | 2018-01-23 | 2018-01-24 | 2018-01-25 | 2018-01-26 | 2018-01-27 | 2018-01-28 | 2018-01-29 | 2018-01-30 | 2018-01-31 | 2018-02-01 | 2018-02-02 | 2018-02-03 | 2018-02-04 | 2018-02-05 | 2018-02-06 | 2018-02-07 | 2018-02-08 | 2018-02-09 | 2018-02-10 | 2018-02-11 | 2018-02-12 | 2018-02-13 | 2018-02-14 | 2018-02-15 | 2018-02-16 | 2018-02-17 | 2018-02-18 | 2018-02-19 | 2018-02-20 | 2018-02-21 | 2018-02-22 | 2018-02-23 | 2018-02-24 | 2018-02-25 | 2018-02-26 | 2018-02-27 | 2018-02-28 | 2018-03-01 | 2018-03-02 | 2018-03-03 | 2018-03-04 | 2018-03-05 | 2018-03-06 | 2018-03-07 | 2018-03-08 | 2018-03-09 | 2018-03-10 | 2018-03-11 | 2018-03-12 | 2018-03-13 | 2018-03-14 | 2018-03-15 | 2018-03-16 | 2018-03-17 | 2018-03-18 | 2018-03-19 | 2018-03-20 | 2018-03-21 | 2018-03-22 | 2018-03-23 | 2018-03-24 | 2018-03-25 | 2018-03-26 | 2018-03-27 | 2018-03-28 | 2018-03-29 | 2018-03-30 | 2018-03-31 | 2018-04-01 | 2018-04-02 | 2018-04-03 | 2018-04-04 | 2018-04-05 | 2018-04-06 | 2018-04-07 | 2018-04-08 | 2018-04-09 | 2018-04-10 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 2018-04-14 | 2018-04-15 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 2018-04-20 | 2018-04-21 | 2018-04-22 | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28 | 2018-04-29 | 2018-04-30 | 2018-05-01 | 2018-05-02 | 2018-05-03 | 2018-05-04 | 2018-05-05 | 2018-05-06 | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-12 | 2018-05-13 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-19 | 2018-05-20 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-26 | 2018-05-27 | 2018-05-28 | 2018-05-29 | 2018-05-30 | 2018-05-31 | 2018-06-01 | 2018-06-02 | 2018-06-03 | 2018-06-04 | 2018-06-05 | 2018-06-06 | 2018-06-07 | 2018-06-08 | 2018-06-09 | 2018-06-10 | 2018-06-11 | 2018-06-12 | 2018-06-13 | 2018-06-14 | 2018-06-15 | 2018-06-16 | 2018-06-17 | 2018-06-18 | 2018-06-19 | 2018-06-20 | 2018-06-21 | 2018-06-22 | 2018-06-23 | 2018-06-24 | 2018-06-25 | 2018-06-26 | 2018-06-27 | 2018-06-28 | 2018-06-29 | 2018-06-30 | 2018-07-01 | 2018-07-02 | 2018-07-03 | 2018-07-04 | 2018-07-05 | 2018-07-06 | 2018-07-07 | 2018-07-08 | 2018-07-09 | 2018-07-10 | 2018-07-11 | 2018-07-12 | 2018-07-13 | 2018-07-14 | 2018-07-15 | 2018-07-16 | 2018-07-17 | 2018-07-18 | 2018-07-19 | 2018-07-20 | 2018-07-21 | 2018-07-22 | 2018-07-23 | 2018-07-24 | 2018-07-25 | 2018-07-26 | 2018-07-27 | 2018-07-28 | 2018-07-29 | 2018-07-30 | 2018-07-31 | 2018-08-01 | 2018-08-02 | 2018-08-03 | 2018-08-04 | 2018-08-05 | 2018-08-06 | 2018-08-07 | 2018-08-08 | 2018-08-09 | 2018-08-10 | 2018-08-11 | 2018-08-12 | 2018-08-13 | 2018-08-14 | 2018-08-15 | 2018-08-16 | 2018-08-17 | 2018-08-18 | 2018-08-19 | 2018-08-20 | 2018-08-21 | 2018-08-22 | 2018-08-23 | 2018-08-24 | 2018-08-25 | 2018-08-26 | 2018-08-27 | 2018-08-28 | 2018-08-29 | 2018-08-30 | 2018-08-31 | 2018-09-01 | 2018-09-02 | 2018-09-03 | 2018-09-04 | 2018-09-05 | 2018-09-06 | 2018-09-07 | 2018-09-08 | 2018-09-09 | 2018-09-10 | 2018-09-11 | 2018-09-12 | 2018-09-13 | 2018-09-14 | 2018-09-15 | 2018-09-16 | 2018-09-17 | 2018-09-18 | 2018-09-19 | 2018-09-20 | 2018-09-21 | 2018-09-22 | 2018-09-23 | 2018-09-24 | 2018-09-25 | 2018-09-26 | 2018-09-27 | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 2018-10-03 | 2018-10-04 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09 | 2018-10-10 | 2018-10-11 | 2018-10-12 | 2018-10-13 | 2018-10-14 | 2018-10-15 | 2018-10-16 | 2018-10-17 | 2018-10-18 | 2018-10-19 | 2018-10-20 | 2018-10-21 | 2018-10-22 | 2018-10-23 | 2018-10-24 | 2018-10-25 | 2018-10-26 | 2018-10-27 | 2018-10-28 | 2018-10-29 | 2018-10-30 | 2018-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-03 | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 | 2018-11-17 | 2018-11-18 | 2018-11-19 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-23 | 2018-11-24 | 2018-11-25 | 2018-11-26 | 2018-11-27 | 2018-11-28 | 2018-11-29 | 2018-11-30 | 2018-12-01 | 2018-12-02 | 2018-12-03 | 2018-12-04 | 2018-12-05 | 2018-12-06 | 2018-12-07 | 2018-12-08 | 2018-12-09 | 2018-12-10 | 2018-12-11 | 2018-12-12 | 2018-12-13 | 2018-12-14 | 2018-12-15 | 2018-12-16 | 2018-12-17 | 2018-12-18 | 2018-12-19 | 2018-12-20 | 2018-12-21 | 2018-12-22 | 2018-12-23 | 2018-12-24 | 2018-12-25 | 2018-12-26 | 2018-12-27 | 2018-12-28 | 2018-12-29 | 2018-12-30 | 2018-12-31 | 2019-01-01 | 2019-01-02 | 2019-01-03 | 2019-01-04 | 2019-01-05 | 2019-01-06 | 2019-01-07 | 2019-01-08 | 2019-01-09 | 2019-01-10 | 2019-01-11 | 2019-01-12 | 2019-01-13 | 2019-01-14 | 2019-01-15 | 2019-01-16 | 2019-01-17 | 2019-01-18 | 2019-01-19 | 2019-01-20 | 2019-01-21 | 2019-01-22 | 2019-01-23 | 2019-01-24 | 2019-01-25 | 2019-01-26 | 2019-01-27 | 2019-01-28 | 2019-01-29 | 2019-01-30 | 2019-01-31 | 2019-02-01 | 2019-02-02 | 2019-02-03 | 2019-02-04 | 2019-02-05 | 2019-02-06 | 2019-02-07 | 2019-02-08 | 2019-02-09 | 2019-02-10 | 2019-02-11 | 2019-02-12 | 2019-02-13 | 2019-02-14 | 2019-02-15 | 2019-02-16 | 2019-02-17 | 2019-02-18 | 2019-02-19 | 2019-02-20 | 2019-02-21 | 2019-02-22 | 2019-02-23 | 2019-02-24 | 2019-02-25 | 2019-02-26 | 2019-02-27 | 2019-02-28 | 2019-03-01 | 2019-03-02 | 2019-03-03 | 2019-03-04 | 2019-03-05 | 2019-03-06 | 2019-03-07 | 2019-03-08 | 2019-03-09 | 2019-03-10 | 2019-03-11 | 2019-03-12 | 2019-03-13 | 2019-03-14 | 2019-03-15 | 2019-03-16 | 2019-03-17 | 2019-03-18 | 2019-03-19 | 2019-03-20 | 2019-03-21 | 2019-03-22 | 2019-03-23 | 2019-03-24 | 2019-03-25 | 2019-03-26 | 2019-03-27 | 2019-03-28 | 2019-03-29 | 2019-03-30 | 2019-03-31 | 2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04 | 2019-04-05 | 2019-04-06 | 2019-04-07 | 2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | 2019-04-12 | 2019-04-13 | 2019-04-14 | 2019-04-15 | 2019-04-16 | 2019-04-17 | 2019-04-18 | 2019-04-19 | 2019-04-20 | 2019-04-21 | 2019-04-22 | 2019-04-23 | 2019-04-24 | 2019-04-25 | 2019-04-26 | 2019-04-27 | 2019-04-28 | 2019-04-29 | 2019-04-30 | 2019-05-01 | 2019-05-02 | 2019-05-03 | 2019-05-04 | 2019-05-05 | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09 | 2019-05-10 | 2019-05-11 | 2019-05-12 | 2019-05-13 | 2019-05-14 | 2019-05-15 | 2019-05-16 | 2019-05-17 | 2019-05-18 | 2019-05-19 | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-25 | 2019-05-26 | 2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30 | 2019-05-31 | 2019-06-01 | 2019-06-02 | 2019-06-03 | 2019-06-04 | 2019-06-05 | 2019-06-06 | 2019-06-07 | 2019-06-08 | 2019-06-09 | 2019-06-10 | 2019-06-11 | 2019-06-12 | 2019-06-13 | 2019-06-14 | 2019-06-15 | 2019-06-16 | 2019-06-17 | 2019-06-18 | 2019-06-19 | 2019-06-20 | 2019-06-21 | 2019-06-22 | 2019-06-23 | 2019-06-24 | 2019-06-25 | 2019-06-26 | 2019-06-27 | 2019-06-28 | 2019-06-29 | 2019-06-30 | 2019-07-01 | 2019-07-02 | 2019-07-03 | 2019-07-04 | 2019-07-05 | 2019-07-06 | 2019-07-07 | 2019-07-08 | 2019-07-09 | 2019-07-10 | 2019-07-11 | 2019-07-12 | 2019-07-13 | 2019-07-14 | 2019-07-15 | 2019-07-16 | 2019-07-17 | 2019-07-18 | 2019-07-19 | 2019-07-20 | 2019-07-21 | 2019-07-22 | 2019-07-23 | 2019-07-24 | 2019-07-25 | 2019-07-26 | 2019-07-27 | 2019-07-28 | 2019-07-29 | 2019-07-30 | 2019-07-31 | 2019-08-01 | 2019-08-02 | 2019-08-03 | 2019-08-04 | 2019-08-05 | 2019-08-06 | 2019-08-07 | 2019-08-08 | 2019-08-09 | 2019-08-10 | 2019-08-11 | 2019-08-12 | 2019-08-13 | 2019-08-14 | 2019-08-15 | 2019-08-16 | 2019-08-17 | 2019-08-18 | 2019-08-19 | 2019-08-20 | 2019-08-21 | 2019-08-22 | 2019-08-23 | 2019-08-24 | 2019-08-25 | 2019-08-26 | 2019-08-27 | 2019-08-28 | 2019-08-29 | 2019-08-30 | 2019-08-31 | 2019-09-01 | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-14 | 2019-09-15 | 2019-09-16 | 2019-09-17 | 2019-09-18 | 2019-09-19 | 2019-09-20 | 2019-09-21 | 2019-09-22 | 2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-28 | 2019-09-29 | 2019-09-30 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-05 | 2019-10-06 | 2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-12 | 2019-10-13 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-19 | 2019-10-20 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-27 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2019-11-01 | 2019-11-02 | 2019-11-03 | 2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14 | 2019-11-15 | 2019-11-16 | 2019-11-17 | 2019-11-18 | 2019-11-19 | 2019-11-20 | 2019-11-21 | 2019-11-22 | 2019-11-23 | 2019-11-24 | 2019-11-25 | 2019-11-26 | 2019-11-27 | 2019-11-28 | 2019-11-29 | 2019-11-30 | 2019-12-01 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06 | 2019-12-07 | 2019-12-08 | 2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12 | 2019-12-13 | 2019-12-14 | 2019-12-15 | 2019-12-16 | 2019-12-17 | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | 2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28 | 2019-12-29 | 2019-12-30 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05 | 2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11 | 2020-01-12 | 2020-01-13 | 2020-01-14 | 2020-01-15 | 2020-01-16 | 2020-01-17 | 2020-01-18 | 2020-01-19 | 2020-01-20 | 2020-01-21 | 2020-01-22 | 2020-01-23 | 2020-01-24 | 2020-01-25 | 2020-01-26 | 2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | 2020-02-01 | 2020-02-02 | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09 | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-15 | 2020-02-16 | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14 | 2020-03-15 | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28 | 2020-03-29 | 2020-03-30 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-04 | 2020-04-05 | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-11 | 2020-04-12 | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-18 | 2020-04-19 | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25 | 2020-04-26 | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01 | 2020-05-02 | 2020-05-03 | 2020-05-04 | 2020-05-05 | 2020-05-06 | 2020-05-07 | 2020-05-08 | 2020-05-09 | 2020-05-10 | 2020-05-11 | 2020-05-12 | 2020-05-13 | 2020-05-14 | 2020-05-15 | 2020-05-16 | 2020-05-17 | 2020-05-18 | 2020-05-19 | 2020-05-20 | 2020-05-21 | 2020-05-22 | 2020-05-23 | 2020-05-24 | 2020-05-25 | 2020-05-26 | 2020-05-27 | 2020-05-28 | 2020-05-29 | 2020-05-30 | 2020-05-31 | 2020-06-01 | 2020-06-02 | 2020-06-03 | 2020-06-04 | 2020-06-05 | 2020-06-06 | 2020-06-07 | 2020-06-08 | 2020-06-09 | 2020-06-10 | 2020-06-11 | 2020-06-12 | 2020-06-13 | 2020-06-14 | 2020-06-15 | 2020-06-16 | 2020-06-17 | 2020-06-18 | 2020-06-19 | 2020-06-20 | 2020-06-21 | 2020-06-22 | 2020-06-23 | 2020-06-24 | 2020-06-25 | 2020-06-26 | 2020-06-27 | 2020-06-28 | 2020-06-29 | 2020-06-30 | 2020-07-01 | 2020-07-02 | 2020-07-03 | 2020-07-04 | 2020-07-05 | 2020-07-06 | 2020-07-07 | 2020-07-08 | 2020-07-09 | 2020-07-10 | 2020-07-11 | 2020-07-12 | 2020-07-13 | 2020-07-14 | 2020-07-15 | 2020-07-16 | 2020-07-17 | 2020-07-18 | 2020-07-19 | 2020-07-20 | 2020-07-21 | 2020-07-22 | 2020-07-23 | 2020-07-24 | 2020-07-25 | 2020-07-26 | 2020-07-27 | 2020-07-28 | 2020-07-29 | 2020-07-30 | 2020-07-31 | 2020-08-01 | 2020-08-02 | 2020-08-03 | 2020-08-04 | 2020-08-05 | 2020-08-06 | 2020-08-07 | 2020-08-08 | 2020-08-09 | 2020-08-10 | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14 | 2020-08-15 | 2020-08-16 | 2020-08-17 | 2020-08-18 | 2020-08-19 | 2020-08-20 | 2020-08-21 | 2020-08-22 | 2020-08-23 | 2020-08-24 | 2020-08-25 | 2020-08-26 | 2020-08-27 | 2020-08-28 | 2020-08-29 | 2020-08-30 | 2020-08-31 | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-19 | 2020-09-20 | 2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27 | 2020-09-28 | 2020-09-29 | 2020-09-30 | 2020-10-01 | 2020-10-02 | 2020-10-03 | 2020-10-04 | 2020-10-05 | 2020-10-06 | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-10 | 2020-10-11 | 2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-17 | 2020-10-18 | 2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23 | 2020-10-24 | 2020-10-25 | 2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31 | 2020-11-01 | 2020-11-02 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-07 | 2020-11-08 | 2020-11-09 | 2020-11-10 | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-14 | 2020-11-15 | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-21 | 2020-11-22 | 2020-11-23 | 2020-11-24 | 2020-11-25 | 2020-11-26 | 2020-11-27 | 2020-11-28 | 2020-11-29 | 2020-11-30 | 2020-12-01 | 2020-12-02 | 2020-12-03 | 2020-12-04 | 2020-12-05 | 2020-12-06 | 2020-12-07 | 2020-12-08 | 2020-12-09 | 2020-12-10 | 2020-12-11 | 2020-12-12 | 2020-12-13 | 2020-12-14 | 2020-12-15 | 2020-12-16 | 2020-12-17 | 2020-12-18 | 2020-12-19 | 2020-12-20 | 2020-12-21 | 2020-12-22 | 2020-12-23 | 2020-12-24 | 2020-12-25 | 2020-12-26 | 2020-12-27 | 2020-12-28 | 2020-12-29 | 2020-12-30 | 2020-12-31 | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-08 | 2021-01-09 | 2021-01-10 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-14 | 2021-01-15 | 2021-01-16 | 2021-01-17 | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-01-21 | 2021-01-22 | 2021-01-23 | 2021-01-24 | 2021-01-25 | 2021-01-26 | 2021-01-27 | 2021-01-28 | 2021-01-29 | 2021-01-30 | 2021-01-31 | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06 | 2021-02-07 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-02-11 | 2021-02-12 | 2021-02-13 | 2021-02-14 | 2021-02-15 | 2021-02-16 | 2021-02-17 | 2021-02-18 | 2021-02-19 | 2021-02-20 | 2021-02-21 | 2021-02-22 | 2021-02-23 | 2021-02-24 | 2021-02-25 | 2021-02-26 | 2021-02-27 | 2021-02-28 | 2021-03-01 | 2021-03-02 | 2021-03-03 | 2021-03-04 | 2021-03-05 | 2021-03-06 | 2021-03-07 | 2021-03-08 | 2021-03-09 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-03-13 | 2021-03-14 | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-18 | 2021-03-19 | 2021-03-20 | 2021-03-21 | 2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-27 | 2021-03-28 | 2021-03-29 | 2021-03-30 | 2021-03-31 | 2021-04-01 | 2021-04-02 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-10 | 2021-04-11 | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-05-01 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-09 | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-21 | 2021-05-22 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 2021-05-27 | 2021-05-28 | 2021-05-29 | 2021-05-30 | 2021-05-31 | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-05 | 2021-06-06 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-19 | 2021-06-20 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 | 2021-07-02 | 2021-07-03 | 2021-07-04 | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 | 2021-07-16 | 2021-07-17 | 2021-07-18 | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-07 | 2021-08-08 | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-21 | 2021-08-22 | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-05 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-18 | 2021-09-19 | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25 | 2021-12-26 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | 2022-01-01 | 2022-01-02 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-08 | 2022-01-09 | 2022-01-10 | 2022-01-11 | 2022-01-12 | 2022-01-13 | 2022-01-14 | 2022-01-15 | 2022-01-16 | 2022-01-17 | 2022-01-18 | 2022-01-19 | 2022-01-20 | 2022-01-21 | 2022-01-22 | 2022-01-23 | 2022-01-24 | 2022-01-25 | 2022-01-26 | 2022-01-27 | 2022-01-28 | 2022-01-29 | 2022-01-30 | 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-14 | 2022-05-15 | 2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-21 | 2022-05-22 | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-28 | 2022-05-29 | 2022-05-30 | 2022-05-31 | 2022-06-01 | 2022-06-02 | 2022-06-03 | 2022-06-04 | 2022-06-05 | 2022-06-06 | 2022-06-07 | 2022-06-08 | 2022-06-09 | 2022-06-10 | 2022-06-11 | 2022-06-12 | 2022-06-13 | 2022-06-14 | 2022-06-15 | 2022-06-16 | 2022-06-17 | 2022-06-18 | 2022-06-19 | 2022-06-20 | 2022-06-21 | 2022-06-22 | 2022-06-23 | 2022-06-24 | 2022-06-25 | 2022-06-26 | 2022-06-27 | 2022-06-28 | 2022-06-29 | 2022-06-30 | 2022-07-01 | 2022-07-02 | 2022-07-03 | 2022-07-04 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-10 | 2022-07-11 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 | 2022-07-16 | 2022-07-17 | 2022-07-18 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-24 | 2022-07-25 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-07-31 | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 2022-08-14 | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-20 | 2022-08-21 | 2022-08-22 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-27 | 2022-08-28 | 2022-08-29 | 2022-08-30 | 2022-08-31 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-04 | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-11 | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18 | 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | 2022-10-02 | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-06 | 2022-10-07 | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-15 | 2022-10-16 | 2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-23 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-10-30 | 2022-10-31 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04 | 2022-11-05 | 2022-11-06 | 2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-13 | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 2022-11-20 | 2022-11-21 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-27 | 2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04 | 2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30 | 2022-12-31 | 2023-01-01 | 2023-01-02 | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-06 | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-21 | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-28 | 2023-01-29 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-18 | 2023-02-19 | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-04 | 2023-03-05 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-11 | 2023-03-12 | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-18 | 2023-03-19 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-01 | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-08 | 2023-04-09 | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-14 | 2023-04-15 | 2023-04-16 | 2023-04-17 | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-21 | 2023-04-22 | 2023-04-23 | 2023-04-24 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29 | 2023-04-30 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 | 2023-05-06 | 2023-05-07 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25 | 2023-05-26 | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-02 | 2023-06-03 | 2023-06-04 | 2023-06-05 | 2023-06-06 | 2023-06-07 | 2023-06-08 | 2023-06-09 | 2023-06-10 | 2023-06-11 | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-17 | 2023-06-18 | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-24 | 2023-06-25 | 2023-06-26 | 2023-06-27 | 2023-06-28 | 2023-06-29 | 2023-06-30 | 2023-07-01 | 2023-07-02 | 2023-07-03 | 2023-07-04 | 2023-07-05 | 2023-07-06 | 2023-07-07 | 2023-07-08 | 2023-07-09 | 2023-07-10 | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-14 | 2023-07-15 | 2023-07-16 | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 | 2023-07-21 | 2023-07-22 | 2023-07-23 | 2023-07-24 | 2023-07-25 | 2023-07-26 | 2023-07-27 | 2023-07-28 | 2023-07-29 | 2023-07-30 | 2023-07-31 | 2023-08-01 | 2023-08-02 | 2023-08-03 | 2023-08-04 | 2023-08-05 | 2023-08-06 | 2023-08-07 | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11 | 2023-08-12 | 2023-08-13 | 2023-08-14 | 2023-08-15 | 2023-08-16 | 2023-08-17 | 2023-08-18 | 2023-08-19 | 2023-08-20 | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | 2023-08-26 | 2023-08-27 | 2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-09-01 | 2023-09-02 | 2023-09-03 | 2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-09-07 | 2023-09-08 | 2023-09-09 | 2023-09-10 | 2023-09-11 | 2023-09-12 | 2023-09-13 | 2023-09-14 | 2023-09-15 | 2023-09-16 | 2023-09-17 | 2023-09-18 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-24 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 | 2023-11-12 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-25 | 2023-11-26 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08 | 2023-12-09 | 2023-12-10 | 2023-12-11 | 2023-12-12 | 2023-12-13 | 2023-12-14 | 2023-12-15 | 2023-12-16 | 2023-12-17 | 2023-12-18 | 2023-12-19 | 2023-12-20 | 2023-12-21 | 2023-12-22 | 2023-12-23 | 2023-12-24 | 2023-12-25 | 2023-12-26 | 2023-12-27 | 2023-12-28 | 2023-12-29 | 2023-12-30 | 2023-12-31 | 2024-01-01 | 2024-01-02 | 2024-01-03 | 2024-01-04 | 2024-01-05 | 2024-01-06 | 2024-01-07 | 2024-01-08 | 2024-01-09 | 2024-01-10 | 2024-01-11 | 2024-01-12 | 2024-01-13 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2024-01-20 | 2024-01-21 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-27 | 2024-01-28 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-03 | 2024-02-04 | 2024-02-05 | 2024-02-06 | 2024-02-07 | 2024-02-08 | 2024-02-09 | 2024-02-10 | 2024-02-11 | 2024-02-12 | 2024-02-13 | 2024-02-14 | 2024-02-15 | 2024-02-16 | 2024-02-17 | 2024-02-18 | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-24 | 2024-02-25 | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-02 | 2024-03-03 | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-27 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-04 | 2024-05-05 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-09 | 2024-05-10 | 2024-05-11 | 2024-05-12 | 2024-05-13 | 2024-05-14 | 2024-05-15 | 2024-05-16 | 2024-05-17 | 2024-05-18 | 2024-05-19 | 2024-05-20 | 2024-05-21 | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-25 | 2024-05-26 | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | 2024-05-31 | 2024-06-01 | 2024-06-02 | 2024-06-03 | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | 2024-06-08 | 2024-06-09 | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-06-15 | 2024-06-16 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-22 | 2024-06-23 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-06-27 | 2024-06-28 | 2024-06-29 | 2024-06-30 | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | 2024-07-06 | 2024-07-07 | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | 2024-07-13 | 2024-07-14 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-20 | 2024-07-21 | 2024-07-22 | 2024-07-23 | 2024-07-24 | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-07-28 | 2024-07-29 | 2024-07-30 | 2024-07-31 | 2024-08-01 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-05 | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-10 | 2024-08-11 | 2024-08-12 | 2024-08-13 | 2024-08-14 | 2024-08-15 | 2024-08-16 | 2024-08-17 | 2024-08-18 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-24 | 2024-08-25 | 2024-08-26 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-08-30 | 2024-08-31 | 2024-09-01 | 2024-09-02 | 2024-09-03 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-07 | 2024-09-08 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28 | 2024-09-29 | 2024-09-30 | 2024-10-01 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-05 | 2024-10-06 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-12 | 2024-10-13 | 2024-10-14 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-18 | 2024-10-19 | 2024-10-20 | 2024-10-21 | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-26 | 2024-10-27 | 2024-10-28 | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-16 | 2024-11-17 | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-22 | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2024-12-29 | 2024-12-30
1 | Red | 2007-06.2 - Phase 2 System Protection Coordination | PRC-001-1.1.(Ret), PER-006-1 (New), and revision to definitions of Operational Planning Analysis and Real-time Assessment. | 69 | Archive_Baseline
2 | Red | 2007-06.2 - Phase 2 System Protection Coordination | PRC-001-1.1.(Ret), PER-006-1 (New), and revision to definitions of Operational Planning Analysis and Real-time Assessment. | 69 | Archive_Current
3 | Red | 2009-02 - Real-time Reliability Monitoring and Analysis Capabilities | New IRO-018-1 and TOP-010-1 | -47 | Archive_Baseline
4 | Red | 2009-02 - Real-time Reliability Monitoring and Analysis Capabilities | New IRO-018-1 and TOP-010-1 | -47 | Archive_Current
5 | Red | 2010-14.2.1a - Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | BAL-005 | -4 | Archive_Baseline
6 | Red | 2010-14.2.1a - Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | BAL-005 | -4 | Archive_Current
7 | Red | 2010-14.2.1b - Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | FAC-001 | -4 | Archive_Baseline
8 | Red | 2010-14.2.1b - Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | FAC-001 | -4 | Archive_Current
9 | Red | 2010-14.2.1c - Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | BAL-006 | -4 | Archive_Baseline
10 | Red | 2010-14.2.1c - Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | BAL-006 | -4 | Archive_Current
11 | Red | 2010-14.2.2 - Phase 2 of Balancing Authority Reliability-based Controls - BAL-004-2 | BAL-004 | -7 | Archive_Baseline
12 | Red | 2010-14.2.2 - Phase 2 of Balancing Authority Reliability-based Controls - BAL-004-2 | BAL-004 | -7 | Archive_Current
13 | Red | 2013-03 - Geomagnetic Disturbance Mitigation | TPL-007-2 | 123 | Archive_Baseline
14 | Red | 2013-03 - Geomagnetic Disturbance Mitigation | TPL-007-2 | 123 | Archive_Current
15 | Red | 2015-04 - Alignment of Terms | Report on process (Phase II Improvement Report) | 0 | Archive_Baseline
16 | Red | 2015-04 - Alignment of Terms | Report on process (Phase II Improvement Report) | 0 | Archive_Current
17 | Red | 2015-07 - Internal Communications Capabilities | COM-001-3 | -74 | Archive_Baseline
18 | Red | 2015-07 - Internal Communications Capabilities | COM-001-3 | -74 | Archive_Current
19 | Red | 2015-08a - Emergency Operations | EOP-005, EOP-006, and EOP-008 | -205 | Archive_Baseline
20 | Red | 2015-08a - Emergency Operations | EOP-005, EOP-006, and EOP-008 | -205 | Archive_Current
21 | Red | 2015-08b - Emergency Operations | EOP-004 | -155 | Archive_Baseline
22 | Red | 2015-08b - Emergency Operations | EOP-004 | -155 | Archive_Current
23 | Red | 2015-09 - Establish and Communicate System Operating Limits | CIP-014-3, FAC-003-5, FAC-011-4, FAC-013-3, PRC-002-3, PRC-023-5, PRC-026 and the retirement of FAC-010 | -433 | Baseline
24 | Red | 2015-09 - Establish and Communicate System Operating Limits | CIP-014-3, FAC-003-5, FAC-011-4, FAC-013-3, PRC-002-3, PRC-023-5, PRC-026 and the retirement of FAC-010 | -433 | Archived
25 | Red | 2015-09b - Establish and Communicate System Operating Limits | IROL Stds. | 0 | Baseline
26 | Red | 2015-09b - Establish and Communicate System Operating Limits | IROL Stds. | 0 | Archived
27 | Red | 2015-10 - Single Points of Failure TPL-001 | TPL-001-5 | -276 | Archive_Baseline
28 | Red | 2015-10 - Single Points of Failure TPL-001 | TPL-001-5 | -276 | Archive_Current
29 | Red | 2015-INT-01 - Interpretation of CIP-002-5.1 for Energy Sector Security Consortium (EnergySec) | Interpretation CIP-002-5.1 | -9 | Archive_Baseline
30 | Red | 2015-INT-01 - Interpretation of CIP-002-5.1 for Energy Sector Security Consortium (EnergySec) | Interpretation CIP-002-5.1 | -9 | Archive_Current
31 | Red | 2015-INT-02 - Interpretation of CIP-007-5 for Foxguard Solutions | CIP-007-5 | 0 | Archive_Baseline
32 | Red | 2015-INT-02 - Interpretation of CIP-007-5 for Foxguard Solutions | CIP-007-5 | 0 | Archive_Current
33 | Red | 2015-INT-03 - Interpretation of TOP-002-2.1b for FMPP | TOP-002-2.1b | 0 | Archive_Baseline
34 | Red | 2015-INT-03 - Interpretation of TOP-002-2.1b for FMPP | TOP-002-2.1b | 0 | Archive_Current
35 | Red | 2016-01 - Modifications to TOP and IRO Standards | TOP/IRO Standards | 46 | Archive_Baseline
36 | Red | 2016-01 - Modifications to TOP and IRO Standards | TOP/IRO Standards | 46 | Archive_Current
37 | Red | 2016-02a - Modifications to CIP Standards | LERC Definition & CIP-003-7 | 27 | Archive_Baseline
38 | Red | 2016-02a - Modifications to CIP Standards | LERC Definition & CIP-003-7 | 27 | Archive_Current
39 | Red | 2016-02b - Modifications to CIP Standards | Directives, Control Center Comm Nets (CIP-012-1)/ Control Center definition | -289 | Archive_Baseline
40 | Red | 2016-02b - Modifications to CIP Standards | Directives, Control Center Comm Nets (CIP-012-1)/ Control Center definition | -289 | Archive_Current
41 | Red | 2016-02c - Modifications to CIP Standards | CIP-002-6 - Address TO Control Centers Performing Transmission Operator (TOP) Obligations. | -891 | Archive_Baseline
42 | Red | 2016-02c - Modifications to CIP Standards | CIP-002-6 - Address TO Control Centers Performing Transmission Operator (TOP) Obligations. | -891 | Archive_Current
43 | Green | 2016-02d - Modifications to CIP Standards | 0 | -1051 | Baseline
44 | Green | 2016-02d - Modifications to CIP Standards | 0 | -1051 | Posted
45 | Red | 2016-02e - Modifications to CIP Standards | CIP-003-8 (FERC Order No. 843 Malicious Code Example Directive) | -83 | Archive_Baseline
46 | Red | 2016-02e - Modifications to CIP Standards | CIP-003-8 (FERC Order No. 843 Malicious Code Example Directive) | -83 | Archive_Current
47 | Red | 2016-EPR-01 - Enhanced Periodic Review of Personnel Performance, Training, and Qualifications Standards | PER-003-1 and PER-004-2 | 0 | Archive_Baseline
48 | Red | 2016-EPR-01 - Enhanced Periodic Review of Personnel Performance, Training, and Qualifications Standards | PER-003-1 and PER-004-2 | 0 | Archive_Current
49 | Red | 2016-EPR-02 - Enhanced Periodic Review of Voltage and Reactive Standards | VAR-001-4.1 & VAR-002-4 | 0 | Archive_Baseline
50 | Red | 2016-EPR-02 - Enhanced Periodic Review of Voltage and Reactive Standards | VAR-001-4.1 & VAR-002-4 | 0 | Archive_Current
51 | Red | 2016-03 - Cyber Security Supply Chain Management | New and revised Standard(s) | -20 | Archive_Baseline
52 | Red | 2016-03 - Cyber Security Supply Chain Management | New and revised Standard(s) | -20 | Archive_Current
53 | Red | 2016-04 - Modifications to PRC-025-1 | PRC-025-2 | 0 | Archive_Baseline
54 | Red | 2016-04 - Modifications to PRC-025-1 | PRC-025-2 | 0 | Archive_Current
55 | Red | 2017-01 - Modifications to BAL-003-1.1 | BAL-003-2 | -177 | Archive_Baseline
56 | Red | 2017-01 - Modifications to BAL-003-1.1 | BAL-003-2 | -177 | Archive_Current
57 | Green | 2017-01b - Modifications to BAL-003-1.1 | BAL-003-3 |  | Baseline
58 | Green | 2017-01b - Modifications to BAL-003-1.1 | BAL-003-3 |  | On Hold
59 | Red | 2017-02 - Modifications to Personnel Performance, Training, and Qualifications Standards | PER-003-2, retire PER-004-2 | 24 | Archive_Baseline
60 | Red | 2017-02 - Modifications to Personnel Performance, Training, and Qualifications Standards | PER-003-2, retire PER-004-2 | 24 | Archive_Current
61 | Red | 2017-03 - Periodic Review of FAC-008-3 Standard | PR Recommendations | 0 | Archive_Baseline
62 | Red | 2017-03 - Periodic Review of FAC-008-3 Standard | PR Recommendations | 0 | Archive_Current
63 | Red | 2017-04 - Periodic Review of Interchange Scheduling and Coordination Standards | PR Recommendations | 0 | Archive_Baseline
64 | Red | 2017-04 - Periodic Review of Interchange Scheduling and Coordination Standards | PR Recommendations | 0 | Archive_Current
65 | Red | 2017-05 - Periodic Review NUC-001-3 | PR Recommendations | 0 | Archive_Baseline
66 | Red | 2017-05 - Periodic Review NUC-001-3 | PR Recommendations | 0 | Archive_Current
67 | Red | 2017-06 - Project 2017-06 Modifications to BAL-002-2 | BAL-002-3 | 0 | Archive_Baseline
68 | Red | 2017-06 - Project 2017-06 Modifications to BAL-002-2 | BAL-002-3 | 0 | Archive_Current
69 | Red | 2017-07 - Stds Alignment with Registration | FAC-002-3, IRO-010-3, MOD-031-3, MOD-033-2, NUC-001-4, PRC-006-4, and TOP-003-4 | -3 | Archive_Baseline
70 | Red | 2017-07 - Stds Alignment with Registration | FAC-002-3, IRO-010-3, MOD-031-3, MOD-033-2, NUC-001-4, PRC-006-4, and TOP-003-4 | -3 | Archive_Current
71 | Red | 2018-01 - Canadian-specific Revisions to TPL-007-2 | TPL-007-3 | 56 | Archive_Baseline
72 | Red | 2018-01 - Canadian-specific Revisions to TPL-007-2 | TPL-007-3 | 56 | Archive_Current
73 | Red | 2018-02 - Modifications to CIP-008 Cyber Security Incident Reporting | CIP-008-6 | -1 | Archive_Baseline
74 | Red | 2018-02 - Modifications to CIP-008 Cyber Security Incident Reporting | CIP-008-6 | -1 | Archive_Current
75 | Red | 2018-03 - Standards Efficiency Review Retirements (SER-Phase I) | Retirements Only | 91 | Archive_Baseline
76 | Red | 2018-03 - Standards Efficiency Review Retirements (SER-Phase I) | Retirements Only | 91 | Archived
77 | Red | 2018-03b - Standards Efficiency Review Retirements (SER-Phase Ib) | 0 | 0 | Archive_Baseline
78 | Red | 2018-03b - Standards Efficiency Review Retirements (SER-Phase Ib) | 0 | 0 | Archived
79 | Red | 2018-04 - Modifications to PRC-024-2 | PRC-024-3 | -51 | Archive_Baseline
80 | Red | 2018-04 - Modifications to PRC-024-2 | PRC-024-3 | -51 | Archive_Current
81 | Red | 2019-01 - Modifications to TPL-007-3 | TPL-007-4 | 100 | Complexity Factors
82 | Red | 2019-01 - Modifications to TPL-007-3 | TPL-007-4 | 100 | Archived
83 | Red | 2019-02 - BES Cyber System Information Access Management | CIP-004-7 and CIP-011-3 | -226 | Complexity Factors
84 | Red | 2019-02 - BES Cyber System Information Access Management | CIP-004-7 and CIP-011-3 | -226 | Archived
85 | Red | 2019-03 - Cyber Security Supply Chain Risks | CIP-005-6, CIP-010-3, and CIP-013-1 | 221 | Complexity Factors
86 | Red | 2019-03 - Cyber Security Supply Chain Risks | CIP-005-6, CIP-010-3, and CIP-013-1 | 221 | Archived
87 | Green | 2019-04 - Modifications to PRC-005-6 | PRC-005 | 844 | Complexity Factors
88 | Green | 2019-04 - Modifications to PRC-005-6 | PRC-005 | 844 | On Hold
89 | Red | 2019-05 - Modifications to PER-003 | PER-003 | -290 | Complexity Factors
90 | Red | 2019-05 - Modifications to PER-003 | PER-003 | -290 | Archived
91 | Red | 2019-06 - Cold Weather | EOP-011, IRO-010, TOP-003. | -21 | Complexity Factors
92 | Red | 2019-06 - Cold Weather | EOP-011, IRO-010, TOP-003. | -21 | Archived
93 | Red | 2020-01 - Modifications to MOD-032-1 | MOD-032-2 | 170 | Complexity Factors
94 | Red | 2020-01 - Modifications to MOD-032-1 | MOD-032-2 | 170 | Terminated
95 | Green | 2020-02 - Modifications to PRC-024 (Generator Ride-through) | PRC-024 | 95 | Complexity Factors
96 | Green | 2020-02 - Modifications to PRC-024 (Generator Ride-through) | PRC-024 | 95 | SDT Development
97 | Red | 2020-03 - Supply Chain Low Impact Revisions | CIP-003-8 | -111 | Complexity Factors
98 | Red | 2020-03 - Supply Chain Low Impact Revisions | CIP-003-8 | -111 | Archived
99 | Red | 2020-04 - Modifications to CIP-012-1 | CIP-012-2 | -447 | Complexity Factors
100 | Red | 2020-04 - Modifications to CIP-012-1 | CIP-012-2 | -447 | Approved
101 | Red | 2020-05 - Modifications to FAC-001-3 and FAC-002-2 | FAC-001-3, FAC-002-3 | 158 | Complexity Factors
102 | Red | 2020-05 - Modifications to FAC-001-3 and FAC-002-2 | FAC-001-3, FAC-002-3 | 158 | Archived
103 | Green | 2020-06 - Verifications of Models and Data for Generators | MOD-026, MOD-027 | -66 | Complexity Factors
104 | Green | 2020-06 - Verifications of Models and Data for Generators | MOD-026, MOD-027 | -66 | SDT Development
105 | Green | 2021-01 - Modifications to MOD-025 and PRC-019 | PRC-019, MOD-025 | 0 | Complexity Factors
106 | Green | 2021-01 - Modifications to MOD-025 and PRC-019 | PRC-019, MOD-025 | 0 | SDT Development
107 | Green | 2021-02 - Modifications to VAR-002-4.1 | VAR-002 | 4 | Complexity Factors
108 | Green | 2021-02 - Modifications to VAR-002-4.1 | VAR-002 | 4 | SDT Development
109 | Green | 2021-03 - CIP-002 Transmission Owner Control Centers (TOCC) | CIP-002 | 95 | Complexity Factors
110 | Green | 2021-03 - CIP-002 Transmission Owner Control Centers (TOCC) | CIP-002 | 95 | SDT Development
111 | Red | 2021-04 - Modifications to PRC-002-2 | PRC-002-4 | -60 | Complexity Factors
112 | Red | 2021-04 - Modifications to PRC-002-2 | PRC-002-4 | -60 | Filed
113 | Yellow | 2021-04b - Modifications to PRC-002-2 | PRC-002-5, PRC-028-1 | -483 | Complexity Factors
114 | Green | 2021-04b - Modifications to PRC-002-2 | PRC-002-5, PRC-028-1 | -483 | SDT Development
115 | Red | 2021-05 - Modifications to PRC-023-4 | PRC-023-6 | -114 | Complexity Factors
116 | Red | 2021-05 - Modifications to PRC-023-4 | PRC-023-6 | -114 | Filed
117 | Red | 2021-06 - Modifications to IRO-010 and TOP-003 | TBD | 27 | Complexity Factors
118 | Red | 2021-06 - Modifications to IRO-010 and TOP-003 | TBD | 27 | Archived
119 | Red | 2021-07 - Extreme Cold Weather Grid Operations, Preparedness, and Coordination | TBD | 208 | Complexity Factors
120 | Red | 2021-07 - Extreme Cold Weather Grid Operations, Preparedness, and Coordination | TBD | 208 | Filed
121 | Red | 2021-07b - Extreme Cold Weather Grid Operations, Preparedness, and Coordination | EOP-011, TOP-002 | 17 | Complexity Factors
122 | Red | 2021-07b - Extreme Cold Weather Grid Operations, Preparedness, and Coordination | EOP-011, TOP-002 | 17 | Filed
123 | Green | 2021-08 - Modifications to FAC-008-5 | FAC-008-6 | -305 | Complexity Factors
124 | Green | 2021-08 - Modifications to FAC-008-5 | FAC-008-6 | -305 | SDT Development
125 | Red | 2022-01 - Reporting ACE Definition and Associated Terms | ACE & IIM Definitions | -49 | Complexity Factors
126 | Red | 2022-01 - Reporting ACE Definition and Associated Terms | ACE & IIM Definitions | -49 | Pending Board Adoption
127 | Green | 2022-02 - Modifications to TPL-001-5.1 and MOD-032-1 | MOD-032, TPL-001 | -434 | Complexity Factors
128 | Green | 2022-02 - Modifications to TPL-001-5.1 and MOD-032-1 | MOD-032, TPL-001 | -434 | SDT Development
129 | Green | 2022-03 - Energy Assurance with Energy-Constrained Resources | TBD | -23 | Complexity Factors
130 | Green | 2022-03 - Energy Assurance with Energy-Constrained Resources | TBD | -23 | Responding to Comment
131 | Green | 2022-04 - EMT Models in NERC MOD, TPL, and FAC Standards | FAC-002, MOD-032, TPL-001 | 30 | Complexity Factors
132 | Green | 2022-04 - EMT Models in NERC MOD, TPL, and FAC Standards | FAC-002, MOD-032, TPL-001 | 30 | SDT Development
133 | Green | 2022-05 - Modifications to CIP-008 Reporting Threshold | CIP-008 | Need FB Date | Complexity Factors
134 | Green | 2022-05 - Modifications to CIP-008 Reporting Threshold | CIP-008 | Need FB Date | SDT Development
135 | Green | 2023-01 - EOP-004 IBR Event Reporting | EOP-004-5 |  | Complexity Factors
136 | Green | 2023-01 - EOP-004 IBR Event Reporting | EOP-004-5 | 165 | Responding to Comment
137 | Green | 2023-02 - Performance of IBRs Standard Authorization Request | PRC-004-7 |  | Complexity Factors
138 | Green | 2023-02 - Performance of IBRs Standard Authorization Request | PRC-004-7 | 120 | SDT Development
139 | Green | 2023-03 - Internal Network Security Monitoring (INSM) | CIP-005, CIP-010, CIP-013 |  | Complexity Factors
140 | Green | 2023-03 - Internal Network Security Monitoring (INSM) | CIP-005, CIP-010, CIP-013 | 0 | SDT Development
141 | Green | 2023-04 - Modifications to CIP-003 | CIP-003 |  | Complexity Factors
142 | Green | 2023-04 - Modifications to CIP-003 | CIP-003 | 7 | Responding to Comment
143 | Green | 2023-05 - Modifications to FAC-001 and FAC-002 | FAC-001, FAC-002 |  | Complexity Factors
144 | Green | 2023-05 - Modifications to FAC-001 and FAC-002 | FAC-001, FAC-002 | 90 | Nominations & SAR
145 | Green | 2023-06 - CIP-014 Risk Assessment Refinement | CIP-014-4 |  | Complexity Factors
146 | Green | 2023-06 - CIP-014 Risk Assessment Refinement | CIP-014-4 | 77 | Nominations & SAR
147 | Green | 2023-07 - Transmission System Planning Performance Requirements for Extreme Weather | TPL-001-6 |  | Complexity Factors
148 | Green | 2023-07 - Transmission System Planning Performance Requirements for Extreme Weather | TPL-001-6 | 269.6383 | Nominations & SAR
149 | Green | 2023-08 - Modifications of MOD-031 Demand and Energy Data | TBD |  | Complexity Factors
150 | Green | 2023-08 - Modifications of MOD-031 Demand and Energy Data | TBD | 0 | Nominations & SAR
Note on B4: Data Freshness Indicator: Green < 14 days since update Yellow >= 15 days since update Red > 30 days since update
Note on E4: Date driven off Final Ballot date.
Note on D79: NOTE: THIS PROJECT HAS A COMPRESSED TIME LINE.

## Summary
Project | PMOS Liaison | Project Name | Status | Comments | Deliverable | Deadline | Priority in RSDP, click to see applicable Footnote | P81 Req (2013) | Number of Directives | No. of Guidances (see Note 2) | Directionally consistent with IERP findings (See Note 5) | Developer | PMOS Liaison | Affected Standards | Last Updated
SUMMARY | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | HOME
2013-03 | Jennifer Sterling | Geomagnetic Disturbance Mitigation | Archived | FERC issued Order No. 830 on September 22, 2016 approving TPL-007-1 and directing modifications. The SDT will develop revised or new requirements to enhance the benchmark GMD event used in GMD assessments, require collection of GMD data, and establish deadlines for GMD Corrective Action Plans and mitigation measures. Revisions must be filed by May 29, 2018. The SAR was accepted by the Standards Committee on March 15, 2017. The standard was adopted by the NERC Board at their November 2017 meeting and filed on January 22, 2018. | TPL-007-2 | 2018-05-29 | Footnote 8, High | N/A | 4 | 13 | N/A | Scott Barfield | Jennifer Sterling | TPL-007-1 | 2018-01-29
2015-08a | Ken Goldsmith | Emergency Operations | Archived | Presented to BOT February 2017, preparing the filing. | EOP-005, EOP-006, and EOP-008 | N/A | Medium | N/A | 1 | 0 | N/A | Laura Anderson | Ken Goldsmith | EOP-005, EOP-006, and EOP-008 | 2017-03-06
2015-08b | Ken Goldsmith | Emergency Operations | Archived | Presented to BOT February 2017, preparing the filing. | EOP-004 | N/A | Medium | N/A | 1 | 0 | N/A | Laura Anderson | Ken Goldsmith | EOP-004 | 2017-03-06
2015-09 | Ken Lanehome | Establish and Communicate System Operating Limits | Archived | NERC Board adopted FAC-003-5, FAC-011-4, FAC‐014‐3, IRO‐008‐3, TOP‐001‐6, PRC-002-3, PRC-023-5, PRC-026 and the retirement of FAC-010 on May 13, 2021. NERC will file with FERC in late June. | CIP-014-3, FAC-003-5, FAC-011-4, FAC-013-3, PRC-002-3, PRC-023-5, PRC-026 and the retirement of FAC-010 | N/A | Footnote 11, Medium | N/A | 0 | 0 | N/A | Latrice Harkness | Ken Lanehome | CIP-014-3, FAC-003-5, FAC-011, FAC-013-3, PRC-002-3, PRC-023-5, PRC-026-1 and the retirement of FAC-010 | 2021-09-22
2015-09b | Ken Lanehome (primary), Rebecca Darrah (secondary) | Establish and Communicate System Operating Limits | Archived | This project will not re-open for phase 2. Therefore, this project is closed. | IROL Stds. | N/A | Footnote 11, Medium | N/A | 1 | 1 | N/A | Latrice Harkness | Ken Lanehome (primary), Rebecca Darrah (secondary) | N/A | 2021-07-23
2015-10 | Mark Pratt | Single Points of Failure TPL-001 | Archived | The standard was approved by industry with a 66.67% vote and adopted by the NERC Board of Trustees at its November 2018 meeting. The standard was filed with regulatory authorities on December 7, 2018. | TPL-001-5 | N/A | Footnote 8, High | N/A | 2 | 0 | N/A | Latrice Harkness | Mark Pratt | TPL-001-4 | 2019-01-23
2015-INT-01 | Brian Murphy and Andrew Gallo | Interpretation of CIP-002-5.1 for Energy Sector Security Consortium (EnergySec) | Archived-Not for Metrics | Interpretation passed. FERC Approved, RD docket. (Interpretation - not used for metrics analysis) | Interpretation CIP-002-5.1 | N/A | Low | N/A | 0 | 0 | N/A | Al McMeekin | Brian Murphy and Andrew Gallo | CIP-002-5.1 | 2017-02-09
2016-01 | Rod Kinard | Modifications to TOP and IRO Standards | Archived | Preparing for final ballot in Dec 2016. NOPR issued June 18, 2015 (under previous project 2014-03). Final Rule issued November 19, 2015 with three directives with an associated 18 month regulatory filing deadline. The SC authorized posting at the June 2016 SC meeting. Standards passed additional ballot ending October 17 2016 and will be posted for final ballot early December 2016. | TOP/IRO Standards | FERC deadline of July 27, 2017 | High | N/A | 0 | 0 | N/A | Mark Olson | Rod Kinard | TOP-001 and IRO-002 | 2016-12-13
2016-02a | Ken Lanehome and Ash Mayfield | Modifications to CIP Standards | Archived | Petition was filed on March 3, 2017 requesting approval. TD at Lows resulted in a balloted CIP-003-7(i), which was not captured in the dates. "(i)" was dropped in the BOT presentation and filing and the standard was filed as CIP-003-7 | LERC Definition & CIP-003-7 | Directive: March 31, 2017 (LERC only) (March 31 in SAR) | High | N/A | 1 | 0 | N/A | Al McMeekin | Ken Lanehome and Ash Mayfield | CIP-003-7 | 2017-04-11
2016-02b | Ken Lanehome, Ash Mayfield, and Kirk Rosener | Modifications to CIP Standards | Archived | CIP-012-1 was approved by industry and the NERC Board adopted the standard at its August 2018 meeting and filed with regulatory authorities on September 18, 2018. | Directives, Control Center Comm Nets (CIP-012-1)/ Control Center definition | N/A | Footnote 8, High | N/A | 2 | 0 | N/A | Jordan Mallory | Ken Lanehome, Ash Mayfield, and Kirk Rosener | CIP-012-1 | 2018-09-24
2016-02c | Ken Lanehome (primary), Kirk Rosener (secondary) and Ash Mayfield (tertiary) | Modifications to CIP Standards | Archived | The standard posted for final ballot passed with a 96.28 %. The NERC Board adopted the standard during its May 2020 Board meeting. | CIP-002-6 - Address TO Control Centers Performing Transmission Operator (TOP) Obligations. | N/A | Footnote 8, High | N/A | 0 | 0 | N/A | Jordan Mallory | Ken Lanehome (primary), Kirk Rosener (secondary) and Ash Mayfield (tertiary) | CIP-002-5.1, CIP-003-6, CIP-004-6, CIP-005-5, CIP-006-6, CIP-007-6, CIP-008-5, CIP-009-6, CIP-010-2, CIP-011-2, CIP-012-1 | 2020-06-22
2016-02d | Ruida Shu (primary), Kirk Rosener (secondary) | Modifications to CIP Standards | Posted | The draft version 5 of the project successfully completed its industry comment and ballot period on November 29, 2023, with the ballot passing. Final ballot from April 3 - 12. | 0 | N/A | Footnote 11, High | N/A | 1 | 0 | N/A | Alison Oswald | Ruida Shu (primary), Kirk Rosener (secondary) | CIP-004, CIP-005, CIP-006, CIP-007 and CIP-010 | 2024-04-10
2016-02e | Ken Lanehome, Ash Mayfield, and Kirk Rosener | Modifications to CIP Standards | Archived | CIP-003 passed Final Ballot on April 29 at 91.44%. The standard was adopted by the NERC Board of Trustees in May 2019 and was filed on May 21, 2019. | CIP-003-8 (FERC Order No. 843 Malicious Code Example Directive) | N/A | Footnote 8, High | N/A | 0 | 0 | N/A | Jordan Mallory | Ken Lanehome, Ash Mayfield, and Kirk Rosener | CIP-003-7 | 2019-06-26
2016-03 | Brenda Hampton | Cyber Security Supply Chain Management | Archived | The petition was filed on September 26, 2017. | New and revised Standard(s) | 2017-09-27 | Footnote 8, High | N/A | 1 | 0 | N/A | Mark Olson | Brenda Hampton | CIP-005-6, CIP-010-3, and CIP-013-1 | 2017-10-03
2016-04 | Charles Yeung | Modifications to PRC-025-1 | Archived | Providing the SC an update on a non-substantive correction (Vlowside to Vhighside) to the Guidelines and Technical Basis before filing. | New and revised Standard(s) | N/A | Footnote 9, Medium | N/A | 0 | 0 | Yes | Scott Barfield-McGinnis | Charles Yeung | PRC-025-1 | 2018-03-14
2016-EPR-01 | Mike Brytowski | Enhanced Periodic Review of Personnel Performance, Training, and Qualifications Standards | Archived | The team will be requesting the Standards Committee at the June 14, 2017 meeting to accept a SAR to revise a Standard and to activate Project 2017-02. | PER-003-1 and PER-004-2 | N/A | Medium | N/A | N/A | N/A | N/A | Darrel Richardson | Mike Brytowski | 0 | 2017-06-14
2016-EPR-02 | Amy Casuscelli | Enhanced Periodic Review of Voltage and Reactive Standards | Archived | The periodic review team (PRT) responded to industry comments that affirm the PRT's recommendations. The PRT maintained its initial recommendation that the standards are sufficient to protect reliablity and although some things could be cleaned up, the recommendation is to not open the standards for revisions (i.e., yellow rating). The PRT will present their recommendations for acceptance to the Standards Committee on June 14, 2017 and to re-affirm the two VAR standards. | VAR-001-4.1 & VAR-002-4 | N/A | Medium | N/A | N/A | N/A | N/A | Scott Barfield-McGinnis | Amy Casuscelli | 0 | 2017-06-14
2017-01 | Amy Casuscelli & Linda Lynch | Modifications to BAL-003-1.1 | Archived | The standard passed at 100%. The project documents went to the Board in November 2019 and was filed on December 19, 2019. | BAL-003-2 | N/A | Footnote 8, Medium | N/A | 0 | 0 | N/A | Laura Anderson | Amy Casuscelli & Linda Lynch | BAL-003-1.1 | 2020-02-14
2017-01b | Pamela Hunter (Primary), Charles Yeung (Backup) | Modifications to BAL-003-1.1 | On Hold | The project is currently on hold. | BAL-003-3 | N/A | Footnote 11, Medium | N/A | 0 | 0 | N/A | Darrel Richardson | Pamela Hunter (Primary), Charles Yeung (Backup) | BAL-003-2 | 2024-04-10
2017-02 | Mike Brytowski | Modifications to Personnel Performance, Training, and Qualifications Standards | Archived | NERC filed a petition for approval of PER-003 on July 23, 2018. Project archived by PMOS on Spetmber 13, 2018. | PER-003-2, retire PER-004-2 | N/A | Footnote 8, Medium | N/A | 0 | 0 | N/A | Darrel Richardson | Mike Brytowski | PER-003-1 & PER-004-2 | 2018-09-13
2017-03 | Mark Pratt | Periodic Review of FAC-008-3 Standard | Archived | The periodic review team recommendation was to reaffirm with an action to revise, but at a later time. The Standards Efficiency Review Project 2018-03 partially revised the standard, therefore, this project is being archived. | PR Recommendations | N/A | Footnote 9, Low (was Medium previously) | N/A | 0 | 0 | N/A | Jordan Mallory | Mark Pratt | FAC-008-3 | 2019-12-18
2017-04 | Charles Yeung | Periodic Review of Interchange Scheduling and Coordination Standards | Archived | The periodic review team recommendation was to reaffirm with an action to revise, but at a later time. The Standards Efficiency Review Project 2018-03 partially revised the standard, therefore, this project is being archived. | PR Recommendations | N/A | Footnote 9, Low (was Medium previously) | N/A | 0 | 0 | N/A | Laura Anderson | Charles Yeung | INT-004, INT-006, INT-009, and INT-010 | 2019-12-18
2017-05 | Amy Casuscelli and Colby Bellville | Periodic Review NUC-001-3 | Archived | The NUC periodic review is being closed because the Project 2017-07 Standards Alignment with Registration is presented to the BOT in February 2020. The 2017-07 SDT is proposing another version of the NUC standards, so there’s no need for this periodic review to move forward. | PR Recommendations | N/A | Footnote 9, Low (was Medium previously) | N/A | 0 | 0 | N/A | Jordan Mallory | Amy Casuscelli and Colby Bellville | NUC-001-3 | 2019-12-18
2017-06 | Ken Lanehome | Project 2017-06 Modifications to BAL-002-2 | Archived | NERC filed a petition for approval on August 17, 2018. The project was archived by the PMOS on September 13, 2018. | BAL-002-3 | N/A | Footnote 8, Medium | N/A | 0 | 0 | N/A | Darrel Richardson | Ken Lanehome | BAL-002-2 | 2018-09-13
2017-07 | Mike Brytowski | Stds Alignment with Registration | Pending Regulatory Filing | Project 2017-07 Standards Alignment with Registration posted final ballot January 14-23. The BOT adoption at the February 2020 meeting. | FAC-002-3, IRO-010-3, MOD-031-3, MOD-033-2, NUC-001-4, PRC-006-4, and TOP-003-4 | 0 | Footnote 9, Low | N/A | 0 | 0 | N/A | Laura Anderson | Mike Brytowski | Standards with PSE, IA, or LSE (FAC-002, INT-004, IRO-010, MOD-031, MOD-032, NUC-001, and TOP-003) | 2020-03-18
2017-08 | 0 | Open - Available | Void | 0 | CIP-014-4 | 0 | 0 | 0 | 0 | 0 | 0 | Mat Bunch | 0 | 0 | 2017-07-17
2018-01 | Charles Yeung | Canadian-specific Revisions to TPL-007-2 | Archived | The standard passed on initial ballot at 100% and was adopted by the NERC Board last November. The standard has been filed with Canadian authorties and an informational filing with FERC. | TPL-007-3 | N/A | Footnote 10, Medium | N/A | 0 | 0 | N/A | Mat Bunch | Charles Yeung | TPL-007-2 | 2019-03-07
2018-02 | Colby Bellville & Amy Casuscelli | Modifications to CIP-008 Cyber Security Incident Reporting | Archived | The standard has been filed with regulatory authorities. | CIP-008-6 | 2019-04-01 | Footnote 10, High | N/A | 1 | 0 | N/A | Alison Oswald | Colby Bellville & Amy Casuscelli | CIP-008-5 | 2019-03-07
2018-03 | Mark Pratt (primary), Michael Brytowski (secondary) | Standards Efficiency Review Retirements (SER-Phase I) | Archived | The Project 2018-03 standard drafting team has been recalled to reconsider retirement of Requirements R7 and R8 of FAC-008-3 per the FERC Order issued on September 17, 2020. | Retirements Only | 0 | N/A | N/A | 0 | 0 | N/A | Laura Anderson | Mark Pratt (primary), Michael Brytowski (secondary) | FAC-008-3 | 2021-01-27
2018-03b | Mark Pratt (primary), Michael Brytowski (secondary) | Standards Efficiency Review Retirements (SER-Phase Ib) | Archived | Initial 45-day posting with 10-day ballot period was posted November 30, 2020, and the ballot passed with over 95% approval. The next steps are as follows: SDT will review comments received during the recent posting period, and post for a 10-day final ballot, target is January 19, 2021, and send it to the NERC BOT for approval in February 4, 2021. | 0 | 0 | 0 | Test P81 | 1 | 0 | Test IERP | Laura Anderson | Mark Pratt (primary), Michael Brytowski (secondary) | Enter number of Affected Standards in column B and the Standard here (e.g. TOP-001-4). This value is 2 of 2 items that calculate the project baseline. | 2021-05-03
2018-04 | Linda Lynch | Modifications to PRC-024-2 | Pending Regulatory Filing | The standards passed industry balloting at 82.47%. The standard was approved by the Board in February. | PRC-024-3 | N/A | N/A | N/A | 0 | 0 | N/A | Latrice Harkness & Alison Oswald | Linda Lynch | PRC-024-2 | 2020-03-18
2019-01 | Michael Brytowski | Modifications to TPL-007-3 | Archived | The TPL-007-4 – Transmission System Planned Performance for Geomagnetic Disturbance Events passed final ballot at 78.95%. Project 2019-01 was approved by the Board in February. | TPL-007-4 | 2020-06-30 | 0 | N/A | 1 | 0 | N/A | Alison Oswald | Michael Brytowski | TPL-007-3 | 2020-03-18
2019-02 | Kirk Rosener (primary), Colby Bellville (secondary) | BES Cyber System Information Access Management | Archived | This project is pending FERC approval. | CIP-004-7 and CIP-011-3 | N/A | Footnote 11, Medium | N/A | 0 | 0 | N/A | Jordan Mallory | Kirk Rosener (primary), Colby Bellville (secondary) | CIP-004 and CIP-0011 | 2021-10-13
2019-03 | Masuncha Bussey (primary), Kirk Rosener (secondary) and Linda Lynch (tertiary) | Cyber Security Supply Chain Risks | Archived | The project passed final ballot on October 16, 2020 and was approved by the NERC board during the November 2020 meeting. | CIP-005-6, CIP-010-3, and CIP-013-1 | 2020-12-25 | 0 | N/A | 1 | 0 | N/A | Alison Oswald/Jordan Mallory | Masuncha Bussey (primary), Kirk Rosener (secondary) and Linda Lynch (tertiary) | CIP-005-6, CIP-010-3, and CIP-013-1 | 2021-01-08
2019-04 | Joseph Gatten (primary), Sarah Habriga (backup) | Modifications to PRC-005-6 | On Hold | This project is on posting hold until after July 2024. The DT will continue to conduct DT meetings, but at a slower pace. We are now in the process of scheduling an in-person meeting with the entire SDT, and anticipating that it’ll be during the month of May in Raleigh, NC. | PRC-005 | 0 | Footnote 11, Low | N/A | 0 | 0 | N/A | Elsa Prince | Joseph Gatten (primary), Sarah Habriga (backup) | PRC-005-6 | 2024-04-10
2019-05 | Colby Bellville (primary), Charles Yeung (secondary) | Modifications to PER-003 | Archived | At the July 21, 2021 SC meeting the PER-003 SAR was rejected. The SAR submitters will be notified and the project will be disbanded until the PCGC finishes their task force work to look into the CEHs. | PER-003 | 0 | 0 | N/A | 0 | 0 | N/A | Alison Oswald | Colby Bellville (primary), Charles Yeung (secondary) | PER-003 | 2021-10-18
2019-06 | Quinn Morrison (primary), Mike Brytowski (secondary) | Cold Weather | Archived | The SDT made a few non-substantive changes and posted for final ballot on May 18, 2021. This project is completed and has been filed with FERC. | EOP-011, IRO-010, TOP-003. | 0 | Footnote 11, High | N/A | 0 | 0 | N/A | Jordan Mallory | Quinn Morrison (primary), Mike Brytowski (secondary) | EOP-011, IRO-010, TOP-003. | 2021-08-05
2020-01 | Linda Lynch (primary), Quinn Morrison (secondary) | Modifications to MOD-032-1 | Terminated | UPDATE: Project 2020-01 Modifications to MOD-032 was rejected by the SC in December 2020 and the team is disbanded.The SAR drafting team members divided up into several sub-groups and developed a list of ‘Major Themes’. Formal meetings were held on August 17th and September 8th to update the SAR. Posting date to be determined. The SAR team will be asking the SC for guidance on the procedure for closing out the SAR and moving it to the SDT status. | MOD-032-2 | 0 | 0 | N/A | 0 | 0 | N/A | Chris Larson | Linda Lynch (primary), Quinn Morrison (secondary) | MOD-032-1 | 2021-01-08
2020-02 | Pamela Hunter (Primary), Anthony Westenkirchner (Backup), Darrel Grumman (Backup) | Modifications to PRC-024 (Generator Ride-through) | SDT Development | Details on Draft: New standard PRC-029 to address IBRs. Will be focused on IBR performance and performance measurement. Still working on the initial draft and assuring performance is measured against actual performance data and not based on unit capabilities or equipment/controller settings. SDT is focused on addressing IBR voltage ride-through for legacy/new IBR equipment. Anticipate Posting: Initial Draft of modified PRC-024 and new PRC-029 to proceed to the Standards Committee in March; requesting approval to post for 25-day formal comment period and ballot in late March. Other: Identified as part of 2024 directives from Order 901. Final draft required by FERC to be approved by Nov 4, 2024. | PRC-024 | 0 | Footnote 11, High | N/A | 0 | 0 | N/A | Jamie Calderon | Pamela Hunter (Primary), Anthony Westenkirchner (Backup), Darrel Grumman (Backup) | PRC-024 | 2024-04-10
2020-03 | Kirk Rosener (primary), Ken Lanehome (secondary) | Supply Chain Low Impact Revisions | Archived | Final ballot occurred 10/26 – 11/04. The NERC board adopted the standard during the November 16th board meeting. | CIP-003-8 | 0 | Footnote 11, High | N/A | 0 | 0 | N/A | Alison Oswald | Kirk Rosener (primary), Ken Lanehome (secondary) | CIP-003-8 | 2023-01-05
2020-04 | Sarah Habriga (primary), Jennifer Richardson (secondary) | Modifications to CIP-012-1 | Approved | The final ballot closed on December 8th, 2023. The ballot passed with 88.36% approval on the Standard and 90.19% on the Implementation Plan. Next step would be presenting to BOT for adoption on December 12, 2023. Then file with FERC. | CIP-012-2 | 0 | Footnote 11, High | N/A | 1 | 0 | N/A | Ben Wu | Sarah Habriga (primary), Jennifer Richardson (secondary) | CIP-012 | 2023-12-18
2020-05 | Anthony Westenkirchner (primary), Cristhian Godoy (secondary) | Modifications to FAC-001-3 and FAC-002-2 | Archived | The project passed final ballot with an 85.63% approval on April 22, 2022. NERC BOT adopted the Standards on May 12, 2022. | FAC-001-3, FAC-002-3 | 0 | Footnote 11, Medium | N/A | 0 | 0 | N/A | Alison Oswald | Anthony Westenkirchner (primary), Cristhian Godoy (secondary) | FAC-001-2 and FAC-002-2. | 2022-06-06
2020-06 | Sarah Habriga (primary), Ellese Murphy (secondary) | Verifications of Models and Data for Generators | SDT Development | Additional Ballot 1 for IBR Glossary Terms ended on 04/08. IBR definition passed (67%), and IBR Unit definition did not pass (61%). NERC and DT will determine next steps and DT will review industry comments. This project is classified as medium except for the IBR definitions, which are high priority. | MOD-026, MOD-027 | 0 | Footnote 11, High | 0 | 0 | 0 | N/A | Chris Larson | Sarah Habriga (primary), Ellese Murphy (secondary) | MOD-026-1 and MOD-027-1 | 2024-04-10
2021-01 | Kirk Rosener (primary), Ruida Shu (backup) | Modifications to MOD-025 and PRC-019 | SDT Development | DT is conducting outreach for PRC-019, meeting with DT leadership & NERC Standards Developer once monthly PRC-019 requirement language has a dependency on the proposed IBR definitions, which will have an additional ballot ending April 8 (Project 2020-06). MOD-025 sub-team has a new draft ready for Informal Comment. DT must assess the impact of FERC Order No. 901 and associated NERC Work Plan. | PRC-019, MOD-025 | 0 | 0 | N/A | 0 | 0 | N/A | Chris Larson | Kirk Rosener (primary), Ruida Shu (backup) | MOD-025, PRC-019 | 2024-04-15
2021-02 | Joseph Gatten (Primary), Anthony Westenkirchner (Backup) | Modifications to VAR-002-4.1 | SDT Development | This project is on posting hold until after July 2024. The DT will continue to conduct DT meetings, but at a slower pace. An April 12, 2024 DT meeting is scheduled. | VAR-002 | 0 | 0 | N/A | 0 | 0 | N/A | Laura Anderson | Joseph Gatten (Primary), Anthony Westenkirchner (Backup) | VAR-002-4.1 | 2024-04-11
2021-03 | Ellese Murphy (Primary), Darrel Grumman (Backup) | CIP-002 Transmission Owner Control Centers (TOCC) | SDT Development | Details on Draft: Current/Anticipate Posting: A 45 Day Formal Comment period and additional ballot scheduled for April 2 – May 17, 2024. Webinar scheduled for April 26. Other: This project is assigned 5 SARS and is currently focusing on the TOCC SAR. | CIP-002 | 0 | Footnote 11, High | N/A | 0 | 0 | N/A | Dominique Love | Ellese Murphy (Primary), Darrel Grumman (Backup) | CIP-002 | 2024-04-04
2021-04 | Michael Brytowski (Primary), Charles Yeung (Backup) | Modifications to PRC-002-2 | Filed | Phase one was completed by the SDT. It got approved by the BOT on February 16, 2023. The petition will be sent to FERC for approval on March 10, 2023. | PRC-002-4 | 2022-12-31 | 0 | N/A | 0 | 0 | N/A | Ben Wu | Michael Brytowski (Primary), Charles Yeung (Backup) | PRC-002-2 | 2023-03-28
2021-04b | Michael Brytowski (Primary), Charles Yeung (Backup) | Modifications to PRC-002-2 | SDT Development | This is a high priority project. The SDT met in person at Georgia Power in Atlanta on February 21 and 22, 2024 to finalize the documents (Standard and associated Implementation Plan, as well as the Technical Rationale document). The final draft were sent out for quality review on March 1, 2024. The SDT will meet on March 11, 2024 to review comments received from the Quality Review Team. The second posting is scheduled to start on March 18, 2024 with 25 day posting. | PRC-002-5, PRC-028-1 | 2024-11-04 | Footnote 11, High | N/A | 0 | 0 | N/A | Ben Wu | Michael Brytowski (Primary), Charles Yeung (Backup) | PRC-002-2; PRC-028-1 | 2024-04-11
2021-05 | Anthony Westenkirchner (primary), Claudine Fritz (secondary) | Modifications to PRC-023-4 | Filed | The proposed Standard passed final ballot and approved by the Board of Trustees on February 16, 2023. The petition was sent to FERC for adoption. | PRC-023-6 | 0 | 0 | N/A | 0 | N/A | 0 | Ben Wu | Anthony Westenkirchner (primary), Claudine Fritz (secondary) | PRC-023-4 | 2023-04-13
2021-06 | Michael Brytowski (Primary), Charles Yeung (Backup) | Modifications to IRO-010 and TOP-003 | Archived | IRO-010-5 passed final ballot on 7/21 with 76% & TOP-003-6 passed with 75%. The NERC BOT at their 8/17 meeting is set to adopt the standards and move forward to FERC. | TBD | 0 | 0 | 0 | 0 | 0 | 0 | Josh Blume | Michael Brytowski (Primary), Charles Yeung (Backup) | IRO-010; TOP-003 | 2023-09-07
2021-07 | Michael Brytowski (Primary), Kirk Rosener (Backup) | Extreme Cold Weather Grid Operations, Preparedness, and Coordination | Filed | Phase 1 of the project passed final ballot 9/23 – 9/30. The standard we adopted during the October 26th board meeting. The team has started phase 2 drafting work. An Initial ballot for phase 2 is expected in January/February of 2023. | TBD | 2022-11-01 | 0 | N/A | 1 | 0 | N/A | Alison Oswald | Michael Brytowski (Primary), Kirk Rosener (Backup) | EOP-011-3, EOP-012-1 | 2024-03-12
2021-07b | Michael Brytowski (Primary), Kirk Rosener (Backup) | Extreme Cold Weather Grid Operations, Preparedness, and Coordination | Filed | DT working to address industry comments around “good utility practice” and the staggered implementation of CAPs in R8. Current/Anticipate Posting: Additional comment and ballot in Jan 2024 with Final Ballot in Feb 2024. Note that the ballot and formal commenting period are anticipated to be reduced/condensed to a 10-20 day timeframe. Other: FERC order deadline of February 16, 2024. | EOP-011, TOP-002 | 2023-11-01 | Footnote 11, High | N/A | 1 | 0 | N/A | Alison Oswald | Michael Brytowski (Primary), Kirk Rosener (Backup) | EOP-011, TOP-002 | 2024-03-12
2021-08 | Sarah Habriga (primary), Jennifer Richardson (secondary) | Modifications to FAC-008-5 | SDT Development | The final draft of the documents were approved for initial posting at the SC's August meeting (August 23, 2023). The initial posting started on September 5, 2023 and closed on October 19, 2023. The SDT will meet in person on November 6 & 7, 2023 to review the results and comments received from the industry. The second posting will probably take place in January, 2024. | FAC-008-6 | 2023-08-31 | 0 | N/A | 0 | N/A | N/A | Al McMeekin | Sarah Habriga (primary), Jennifer Richardson (secondary) | FAC-008-5 | 2024-04-11
2022-01 | Claudine Fritz (Primary), Ruida Shu (Backup) | Reporting ACE Definition and Associated Terms | Pending Board Adoption | Although this project is now lower priority, the preparation of responses to the comments received in the last balloting has been completed by the team. Team was expecting final balloting in December and going to the BOT in February but has not been posted yet. (the project status spreadsheet dates need updating for planned final ballot) | ACE & IIM Definitions | 2023-08-09 | 0 | N/A | 0 | N/A | N/A | Josh Blume | Claudine Fritz (Primary), Ruida Shu (Backup) | Enter number of Affected Standards in column B and the Standard here (e.g. TOP-001-4). This value is 2 of 2 items that calculate the project baseline. | 2023-12-22
2022-02 | Ellese Murphy (Primary), Terri Pyle (Backup) | Modifications to TPL-001-5.1 and MOD-032-1 | SDT Development | The SDT had a meeting on February 12, 2024. The team finished responding to all of the comments received from the second posting. They also reviewed the Standard (MOD-032) and associated Implementation Plan, as well as the Technical Rationale document. This project will not be posted until July, 2024. The SDT has another meeting scheduled for February 26, 2024. The team is working on the outreach to collect feedback before next posting. | MOD-032, TPL-001 | 2025-12-31 | 0 | N/A | 0 | N/A | N/A | Ben Wu | Ellese Murphy (Primary), Terri Pyle (Backup) | TPL-001-5.1; MOD-032-1 | 2024-04-11
2022-03 | Joe Gatten (primary), Terri Pyle (backup) | Energy Assurance with Energy-Constrained Resources | Responding to Comment | Details on Draft: BAL-007-1 standard is a new standard that is based on the Operations and Operations planning horizon SAR. It looks to address energy reliability assessments for both seasonal and near-term time horizons. Current/Anticipate Posting: BAL-007 Draft #1 concluded initial b on March 11, 2024. Consideration of Comment in progress. | TBD | 2023-12-31 | Footnote 11, High | N/A | 0 | N/A | N/A | Jordan Mallory; Dominique Love | Joe Gatten (primary), Terri Pyle (backup) | Enter number of Affected Standards in column B and the Standard here (e.g. TOP-001-4). This value is 2 of 2 items that calculate the project baseline. | 2024-04-04
2022-04 | Claudine Fritz (Primary), Charles Yeung (Backup) | EMT Models in NERC MOD, TPL, and FAC Standards | SDT Development | Although this is a low priority project at this point, the team is continuing to meet about every two weeks. As the team is looking at revising several standards, the DT is focusing on drafting revisions to FAC-002. Once complete, an informal comment period may be pursued. A new developer as been assigned to the project, Jessica Harris. | FAC-002, MOD-032, TPL-001 | 2023-12-31 | 0 | N/A | 0 | N/A | N/A | Jessica Harris | Claudine Fritz (Primary), Charles Yeung (Backup) | FAC-002, MOD-032, TPL-001 | 2024-04-04
2022-05 | Ellese Murphy (Primary), Ruida Shu (backup) | Modifications to CIP-008 Reporting Threshold | SDT Development | The team is beginning to work through revisions to CIP-008 and associated glossary terms. They are taking a big picture view of the issues. The DT plans to conduct a webinar for outreach in May 2024. No formal posting will occur until Q3 2024 or later due to this being a low priority project. | CIP-008 | 2025-04-15 15:19 | 0 | N/A | 0 | N/A | N/A | Alison Oswald | Ellese Murphy (Primary), Ruida Shu (backup) | CIP-008 | 2024-04-11
2023-01 | Ruida Shu (Primary), Terri Pyle (Backup), | EOP-004 IBR Event Reporting | Responding to Comment | Details on Draft: Added/revising IBR event reporting threshold. Current/Anticipated Posting: Informal comment period ended on 03/27. DT will review industry comments and schedule a meeting to discuss in late April or early May. | EOP-004-5 | 0 | 0 | N/A | 0 | N/A | N/A | Chris Larson | Ruida Shu (Primary), Terri Pyle (Backup), | EOP-004 | 2024-04-10
2023-02 | Claudine Fritz (Primary), Terri Pyle (Backup) | Performance of IBRs Standard Authorization Request | SDT Development | Details on Draft: The team discussed and drafted language around Requirement R4 and R5. Requirement R4 pertains to the analysis section of the standard, the team discussed timeframes and which functional entities are applicable to the requirement. Requirement R5 deals with the mitigation aspect of the standard in relation to the Generator Owner (GO). The previous discussion focused on Corrective Action Plans (CAPs) and how this would be applied to a GO with numerous IBR facilities with the same or similar equipment. The team ended drafting with Requirement R6 corresponding to the correct functional entities to communicate the CAP to and the time period this will be occurring. Current/Anticipate Posting: Anticipated Initial ballot and comment the week of March 25th. This will be a shortened 25 day formal comment and ballot period per the wavier approved on December 13, 2023. Other: Identified as part of 2024 directives from Order 901. Final draft required by FERC to be approved by Nov 4, 2024. | PRC-004-7 | 2025-04-15 15:19 | Footnote 11, High | N/A | 1 | N/A | N/A | Josh Blume | Claudine Fritz (Primary), Terri Pyle (Backup) | PRC-004-6 | 2024-04-11
2023-03 | Ruida Shu (Primary), Ron Sporseen (Backup) | Internal Network Security Monitoring (INSM) | SDT Development | Project 2023-03 INSM is currently in Additional Comment period and ballot period is scheduled April 12 through April 17, 2024. The DT unanimously determined to proceed with Project 2023-03 without including EACMS and PACS outside the ESP. A new standard, CIP-015-1, has been created for Internal Network Security Monitoring, rather than modifying CIP-007. The DT incorporated CIP Exceptional Circumstances into proposed Reliability Standard CIP-015-1. Should the current additional comment period with ballot pass, the DT will post the project for final ballot April 24-30, 2024 and present the project to the Board of Trustees at its May 2024 meeting. This project has a regulatory deadline of July 9, 2024. | CIP-005, CIP-010, CIP-013 | 2025-04-15 15:19 | Footnote 11, High | N/A | 0 | N/A | N/A | Laura Anderson | Ruida Shu (Primary), Ron Sporseen (Backup) | CIP-005-7, CIP-010-4, CIP-013-2 | 2024-04-11
2023-04 | Kirk Rosener (primary), Ron Sporseen (Backup) | Modifications to CIP-003 | Responding to Comment | Details on Draft: Team merged CIP-003, Attachment 1, Sections 3 and 6; added three controls for Low Impact Criteria. Updates made to Section 3.1. Configuration diagrams added to Technical Rationale. Current/Anticipated Posting: Formal comment ended on March 14. Other: DT team is revising CIP-003 and planning on additional ballot in May. | CIP-003 | 2023-10-31 | Footnote 11, High | N/A | 0 | N/A | N/A | Chris Larson | Kirk Rosener (primary), Ron Sporseen (Backup) | CIP-003-9 | 2024-04-15
2023-05 | Donovan Crane (Primary), Jason Chandler (Backup) | Modifications to FAC-001 and FAC-002 | Nominations & SAR | Project is on hold and ready to start. | FAC-001, FAC-002 | 2025-04-15 15:19 | Low | N/A | 0 | N/A | N/A | Josh Blume | Donovan Crane (Primary), Jason Chandler (Backup) | FAC-001-4; FAC-002-4 | 2024-04-11
2023-06 | Claudine Fritz (Primary), Ellese Murphy (Backup) | CIP-014 Risk Assessment Refinement | Nominations & SAR | This high priority project has the drafting team meeting twice per week. Details on Draft: Currently working initial draft requirements for establishing an annual applicability review for determination of newly applicable stations for a risk assessment. Current/Anticipate Posting: Anticipated initial comment and ballot in April/May 2024. Other: Identified as part of NERC Corporate Goals and anticipate submitting to board by end of 2024. | CIP-014-4 | 2025-04-15 15:19 | Footnote 11, High | N/A | 0 | N/A | N/A | Ben Wu | Claudine Fritz (Primary), Ellese Murphy (Backup) | CIP-014-3 | 2024-04-11
2023-07 | Jason Chandler (Primary), Donovan Crane (Backup) | Transmission System Planning Performance Requirements for Extreme Weather | Nominations & SAR | Seeking authorization to post from the SC at its March 20 meeting. If authorized to post, will post same day (March 20) for an initial 45-day comment and ballot period. An anticipated industry webinar to be completed the week of April 8th. | TPL-001-6 | 2024-12-15 | Footnote 11, High | N/A | 23 | N/A | N/A | Jordan Mallory | Jason Chandler (Primary), Donovan Crane (Backup) | TPL-001-5.1 | 2024-04-11
2023-08 | Darrel Grumman (Primary); Pamela Hunter (Backup) | Modifications of MOD-031 Demand and Energy Data | Nominations & SAR | SAR accepted by the SC on July 19, 2023. Working to determine a posting date for a 30-day SAR comment period and solicitation for nominations. | TBD | 2025-04-15 15:19 | Low | N/A | 0 | N/A | N/A | Jessica Harris | Darrel Grumman (Primary); Pamela Hunter (Backup) | MOD-031 | 2024-04-11
Note on P1: Data Freshness Indicator: Green < 14 days since update Yellow >= 15 days since update Red > 30 days since update

## Archive_Summary (hidden)
ARCHIVE SUMMARY |  | (Sorting okay) | [9 empty] | HOME
Project | Project Name | Status | Comments | Deliverable | Deadline | Priority in RSDP, click to see applicable Footnote | P81 Req (2013) | Number of Directives | No. of Guidances (see Note 2) | Directionally consistent with IERP findings (See Note 5) | Developer | PMOS Liaison
2007-06.2 | Phase 2 System Protection Coordination | Archived-Not for Metrics | The standard passed overwhelmingly along with the definitions. BOT adopted August 11, 2016 and filed with FERC on September 2, 2016. Excluded from Metrics due very long period, 10 years. There was 5 years from SAR to first activity. | PRC-001-1.1.(Ret), PER-006-1 (New), and revision to definitions of Operational Planning Analysis and Real-time Assessment. | NERC-imposed deadline of 12/31/2015 | N/A | 1 - Move PRC-001, R1 to Training | 6 | 1 | Yes - PRC-001-1.1(ii), R1 was noted as duplicative of TOP-006-2 R3, but TOP-006 was retired without addressing R1 under TOP/IRO in 2015. | Scott Barfield-McGinnis | Brenda Hampton
2009-02 | Real-time Reliability Monitoring and Analysis Capabilities | Archived | 0 | New IRO-018-1 and TOP-010-1 | N/A | N/A | N/A | 3 | 0 | N/A | Mark Olson | Jennifer Sterling
2010-14.2.1a | Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | Archived | Passed final ballot with 72% approval February 2016. Adopted by NERC BOT in February 2016. Filed with FERC in April 2016. | BAL-005 | N/A | N/A | N/A | N/A | 4 | N/A | Darrel Richardson | Ken Goldsmith
2010-14.2.1b | Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | Archived | Passed final ballot with 80% approval February 2016. Adopted by NERC BOT in February 2016. Filed with FERC in April 2016. | FAC-001 | N/A | N/A | 11 | 7 | 1 | N/A | Darrel Richardson | Ken Goldsmith
2010-14.2.1c | Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | Archived | Passed final ballot with 94% approval February 2016. Adopted by NERC BOT in February 2016. Filed with FERC in April 2016. | BAL-006 | N/A | N/A | N/A | N/A | N/A | N/A | Darrel Richardson | Ken Goldsmith
2010-14.2.2 | Phase 2 of Balancing Authority Reliability-based Controls - BAL-004-2 | Archived | Filed with regulators on November 10, 2016. | BAL-004 | N/A | N/A | N/A | N/A | 4 | 0 | Darrel Richardson | Ken Goldsmith
2015-04 | Alignment of Terms | Terminated | SDT is developing recommendations to present to SC. The Phase II work was completed in February 2016 and the proposed recommendations were submitted for consideration at the March 2016 meeting. The item was pulled from the SC agenda based on a request from the SC chair, Brian Murphy. The SDT reviewed the revisions proposed by the SC chair, and determined to move forward with submitting the recommendations as developed by the SDT. The Phase II recommendation document will be resubmitted for inclusion on the September 2016 SC agenda. | Report on process (Phase II Improvement Report) | N/A | Low | N/A | N/A | N/A | N/A | Lacey Ourso | Andrew Gallo
2015-07 | Internal Communications Capabilities | Archived | Filing anticipated in late August. | COM-001-3 | N/A | High | N/A | 1 | N/A | N/A | Darrel Richardson | Brenda Hampton
2015-INT-02 | Interpretation of CIP-007-5 for Foxguard Solutions | Terminated | Currently on hold. SC approved RFI and for the interpretation drafting team to be formed in April 2016. | CIP-007-5 | N/A | N/A | N/A | N/A | N/A | N/A | Lacey Ourso | Brian Murphy
2015-INT-03 | Interpretation of TOP-002-2.1b for FMPP | Terminated | Currently on hold. Interpretation drafting team recommendations were submitted to the SC in February 2016. | TOP-002-2.1b | N/A | Low | N/A | N/A | N/A | N/A | Lacey Ourso | Brian Murphy
2016-02a | Modifications to CIP Standards | Archived | Petition was filed on March 3, 2017 requesting approval. TD at Lows resulted in a balloted CIP-003-7(i), which was not captured in the dates. "(i)" was dropped in the BOT presentation and filing and the standard was filed as CIP-003-7 | LERC Definition & CIP-003-7 | Directive: March 31, 2017 (LERC only) (March 31 in SAR) | High | N/A | 1 | N/A | N/A | Al McMeekin | Ken Lanehome and Ash Mayfield

## Metrics (hidden)
|  |  |  | Intercept |  | 517 |  |  |  |  | Weight Factor |  | 142 | HOME
Project | Title | Status | SAR Posting Start Date | Final Ballot Date | Baseline End Date | Completed Actual No. of Days | Active Project Calculated No. of Days | Baseline No. of Days based on Team Est. | Priority | No. of Directives | Number of Guidances | No. of Standards | Weighting Factor | No. of Days Expected Based on Complexity | Relative Diff % | 18-Month Baseline | Data Used for 5-Year Filing 2019
2006-03 | Project 2006-03 System Restoration and Blackstart | Metrics-Pre 2009 | 2006-11-06 | 2009-05-18 | 0 | 924 |  | 0 | 2 | 0 | 5 | 3 | 2.5 | 872 | 5.628% | 547.5
2018-03 | Standards Efficiency Review Retirements (SER-Phase I) | Archived | 2018-08-28 | 2019-05-02 | 2019-08-01 |  | 338 | 338 | 0 | 0 | 0 | 1 | 0.25 | 552.5 | #DIV/0! | 547.5
2006-06 | Reliability Coordination | Metrics-Pre 2013 | 2007-01-15 | 2012-09-17 | 0 | 2072 |  | 0 | 3 | 8 | 5 | 8 | 6 | 1369 | 33.93% | 547.5
2006-07 | ATC/TTC/AFC and CBM/TRM Revisions | Void | 2005-07-08 | 2009-01-29 | 0 | 1301 |  | 0 | 2 | 62 | 16 | 6 | 21.5 | 3570 | -174.4% | 547.5
2006-08 | Reliability Coordination - Transmission Loading Relief | Metrics-Pre 2013 | 2006-07-24 | 2010-08-22 | 0 | 1490 |  | 0 | 2 | 4 | 3 | 3 | 3 | 943 | 36.71% | 547.5
2007-02 | Operating Personnel Communications Protocols | Metrics | 2007-03-19 | 2014-04-07 | 0 | 2576 |  | 0 | 3 | 1 | 0 | 1 | 1.25 | 694.5 | 73.04% | 547.5
2007-03 | Real-time Transmission Operations | Metrics-Pre 2009 | 2007-05-15 | 2013-05-06 | 0 | 2183 |  | 0 | 3 | 4 | 21 | 3 | 7.75 | 1617.5 | 25.9% | 547.5
2007-04 | Back-up Facilities | Metrics-Pre 2013 | 2006-11-06 | 2010-07-26 | 0 | 1358 |  | 0 | 2 | 6 | 1 | 1 | 2.5 | 872 | 35.79% | 547.5
2007-06 | System Protection Coordination | Metrics | 2012-05-21 | 2015-10-14 | 2013-10-31 | 1241 |  | 528 | 3 | 0 | 0 | 1 | 1 | 659 | 46.9% | 547.5 | 2019 Filing
2012-09 | IRO Review | Void | 0 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 8 | 2.5 | 872 | #DIV/0! | 547.5
2015-09 | Establish and Communicate System Operating Limits | Archived | 2015-08-20 | 2021-05-10 | 2020-02-21 |  | 1194 | 1646 | 2 | 0 | 0 | 7 | 2.25 | 836.5 | #DIV/0! | 547.5
2007-06.2 | Phase 2 System Protection Coordination | Archived-Not for Metrics | 2007-06-11 | 2016-05-26 | 2016-08-04 | 3272 |  | 3342 | 2 | 6 | 1 | 2 | 2.75 | 907.5 | 72.26% | 547.5
2007-09 | Generator Verification | Metrics-Pre 2013 | 2007-04-18 | 2013-03-27 | 0 | 2170 |  | 0 | 3 | 5 | 2 | 6 | 4 | 1085 | 50% | 547.5
2007-11 | Disturbance Monitoring | Metrics | 2007-03-22 | 2014-11-06 | 0 | 2786 |  | 0 | 3 | 0 | 1 | 2 | 1.5 | 730 | 73.8% | 547.5
2007-12 | Frequency Response | Metrics-Pre 2013 | 2005-01-17 | 2012-12-21 | 0 | 2895 |  | 0 | 3 | 10 | 0 | 1 | 3.5 | 1014 | 64.97% | 547.5
2007-14 | Coordinate Interchange ― Timing Table | Metrics-Pre 2009 | 2007-03-19 | 2008-09-22 | 0 | 553 |  | 0 | 3 | 0 | 0 | 3 | 1.5 | 730 | -32.01% | 547.5
2007-17 | Protection System Maintenance and Testing Protection System Maintenance and Testing Protection System Maintenance and Testing | Metrics | 2007-06-11 | 2012-10-24 | 0 | 1962 |  | 0 | 3 | 6 | 1 | 4 | 3.5 | 1014 | 48.32% | 547.5
2016-02d | Modifications to CIP Standards | Posted | 2019-05-30 | 2024-04-12 | 2021-05-28 |  | 1156 | 729 | 3 | 1 | 0 | 5 | 2.25 | 836.5 | #DIV/0! | 547.5
2007-17.2 | Protection System Maintenance and Testing - Phase 2 (Reclosing Relays) | Metrics | 2013-04-05 | 2016-10-25 | 2013-10-31 | 1299 |  | 209 | 3 | 1 | 0 | 1 | 1.25 | 694.5 | 46.54% | 547.5 | 2019 Filing
2007-17.3 | (PRC-005-X) Protection System Maintenance and Testing - Phase 3 (Sudden Pressure Relays) | Metrics | 2014-02-13 | 2014-10-29 | 0 | 258 |  | 0 | 3 | 1 | 0 | 1 | 1.25 | 694.5 | -169.2% | 547.5
2007-17.4 | PRC-005 FERC Order No. 803 Directive | Metrics | 2015-03-12 | 2015-10-26 | 2016-01-31 | 228 |  | 325 | 3 | 1 | 0 | 1 | 1.25 | 694.5 | -204.6% | 547.5 | 2019 Filing
2015-02 | Periodic Review of Emergency Operations | Void | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 | 0 | 4 | 1.25 | 694.5 | #DIV/0! | 547.5
2017-04 | Periodic Review of Interchange Scheduling and Coordination Standards | Archived | 0 | 0 | 0 | 0 |  | 0 | 3 | 0 | 0 | 4 | 1.75 | 765.5 | #DIV/0! | 547.5
2008-02 | Undervoltage Load Shedding (UVLS) & Underfrequency Load Shedding (UFLS) | Metrics | 2010-01-20 | 2014-10-31 | 0 | 1745 |  | 0 | 3 | 2 | 1 | 2 | 2 | 801 | 54.1% | 547.5
2008-02.2 | Phase 2 of Undervoltage Load Shedding (UVLS): Misoperations | Metrics | 2014-09-29 | 2015-04-27 | 2015-07-31 | 210 |  | 305 | 1 | 0 | 0 | 2 | 0.75 | 623.5 | -196.9% | 547.5 | 2019 Filing
2008-06 | Cyber Security Order 706 Version 5 CIP Standards | Void | 2008-09-22 | 2012-11-05 | 0 | 1505 |  | 0 | 3 | 62 | 22 | 10 | 24.25 | 3960.5 | -163.2% | 547.5
2008-12 | Coordinate Interchange Standards | Metrics | 2008-07-02 | 2014-02-05 | 0 | 2044 |  | 0 | 2 | 1 | 7 | 5 | 3.75 | 1049.5 | 48.65% | 547.5
2009-01 | Disturbance Sabotage Reporting | Metrics-Pre 2013 | 2009-04-22 | 2012-11-05 | 0 | 1293 |  | 0 | 3 | 9 | 4 | 2 | 4.5 | 1156 | 10.6% | 547.5
2015-03 | Periodic Review of System Operating Limit Standards | Void | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 | 0 | 3 | 1 | 659 | #DIV/0! | 547.5
2009-02 | Real-time Reliability Monitoring and Analysis Capabilities | Archived | 2015-07-16 | 2016-02-26 | 2016-01-11 | 225 |  | 179 | 3 | 3 | 0 | 2 | 2 | 801 | -256% | 547.5 | 2019 Filing
2009-03 | Emergency Operations | Metrics | 2009-12-07 | 2014-11-06 | 0 | 1795 |  | 0 | 3 | 9 | 4 | 4 | 5 | 1227 | 31.64% | 547.5
2009-06 | Facility Ratings | Metrics-Pre 2013 | 2009-01-20 | 2011-05-23 | 0 | 853 |  | 0 | 2 | 2 | 0 | 1 | 1.25 | 694.5 | 18.58% | 547.5
2009-08 | Nuclear Plant Interface Coordination | Metrics-Pre 2009 | 2009-02-02 | 2009-07-20 | 0 | 168 |  | 0 | 1 | 7 | 0 | 1 | 2.25 | 836.5 | -397.9% | 547.5
2009-10 | Interpretation − PRC-005-1, R1 − CMPWG | Void | 2009-03-09 | 2009-08-06 | 0 | 150 |  | 0 | 1 | 0 | 0 | 1 | 0.5 | 588 | -292% | 547.5
2009-17 | Interpretation of PRC-004-1 and PRC-005-1 for Y-W Electric and Tri-State | Void | 2009-06-30 | 2010-12-03 | 0 | 521 |  | 0 | 1 | 0 | 0 | 2 | 0.75 | 623.5 | -19.67% | 547.5
2009-21 | Cyber Security Ninety-Day Response | Void | 2009-10-13 | 2009-12-14 | 0 | 62 |  | 0 | 3 | 0 | 0 | 1 | 1 | 659 | -962.9% | 547.5
2010-01 | Training | Metrics | 2013-07-19 | 2014-02-05 | 0 | 201 |  | 0 | 0 | 4 | 3 | 1 | 2 | 801 | -298.5% | 547.5
2010-02 | Connecting New Facilities to the Grid | Metrics | 2013-08-01 | 2014-06-23 | 0 | 326 |  | 0 | 1 | 1 | 1 | 2 | 1.25 | 694.5 | -113% | 547.5
2010-03 | Modeling Data (MOD B) | Metrics | 2013-09-09 | 2014-02-05 | 0 | 149 |  | 0 | 0 | 17 | 2 | 2 | 5.25 | 1262.5 | -747.3% | 547.5
2010-04 | Demand Data (MOD C) | Metrics | 2013-07-22 | 2014-05-05 | 0 | 287 |  | 0 | 0 | 10 | 4 | 1 | 3.75 | 1049.5 | -265.7% | 547.5
2010-04.1 | MOD-031 FERC Order No. 804 Directives | Metrics | 2015-04-16 | 2015-10-15 | 2015-07-15 | 182 |  | 90 | 0 | 1 | 1 | 1 | 0.75 | 623.5 | -242.6% | 547.5 | 2019 Filing
2010-14.2 | Periodic Review of BAL Standards | Void | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 | 0 | 2 | 0.75 | 623.5 | #DIV/0! | 547.5
2010-05.1 | Protection System (Misoperations) | Metrics | 2011-06-10 | 2014-08-07 | 2013-10-30 | 1154 |  | 873 | 3 | 0 | 2 | 1 | 1.5 | 730 | 36.74% | 547.5
2010-05.2 | Phase 2 of Protection Systems | Metrics | 2014-02-18 | 2014-11-06 | 0 | 261 |  | 0 | 2 | 1 | 2 | 29 | 8.5 | 1724 | -560.5% | 547.5
2010-05.3 | Phase 3 of Protection Systems: Remedial Action Schemes (RAS) | Metrics | 2014-02-18 | 2016-04-29 | 2016-04-30 | 801 |  | 802 | 3 | 0 | 0 | 5 | 2 | 801 | 0% | 547.5 | 2019 Filing
2010-07 | Generator Requirements at the Transmission Interface | Metrics-Pre 2013 | 2010-02-12 | 2012-05-03 | 0 | 811 |  | 0 | 3 | 2 | 0 | 2 | 1.75 | 765.5 | 5.61% | 547.5
2010-07.1 | Vegetation Management | Metrics | 2015-08-24 | 2016-02-08 | 2016-04-08 | 168 |  | 228 | 3 | 2 | 0 | 1 | 1.5 | 730 | -334.5% | 547.5 | 2019 Filing
2010-09 | Cyber Security Order 706B Nuclear Plant Implementation Plan | Metrics-Pre 2013 | 2009-07-20 | 2010-07-02 | 0 | 347 |  | 0 | 0 | 2 | 0 | 8 | 2.5 | 872 | -151.3% | 547.5
2010-10 | FAC Order 729 | Metrics-Pre 2013 | 2010-03-15 | 2011-01-23 | 0 | 314 |  | 0 | 0 | 5 | 3 | 1 | 2.25 | 836.5 | -166.4% | 547.5
2010-11 | TPL Table 1 Order | Metrics-Pre 2013 | 2010-04-15 | 2013-01-31 | 0 | 1022 |  | 0 | 0 | 7 | 2 | 4 | 3.25 | 978.5 | 4.256% | 547.5
2010-12 | Order 693 Directives | Void | 2010-06-18 | 2010-07-31 | 0 | 43 |  | 0 | 0 | 5 | 2 | 6 | 3.25 | 978.5 | -2176% | 547.5
2010-13.1 | Phase 1 of Relay Loadability: Transmission | Metrics-Pre 2009 | 2006-01-16 | 2008-02-09 | 0 | 754 |  | 0 | 3 | 19 | 0 | 0 | 5.5 | 1298 | -72.15% | 547.5
2010-13.2 | Phase 2 Relay Loadability: Generation | Metrics-Pre 2013 | 2012-10-05 | 2013-09-13 | 0 | 343 |  | 0 | 3 | 0 | 1 | 1 | 1.25 | 694.5 | -102.5% | 547.5
2010-13.3 | Phase 3 of Relay Loadability: Stable Power Swings | Metrics | 2014-02-27 | 2014-12-16 | 0 | 292 |  | 0 | 3 | 2 | 1 | 1 | 1.75 | 765.5 | -162.2% | 547.5
2010-14.1 | Phase 1 of Balancing Authority Reliability-based Controls: Reserves | Metrics | 2012-06-04 | 2015-10-08 | 2016-02-08 | 1221 |  | 1344 | 2 | 6 | 0 | 1 | 2.25 | 836.5 | 31.49% | 547.5 | 2019 Filing
2010-14.2.1a | Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | Archived | 2014-07-16 | 2016-02-08 | 2016-02-04 | 572 |  | 568 | 1 | 0 | 4 | 1 | 1.5 | 730 | -27.62% | 547.5 | 2019 Filing
2010-14.2.1b | Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | Archived | 2014-07-16 | 2016-02-08 | 2016-02-04 | 572 |  | 568 | 1 | 7 | 1 | 1 | 2.5 | 872 | -52.45% | 547.5 | 2019 Filing
2010-14.2.1c | Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | Archived | 2014-07-16 | 2016-02-08 | 2016-02-04 | 572 |  | 568 | 1 | 0 | 0 | 1 | 0.5 | 588 | -2.797% | 547.5 | 2019 Filing
2010-14.2.2 | Phase 2 of Balancing Authority Reliability-based Controls - BAL-004-2 | Archived | 2015-03-17 | 2015-12-17 | 2015-12-11 | 275 |  | 269 | 1 | 0 | 4 | 1 | 1.5 | 730 | -165.5% | 547.5 | 2019 Filing
2010-17 | Proposed Definition of Bulk Electric System | Metrics-Pre 2013 | 2010-12-17 | 2013-11-18 | 0 | 1067 |  | 0 | 3 | 7 | 2 | 1 | 3.25 | 978.5 | 8.294% | 547.5
2011-INT-01 | Revision of MOD-028-1 to address FPL Request for Interpretation | Void | 2011-10-03 | 2011-12-22 | 0 | 80 |  | 0 | 1 | 0 | 0 | 1 | 0.5 | 588 | -635% | 547.5
2012-05 | ATC Revisions (MOD A) | Metrics-Pre 2013 | 2013-07-11 | 2013-12-20 | 0 | 162 |  | 0 | 2 | 0 | 0 | 6 | 2 | 801 | -394.4% | 547.5
2012-13 | NUC - Nuclear Plant Interface Coordination | Metrics | 2014-02-12 | 2014-07-03 | 0 | 141 |  | 0 | 1 | 0 | 0 | 1 | 0.5 | 588 | -317% | 547.5
2012-INT-02 | Interpretation 2012-INT-02 TPL-003-0a and TPL-004-0 for SPCS | Void | 2012-06-20 | 2013-01-31 | 0 | 225 |  | 0 | 1 | 0 | 0 | 2 | 0.75 | 623.5 | -177.1% | 547.5
2013-02 | Paragraph 81 | Void | 2012-08-03 | 2013-01-17 | 0 | 167 |  | 0 | 1 | 0 | 0 | 36 | 9.25 | 1830.5 | -996.1% | 547.5
2013-03 | Geomagnetic Disturbance Mitigation | Archived | 2016-12-16 | 2017-10-30 | 2018-03-02 | 318 |  | 441 | 3 | 4 | 13 | 1 | 5.25 | 1262.5 | -297% | 547.5 | 2019 Filing
2013-04 | Voltage & Reactive Control | Metrics | 2013-07-19 | 2014-05-05 | 0 | 290 |  | 0 | 0 | 4 | 4 | 2 | 2.5 | 872 | -200.7% | 547.5
2014-01 | Standards Applicability for Dispersed Generation Resources | Metrics | 2013-11-20 | 2015-03-11 | 2015-01-15 | 476 |  | 421 | 2 | 0 | 0 | 3 | 1.25 | 694.5 | -45.9% | 547.5 | 2019 Filing
2014-02 | Critical Infrastructure Protection Standards Version 5 Revisions | Metrics | 2014-01-17 | 2015-02-02 | 2014-10-15 | 381 |  | 271 | 3 | 13 | 0 | 10 | 6.5 | 1440 | -278% | 547.5 | 2019 Filing
2014-03 | Revisions to TOP and IRO Standards | Metrics | 2014-02-21 | 2015-01-21 | 2014-10-15 | 334 |  | 236 | 3 | 1 | 0 | 9 | 3.25 | 978.5 | -193% | 547.5 | 2019 Filing
2014-04 | Physical Security | Metrics | 2014-03-21 | 2015-04-29 | 2015-06-30 | 404 |  | 466 | 3 | 3 | 0 | 1 | 1.75 | 765.5 | -89.48% | 547.5 | 2019 Filing
2015-07 | Internal Communications Capabilities | Archived | 2015-06-11 | 2016-06-24 | 2016-04-11 | 379 |  | 305 | 1 | 1 | 0 | 1 | 0.75 | 623.5 | -64.51% | 547.5 | 2019 Filing
2015-08a | Emergency Operations | Archived | 2015-07-21 | 2017-01-06 | 2016-06-16 | 535 |  | 331 | 2 | 1 | 0 | 3 | 1.5 | 730 | -36.45% | 547.5 | 2019 Filing
2015-08b | Emergency Operations | Archived | 2015-07-21 | 2017-02-02 | 2016-09-01 | 562 |  | 408 | 2 | 1 | 0 | 1 | 1 | 659 | -17.26% | 547.5 | 2019 Filing
2015-10 | Single Points of Failure TPL-001 | Archived | 2015-11-12 | 2018-10-22 | 2018-01-17 | 1075 |  | 797 | 3 | 2 | 0 | 1 | 1.5 | 730 | 32.09% | 547.5 | 2019 Filing
2015-04 | Alignment of Terms | Terminated | 0 | 0 | 0 | 0 |  | 0 | 3 | 0 | 0 | 1 | 1 | 659 | #DIV/0! | 547.5
2015-INT-01 | Interpretation of CIP-002-5.1 for Energy Sector Security Consortium (EnergySec) | Archived-Not for Metrics | 2016-07-27 | 2016-10-24 | 2016-10-14 | 89 |  | 79 | 3 | 0 | 0 | 1 | 1 | 659 | -640.4% | 547.5
2016-01 | Modifications to TOP and IRO Standards | Archived | 2016-01-22 | 2016-12-12 | 2017-01-27 | 325 |  | 371 | 1 | 0 | 0 | 2 | 0.75 | 623.5 | -91.85% | 547.5 | 2019 Filing
2016-02a | Modifications to CIP Standards | Archived | 2016-03-23 | 2016-12-19 | 2017-01-15 | 271 |  | 298 | 3 | 1 | 0 | 1 | 1.25 | 694.5 | -156.3% | 547.5 | 2019 Filing
2016-02b | Modifications to CIP Standards | Archived | 2016-03-23 | 2018-08-09 | 2017-10-27 | 869 |  | 583 | 3 | 2 | 0 | 1 | 1.5 | 730 | 16% | 547.5 | 2019 Filing
2015-INT-03 | Interpretation of TOP-002-2.1b for FMPP | Terminated | 0 | 0 | 0 | 0 |  | 0 | 3 | 0 | 0 | 1 | 1 | 659 | #DIV/0! | 547.5
2016-03 | Cyber Security Supply Chain Management | Archived | 2016-10-20 | 2017-07-20 | 2017-06-30 | 273 |  | 253 | 1 | 1 | 0 | 3 | 1.25 | 694.5 | -154.4% | 547.5 | 2019 Filing
2016-04 | Modifications to PRC-025-1 | Archived | 2016-09-16 | 2018-01-18 | 2018-01-18 | 489 |  | 489 | 2 | 0 | 0 | 1 | 0.75 | 623.5 | -27.51% | 547.5 | 2019 Filing
2016-02c | Modifications to CIP Standards | Archived | 2016-03-23 | 2020-04-05 | 2017-10-27 |  | 1031 | 583 | 3 | 0 | 0 | 11 | 3.5 | 1014 | #DIV/0! | 547.5
2016-02e | Modifications to CIP Standards | Archived | 2016-03-23 | 2019-04-29 | 2019-02-04 |  | 1031 | 1048 | 3 | 0 | 0 | 1 | 1 | 659 | #DIV/0! | 547.5
2017-02 | Modifications to Personnel Performance, Training, and Qualifications Standards | Archived | 2017-06-21 | 2018-04-12 | 2018-05-06 | 295 |  | 319 | 2 | 0 | 0 | 2 | 1 | 659 | -123.4% | 547.5 | 2019 Filing
2017-01 | Modifications to BAL-003-1.1 | Archived | 2017-06-19 | 2019-10-24 | 2019-04-26 |  | 676 | 676 | 2 | 0 | 0 | 1 | 0.75 | 623.5 | #DIV/0! | 547.5
2017-03 | Periodic Review of FAC-008-3 Standard | Archived | 0 | 0 | 0 | 0 |  | 0 | 3 | 0 | 0 | 1 | 1 | 659 | #DIV/0! | 547.5
2017-05 | Periodic Review NUC-001-3 | Archived | 0 | 0 | 0 | 0 |  | 0 | 3 | 0 | 0 | 1 | 1 | 659 | #DIV/0! | 547.5
2017-06 | Project 2017-06 Modifications to BAL-002-2 | Archived | 2017-06-20 | 2018-07-08 | 0 | 383 |  | 0 | 2 | 0 | 0 | 1 | 0.75 | 623.5 | -62.79% | 547.5 | 2019 Filing
2017-07 | Stds Alignment with Registration | Pending Regulatory Filing | 2017-08-01 | 2020-01-19 | 2020-01-16 | 901 |  | 898 | 3 | 0 | 0 | 7 | 2.5 | 872 | 3.219% | 547.5
2018-01 | Canadian-specific Revisions to TPL-007-2 | Archived | 2018-03-30 | 2018-12-10 | 2019-02-03 | 255 |  | 310 | 2 | 0 | 0 | 1 | 0.75 | 623.5 | -144.5% | 547.5 | 2019 Filing
2018-04 | Modifications to PRC-024-2 | Pending Regulatory Filing | 2018-12-19 | 2019-12-13 | 2019-10-24 |  | 309 | 309 | 3 | 0 | 0 | 1 | 1 | 659 | #DIV/0! | 547.5
2019-01 | Modifications to TPL-007-3 | Archived | 2019-02-25 | 2019-11-22 | 2020-03-01 |  | 309 | 370 | 2 | 1 | 0 | 1 | 1 | 659 | #DIV/0! | 547.5
2007-18 | Reliability Based Control | Void | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 517 | #DIV/0! | 547.5
2018-02 | Modifications to CIP-008 Cyber Security Incident Reporting | Archived | 2018-08-10 | 2019-01-22 | 2019-01-19 | 165 |  | 162 | 1 | 1 | 0 | 1 | 0.75 | 623.5 | -277.9% | 547.5 | 2019 Filing
2015-09b | Establish and Communicate System Operating Limits | Archived | 0 | 0 | 0 | 0 |  | 0 | 2 | 1 | 1 | 0 | 1 | 659 | #DIV/0! | 547.5
2015-INT-02 | Interpretation of CIP-007-5 for Foxguard Solutions | Terminated | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 517 | #DIV/0! | 547.5
2017-08 | Open - Available | Void | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 517 | #DIV/0! | 547.5
Formulas:
Completed Actual No. of Days = IF(AND(DAYS([Final Ballot Date],[SAR Posting Start Date])<4000,DAYS([Final Ballot Date],[SAR Posting Start Date])>0),DAYS([Final Ballot Date],[SAR Posting Start Date]),0)

## Regression (hidden)
SUMMARY OUTPUT 2019 Filing (Projects Completed in the last 10 years)
Regression Statistics
Multiple R | 0.34721
R Square | 0.12056
Adjusted R Square | 0.10457
Standard Error | 701.8978
Observations | 57
ANOVA
| df | SS | MS | F | Significance F
Regression | 1 | 3714386.1159 | 3714386.1159 | 7.5394 | 0.0081406
Residual | 55 | 27096329.3578 | 492660.5338
Total | 56 | 30810715.4737
| Coefficients | Standard Error | t Stat | P-value | Lower 95% | Upper 95% | Lower 95.0% | Upper 95.0%
Intercept | 517.4002 | 152.1783 | 3.4 | 0.001261 | 212.428 | 822.3723 | 212.428 | 822.3723
Weighting Factor | 141.7759 | 51.6336 | 2.7458 | 0.0081406 | 38.2998 | 245.252 | 38.2998 | 245.252
RESIDUAL OUTPUT
Observation | Predicted Completed Actual No. of Days | Residuals
1 | 871.8398 | 52.1602
2 | 1368.0554 | 703.9446
3 | 942.7278 | 547.2722
4 | 694.62 | 1881.38
5 | 1616.1632 | 566.8368
6 | 871.8398 | 486.1602
7 | 659.176 | 581.824
8 | 1084.5036 | 1085.4964
9 | 730.064 | 2055.936
10 | 1013.6157 | 1881.3843
11 | 730.064 | -177.064
12 | 1013.6157 | 948.3843
13 | 694.62 | -491.62
14 | 694.62 | -436.62
15 | 694.62 | -466.62
16 | 800.9519 | 944.0481
17 | 623.7321 | -413.7321
18 | 1049.0597 | 994.9403
19 | 1155.3916 | 137.6084
20 | 800.9519 | -575.9519
21 | 1226.2795 | 568.7205
22 | 694.62 | 158.38
23 | 836.3959 | -668.3959
24 | 694.62 | -368.62
25 | 730.064 | 423.936
26 | 1722.4951 | -1461.4951
27 | 800.9519 | 0.048098
28 | 765.5079 | 45.4921
29 | 730.064 | -562.064
30 | 1297.1675 | -543.1675
31 | 694.62 | -351.62
32 | 765.5079 | -473.5079
33 | 836.3959 | 384.6041
34 | 730.064 | -158.064
35 | 871.8398 | -299.8398
36 | 588.2881 | -16.2881
37 | 730.064 | -455.064
38 | 978.1717 | 88.8283
39 | 800.9519 | -638.9519
40 | 588.2881 | -447.2881
41 | 1261.7235 | -943.7235
42 | 694.62 | -218.62
43 | 1438.9433 | -1057.9433
44 | 978.1717 | -644.1717
45 | 765.5079 | -361.5079
46 | 623.7321 | -244.7321
47 | 730.064 | -195.064
48 | 659.176 | -97.176
49 | 730.064 | 344.936
50 | 623.7321 | -298.7321
51 | 694.62 | -423.62
52 | 730.064 | 138.936
53 | 694.62 | -421.62
54 | 623.7321 | -134.7321
55 | 659.176 | -364.176
56 | 623.7321 | -240.7321
57 | 623.7321 | -368.7321

## Roster
PMOS ROSTER & LIAISON PROJECT ASSIGNMENTS | [29 empty] | HOME
Position | Term | Name | Entity | # Std. | 2016-02d | 2017-01b | 2019-04 | 2020-02 | 2020-06 | 2021-01 | 2021-02 | 2021-03 | 2021-04b | 2021-05 | 2021-06 | 2021-08 | 2022-01 | 2022-02 | 2022-03 | 2022-04 | 2022-05 | 2023-01 | 2023-02 | 2023-03 | 2023-04 | 2023-05 | 2023-06 | 2023-07 | 2023-08 | Insert New
Chair | 2024-2025 | Michael Brytowski | Great River Energy | 3 | [8 empty] | 1 |  | 2
Vice Chair | 2023-2024 | Charles Yeung | Southwest Power Pool, Inc. | 7 |  | 1 | [6 empty] | 1 |  | 2 |  |  |  |  | 3
Member | 2024-2025 | Kirk Rosener | CPS Energy | 8 | 5 |  |  |  |  | 2 | [14 empty] | 1
Member | 2023-2024 | Anthony Westenkirchner | Evergy | 3 |  |  |  | 1 |  |  | 1 |  |  | 1
Member | 2024-2025 | Joseph Gatten | Xcel Energy | 3 |  |  | 1 |  |  |  | 1 | [7 empty] | 1
Member | 2024-2025 | Sarah Habriga | American Transmission Co. LLC | 4 |  |  | 1 |  | 2 | [6 empty] | 1
Member | 2024-2025 | Claudine Fritz | Exelon Corporation | 7 | [9 empty] | 1 |  |  | 1 |  |  | 3 |  |  | 1 |  |  |  | 1
Member | 2024-2025 | Ellese Murphy | Duke Energy | 7 |  |  |  |  | 2 |  |  | 1 | [5 empty] | 2 |  |  | 1 | [5 empty] | 1
Member | 2024-2025 | Pamela Hunter | Southern Company | 3 |  | 1 |  | 1 | [20 empty] | 1
Member | 2023-2024 | Terri Pyle | Oklahoma Gas & Electric | 5 | [13 empty] | 2 | 1 |  |  | 1 | 1
Member | 2023-2024 | Ruida Shu | NPCC | 13 | 5 |  |  |  |  | 2 | [6 empty] | 1 |  |  |  | 1 | 1 |  | 3
Member | 2024-2025 | Donovan Crane | WECC | 3 | [21 empty] | 2 |  | 1
Member | 2024-2025 | Jason Chandler | Consolidated Edison Inc. | 3 | [21 empty] | 2 |  | 1
Member | 2024-2025 | Jennifer Richardson | LS Power | 1 | [11 empty] | 1
Member | 2024-2025 | Darrel Grumman | Electric Power Engineers LLC | 3 |  |  |  | 1 |  |  |  | 1 | [16 empty] | 1
Member | 2024-2025 | Ron Sporseen | Bonneville Power Administration | 4 | [19 empty] | 3 | 1
Non-voting Member | SC Chair | Todd Bennett | Associated Electric Cooperative
Non-voting Member | SC Vice Chair | Troy Brumfield | American Transmission Co. LLC
NERC Staff | NERC Staff | Chris Larson, Secretary | NERC
NERC Staff | NERC Staff | Marisa Hecht, Legal | NERC
NERC Staff | NERC Staff | Lauren Perotti, Legal | NERC
INSERT NEW ROW
*The Primary PMOS liaison is bold white, and the active secondary PMOS liaison is bold black
PTS Change Control
Reason for Update | Date | Notes
New Tab | 2019-05-15 | Created tab with roster and liaison work load.
Formatting | 2019-07-30 | Added affected standard weighting, improved conditional formatting and abililty to add new rows and columns.
Data Correction | 2019-07-30 | Corrected Colby Bellville's company name from Duke to Cooperative Energy.
Liaison Resignation | 2019-09-18 | Sean Cavote resigned from the PMOS.
Update | 2020-01-29 | Scott Barfield is no longer the PMOS secretary, Elsa Prince is the new PMOS secretary.
Update | 2020-03-18 | Updated SC Chair and SC Vice Chair information.
Formatting | 2020-05-06 | Modified the conditional formatting to show which standards line up with the PMOS liaisons.
Liaison Additions | 2020-11-17 | Added R. Darrah, A. Westenkirchner and C. Godoy.
PMOS Chair | 2020-11-17 | Updated the 2-year term of Chair Yeung.
Liaison Resignation | 2020-12-08 | A. Mayfield ended his 2-year term as PMOS liaison.
Liaison Resignation | 2021-04-07 | Q. Morrison will retired at the end of May 2021, his last meeting will be the May 5 PMOS call.
Update | 2021-08-04 | Elsa Prince is no longer the PMOS secretary, Ben Wu is the new PMOS secretary.
Liaison Resignation | 2021-12-13 | Masuncha Bussey resigned from the PMOS.
Liaison Resignation | 2021-12-13 | Mark Pratt resigned from the PMOS.
Liaison Resignation | 2021-12-31 | Colby Bellville ended his 2-year term as PMOS liaison.
Liaison Resignation | 2022-10-01 | Linda Lynch is retiring from NextEra Energy/FPL.
Note on E2: Green-Below the average Brownish - Average Red-Above the average

## SER_Overview (hidden)
Project | Standards Efficiency Review | [5 empty] | Home
Project Name | Overview for PMOS
Status | Other
Comments | SER Working Team provided final recommendation for SC endorsement at April meeting. Additionally, the team is drafting a final report to memorialize and transition the project. The Standards Efficiency Review (SER) Final Report provided below outlines the accomplishments and recommendations from the project. In addition, the four Phase 2 concepts addressed by the SER group are listed below with their respective materials. 1. Evidence Retention Overhaul -SER Evidence Retention Recommendations (Endorsed by SC December 18, 2019, agenda item 9) -SER Evidence Retention White Paper 2. Consolidate Information/Data Exchange Requirements Operation Data Exchange Simplification SAR (Pending SC endorsement January 20, 2021, agenda item 7) 3. Move Requirements to Guidance (incorporated into NERC policy; Risk Mitigation Framework) Framework to Address Known and Emerging Reliability and Security Risks (Endorsed by RSTC December 16, 2020, agenda item 4) 4. Prototype Standard (reframed) SER Recommendation for Standards Template and Drafting Team Training Review​; (Endorsed by SC December 9, 2020, agenda item 6)
Deliverable
Operations Planning Subteam | Amy Casuscelli & Charles Yeung
Real-time Operations Subteam | Mike Brytowski
Long-term Planning Subteam | Linda Lynch
SER Phase 1 | Mike Brytowski & Mark Pratt
SER Phase 2 (Concepts) | Mike Brytowski & Linda Lynch
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Chris Larson
PMOS Liaison | Mark Pratt (primary), Michael Brytowski (secondary)
Affected Standards | See SAR (too many to list)
Last Updated | 2021-07-12
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | [7 empty] | 1
Nominations - DT | [7 empty] | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | [7 empty] | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | [7 empty] | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes

## _2006-03 (hidden)
Project | 2006-03 | [5 empty] | Home
Project Name | Project 2006-03 System Restoration and Blackstart
Status | Metrics-Pre 2009
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote | Test Priority |  | Priority (High, Med, Low is 1, 2, 3) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | Test P81
Number of Directives | 0 | Enter # in column B and description here
No. of Guidances (see Note 2) | 5 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 3 | EOP-001-1, EOP-005-1, and EOP-006-1
Last Updated
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2006-11-06 | 2006-12-05 |  |  | -39027 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2009-05-06 | 2009-05-18 |  |  | -39939 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-01-09 | This project was added for the purpose of metrics.

## _2006-04 (hidden)
Project | 2007-04 | [5 empty] | Home
Project Name | Back-up Facilities
Status | Metrics-Pre 2013
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 6 | Enter # in column B and description here
No. of Guidances (see Note 2) | 1 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | EOP-008
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2006-11-06 | 2006-11-17 |  |  | -39027 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2010-07-16 | 2010-07-26 |  |  | -40375 |  |  | 13
PTB - Present to BOT | 2010-08-05 | 2010-08-06 |  |  | -40395 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-01-09 | This project was added for the purpose of metrics.

## _2006-06 (hidden)
Project | 2006-06 | [5 empty] | Home
Project Name | Reliability Coordination
Status | Metrics-Pre 2013
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote | Test Priority |  | Priority (High, Med, Low is 1, 2, 3) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | Test P81
Number of Directives | 8 | Enter # in column B and description here
No. of Guidances (see Note 2) | 5 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 8 | COM-001-2, COM-0023, and IRO-001-3, IRO-002-3, IRO-005, IRO-014, IRO-015, and IRO-016
Last Updated
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2007-01-15 | 2007-02-14 |  |  | -39097 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2012-09-06 | 2012-09-17 |  |  | -41158 |  |  | 13
PTB - Present to BOT | 2012-11-07 | 2012-11-08 |  |  | -41220 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-01-09 | This project was added for the purpose of metrics.

## _2006-07 (hidden)
Project | 2006-07 | [5 empty] | Home
Project Name | ATC/TTC/AFC and CBM/TRM Revisions
Status | Void
Comments | This project was added for the purpose of metrics. Not used for metrics due to excessive number of directives.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (High, Med, Low is 1, 2, 3) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 62 | Summary of FERC Directives in FERC Orders 693 and 890 and Corresponding NERC Standards and Requirements
No. of Guidances (see Note 2) | 16 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 6 | MOD-001-1, MOD-004-1, MOD-008-1, MOD-028-1, MOD-029-1, and MOD-030-1
Last Updated
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2005-07-08 | 2005-08-08 |  |  | -38541 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2009-01-20 | 2009-01-29 |  |  | -39833 |  |  | 13
PTB - Present to BOT | 2009-11-05 | 2009-11-07 |  |  | -40122 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-01-09 | This project was added for the purpose of metrics.

## _2006-08 (hidden)
Project | 2006-08 | [5 empty] | Home
Project Name | Reliability Coordination - Transmission Loading Relief
Status | Metrics-Pre 2013
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (High, Med, Low is 1, 2, 3) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 4 | Enter number in column B and text here.
No. of Guidances (see Note 2) | 3 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 3 | IRO-006-4, IRO-006-5, IRO-006-EAST-1
Last Updated
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2006-07-24 | 2006-08-23 |  |  | -38922 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2010-08-20 | 2010-08-22 |  |  | -40410 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-01-09 | This project was added for the purpose of metrics.
Formulas:
Projected or Actual End = +[Projected or Actual Start]+30

## _2007-01 (hidden)
Project | 2007-01 | [5 empty] | Home
Project Name | Underfrequency Load Shedding
Status | Metrics-Pre 2013
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | Test P81
Number of Directives | 0 | Enter # in column B and description here
No. of Guidances (see Note 2) | 1 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 2 | EOP-003-1 and PRC-006-0 (Absorbed PRC-007-0, PRC-009-0)
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2006-11-29 | 2006-12-12 |  |  | -39050 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2010-10-18 | 2010-10-28 |  |  | -40469 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-01-09 | This project was added for the purpose of metrics.

## _2007-02 (hidden)
Project | 2007-02 | [5 empty] | Home
Project Name | Operating Personnel Communications Protocols
Status | Metrics
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 1 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | COM-002-4
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2007-03-19 | 2007-04-17 |  |  | -39160 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2014-03-28 | 2014-04-07 |  |  | -41726 |  |  | 13
PTB - Present to BOT | 2014-05-07 | 2014-05-09 |  |  | -41766 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-01-09 | This project was added for the purpose of metrics.

## _2007-03 (hidden)
Project | 2007-03 | [5 empty] | Home
Project Name | Real-time Transmission Operations
Status | Metrics-Pre 2009
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 4 | Enter # in column B and description here
No. of Guidances (see Note 2) | 21 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 3 | EOP-001, EOP-005, and EOP-006
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2007-05-15 | 2007-06-13 |  |  | -39217 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2012-04-27 | 2013-05-06 |  |  | -41026 |  |  | 13
PTB - Present to BOT | 2012-03-08 | 2012-03-09 |  |  | -40976 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-01-09 | This project was added for the purpose of metrics.

## _2007-06 (hidden)
Project | 2007-06 | [5 empty] | Home
Project Name | System Protection Coordination
Status | Metrics
Comments | This project was added for the purpose of metrics. The SAR date was adjusted from 2007 to 2012 due to an intentional delay to 2009 and then to 2012. The baseline final ballot date was taken from the 2013 PTS. It was adjust to 10/31/2015 in the 2015 PTS.
Deliverable | PRC-027-1
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 1
P81 Req (2013)
Number of Directives | 0 | Enter # in column B and description here
No. of Guidances (see Note 2) | 0 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | PRC-001-1
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2012-05-21 | 2012-07-05 |  |  | -41050 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2015-10-05 | 2015-10-14 |  | 2013-10-31 | -42282 |  |  | 13
PTB - Present to BOT | 2015-11-05 | 2015-11-07 |  |  | -42313 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-01-09 | This project was added for the purpose of metrics.

## 2007-06.2 (hidden)
Project | 2007-06.2 | [5 empty] | Home
Project Name | Phase 2 System Protection Coordination
Status | Archived-Not for Metrics
Comments | The standard passed overwhelmingly along with the definitions. BOT adopted August 11, 2016 and filed with FERC on September 2, 2016. Excluded from Metrics due very long period, 10 years. There was 5 years from SAR to first activity.
Deliverable | PRC-001-1.1.(Ret), PER-006-1 (New), and revision to definitions of Operational Planning Analysis and Real-time Assessment.
Deadline | NERC-imposed deadline of 12/31/2015
Priority in RSDP, click to see applicable Footnote | N/A |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | 1 - Move PRC-001, R1 to Training
Number of Directives | 6
No. of Guidances (see Note 2) | 1
Directionally consistent with IERP findings (See Note 5) | Yes - PRC-001-1.1(ii), R1 was noted as duplicative of TOP-006-2 R3, but TOP-006 was retired without addressing R1 under TOP/IRO in 2015.
Developer | Scott Barfield-McGinnis
PMOS Liaison | Brenda Hampton
Affected Standards | 2 | PRC-001-1.1.(ret.), PER-006-1 (new)
Last Updated | 2016-09-29
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  | 0 | 0 |  |  | 1
Nominations - DT | 2015-01-06 | 2015-01-20 | 2015-01-30 | 2015-02-13 | 24 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2007-06-11 | 2007-07-10 |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  | 0 | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  | 0 | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  | 0 | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2015-07-29 | 2015-09-11 | 2015-05-11 | 2015-06-25 | -79 | Regulatory Meeting | 62.55% | 8
CAB - Com/Add Ballot 2 | 2015-10-06 | 2015-11-19 | 2015-07-27 | 2015-09-10 | -71 | Baseline Reset | 57.29% | 9
CAB - Com/Add Ballot 3 | 2016-03-10 | 2016-04-30 | 2016-02-14 | 2016-03-30 | -25 | Change in Approach | 80.57% | 10
CAB - Com/Add Ballot 4 |  |  | 2016-06-01 | 2016-07-16 | 0 | Not needed |  | 11
CAB - Com/Add Ballot 5 |  |  |  | 0 | 0 |  |  | 12
FB - Final Ballot | 2016-05-17 | 2016-05-26 | 2016-07-25 | 2016-08-04 | 69 |  | 82.52% | 13
PTB - Present to BOT | 2016-08-10 | 2016-08-12 | 2016-08-10 | 2016-08-12 | 0 |  |  | 14
Filing - Filing with Regulators | 2016-09-10 | 2016-10-10 | 2016-09-10 | 2016-10-10 | 0 |  |  | 15
PT - Post Approval Training |  |  |  | 0 | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Project split | 2015-05-01 | Phase II was split from Phase I addressing PRC-027 (R3 & R4) using the date 1/6/2015 for PMOS tracking. The date was changed back to the original revised SAR date of 6/11/2007 to 7/10/2007 for metric tracking.
Change in SAR Date | 2015-05-01 | SAR date of 6/11/2007 changed to Nomination - DT date of 1/6/2015 to mark when this portion of the project was split off to address Requirements R1, R2, R5, and R6.
Explain the delay | 2015-05-01 | Did not pass Septmber 2015 ballot and will plan to conduct another SDT meeting and post for additional ballot. Goal to post end of January 2016; however, the SDT's plan to present a PER-005-2 revision met industry opposition during informal outreach. The SDT held a technical conference to resolve - resulting in PER-006-1 and definition changes to OPA and RTA. The first formal comment period for PER-006-1 runs March 10 to April 25 with an initial ballot.
Explain early finish | 2016-06-01 | PER-006-1 did not require an additional planned ballot, passed on initial.

## _2007-09 (hidden)
Project | 2007-09 | [5 empty] | Home
Project Name | Generator Verification
Status | Metrics-Pre 2013
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 5 | Enter # in column B and description here
No. of Guidances (see Note 2) | 2 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 6 | MOD-024-1, MOD-025-1, MOD-026-1, MOD-027-1, PRC-019-1, and PRC-024
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2007-04-18 | 2007-05-02 |  |  | -39190 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2013-03-18 | 2013-03-27 |  |  | -41351 |  |  | 13
PTB - Present to BOT | 2013-05-09 | 2013-05-11 |  |  | -41403 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-01-09 | This project was added for the purpose of metrics.

## _2007-11 (hidden)
Project | 2007-11 | [5 empty] | Home
Project Name | Disturbance Monitoring
Status | Metrics
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 0 | Enter # in column B and description here
No. of Guidances (see Note 2) | 1 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 2 | PRC-002 and PRC-018
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2007-03-22 | 2007-04-20 |  |  | -39163 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2014-10-28 | 2014-11-06 |  |  | -41940 |  |  | 13
PTB - Present to BOT | 2014-11-13 | 2014-11-15 |  |  | -41956 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-01-09 | This project was added for the purpose of metrics.

## _2007-12 (hidden)
Project | 2007-12 | [5 empty] | Home
Project Name | Frequency Response
Status | Metrics-Pre 2013
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 10 | Enter number in column B and text here.
No. of Guidances (see Note 2) | 0 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | BAL-003
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2005-01-17 | 2005-02-17 |  |  | -38369 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2012-12-12 | 2012-12-21 |  |  | -41255 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-01-09 | This project was added for the purpose of metrics.

## _2007-14 (hidden)
Project | 2007-14 | [5 empty] | Home
Project Name | Coordinate Interchange ― Timing Table
Status | Metrics-Pre 2009
Comments | This project was added for the purpose of metrics. Project 2007-05 was merged into this project. It was an URGENT ACTION project.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 0 | Enter number in column B and text here.
No. of Guidances (see Note 2) | 0 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 3 | INT-005, INT-006, and INT-008
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2007-03-19 | 2007-03-30 |  |  | -39160 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2008-09-11 | 2008-09-22 |  |  | -39702 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-01-09 | This project was added for the purpose of metrics.

## _2007-17 (hidden)
Project | 2007-17 | [5 empty] | Home
Project Name | Protection System Maintenance and Testing Protection System Maintenance and Testing Protection System Maintenance and Testing
Status | Metrics
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 6 | Enter number in column B and text here.
No. of Guidances (see Note 2) | 1 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 4 | PRC-005, PRC-008, PRC-011, and PRC-017
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2007-06-11 | 2007-07-10 |  |  | -39244 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2012-10-15 | 2012-10-24 |  |  | -41197 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-01-09 | This project was added for the purpose of metrics.

## _2007-17.2 (hidden)
Project | 2007-17.2 | [5 empty] | Home
Project Name | Protection System Maintenance and Testing - Phase 2 (Reclosing Relays)
Status | Metrics
Comments | This project was added for the purpose of metrics. The baseline final ballot date was taken from the 2013 PTS.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 1 | Enter # in column B and description here
No. of Guidances (see Note 2) | 0 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | PRC-005
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2013-04-05 | 2013-05-06 |  |  | -41369 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-10-16 | 2016-10-25 |  | 2013-10-31 | -42659 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-01-09 | This project was added for the purpose of metrics.

## _2007-17.3 (hidden)
Project | 2007-17.3 | [5 empty] | Home
Project Name | (PRC-005-X) Protection System Maintenance and Testing - Phase 3 (Sudden Pressure Relays)
Status | Metrics
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 1 | Enter # in column B and description here
No. of Guidances (see Note 2) | 0 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | PRC-005
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2014-02-13 | 2014-03-14 |  |  | -41683 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2014-10-20 | 2014-10-29 |  |  | -41932 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-01-09 | This project was added for the purpose of metrics.

## _2007-17.4 (hidden)
Project | 2007-17.4 | [5 empty] | Home
Project Name | PRC-005 FERC Order No. 803 Directive
Status | Metrics
Comments | This project was added for the purpose of metrics. The baseline final ballot date was taken from the 2015 PTS.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 1 | Enter # in column B and description here
No. of Guidances (see Note 2) | 0 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | PRC-005
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2015-03-12 | 2015-04-10 |  |  | -42075 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2015-10-15 | 2015-10-26 |  | 2016-01-31 | -42292 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-01-09 | This project was added for the purpose of metrics.

## _2007-18 (hidden)
Project | 2007-18 | [5 empty] | Home
Project Name | Reliability Based Control
Status | Void
Comments | This project was added for the purpose of metrics. As of July 28, 2010 this project has been merged with Project 2007-05 - Balancing Authority Controls and is now Project 2010-14.1 Phase 1 of Balancing Authority Reliability-based Controls: Reserves. The new project page is available at: Project 2010-14.1 Phase 1 BARC: Reserves
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 0 | Enter # in column B and description here
No. of Guidances (see Note 2) | 0 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 0
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-01-09 | This project was added for the purpose of metrics.

## _2008-02 (hidden)
Project | 2008-02 | [5 empty] | Home
Project Name | Undervoltage Load Shedding (UVLS) & Underfrequency Load Shedding (UFLS)
Status | Metrics
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 2 | Enter # in column B and description here
No. of Guidances (see Note 2) | 1 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 2 | PRC-006 and PRC-010
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2010-01-20 | 2010-02-03 |  |  | -40198 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2014-10-22 | 2014-10-31 |  |  | -41934 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2008-02.2 (hidden)
Project | 2008-02.2 | [5 empty] | Home
Project Name | Phase 2 of Undervoltage Load Shedding (UVLS): Misoperations
Status | Metrics
Comments | This project was added for the purpose of metrics. The baseline final ballot date was taken from the 2015 PTS.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 0 | Enter # in column B and description here
No. of Guidances (see Note 2) | 0 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 2 | PRC-004 and PRC-010
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2014-09-29 | 2014-10-08 |  |  | -41911 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2015-04-17 | 2015-04-27 |  | 2015-07-31 | -42111 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2008-06 (hidden)
Project | 2008-06 | [5 empty] | Home
Project Name | Cyber Security Order 706 Version 5 CIP Standards
Status | Void
Comments | This project was added for the purpose of metrics. Not used for metrics due to excessive number of directives. No SAR Date. The earliest start date is not truly reflected on the project page; therefore the first meeting date of the team taken from the Releated files is used as the SAR date (9/22/2008).
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 62 | Enter # in column B and description here
No. of Guidances (see Note 2) | 22 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 10 | CIP-002, CIP-003, CIP-004, CIP-005, CIP-006, CIP-007, CIP-008, CIP-009, CIP-010, and CIP-011
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2008-09-22 | 2008-10-22 |  |  | -39713 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2012-10-26 | 2012-11-05 |  |  | -41208 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.
Formulas:
Projected or Actual End = +[Projected or Actual Start]+30

## _2008-12 (hidden)
Project | 2008-12 | [5 empty] | Home
Project Name | Coordinate Interchange Standards
Status | Metrics
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 1 | Enter # in column B and description here
No. of Guidances (see Note 2) | 7 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 5 | INT-004, INT-006, INT-009, INT-010, and INT-011
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2008-07-02 | 2008-07-31 |  |  | -39631 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2014-01-27 | 2014-02-05 |  |  | -41666 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2009-01 (hidden)
Project | 2009-01 | [5 empty] | Home
Project Name | Disturbance Sabotage Reporting
Status | Metrics-Pre 2013
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 9
No. of Guidances (see Note 2) | 4
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 2 | CIP-001 and EOP-004
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2009-04-22 | 2009-05-21 |  |  | -39925 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2012-10-24 | 2012-11-05 |  |  | -41206 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## 2009-02 (hidden)
Project | 2009-02 | [5 empty] | Home
Project Name | Real-time Reliability Monitoring and Analysis Capabilities
Status | Archived
Comments
Deliverable | New IRO-018-1 and TOP-010-1
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 3
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Mark Olson
PMOS Liaison | Jennifer Sterling
Affected Standards | 2 | New IRO-018-1 and TOP-010-1
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2015-07-16 | 2015-08-17 | 2015-04-01 | 2015-05-01 | -106 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2015-09-24 | 2015-11-09 | 2015-06-15 | 2015-07-30 | -101 |  | 47.38% & 48.00% | 8
CAB - Com/Add Ballot 2 | 2015-12-10 | 2016-01-26 | 2015-08-15 | 2015-09-29 | -117 |  | 72.13% & 68.01% | 9
CAB - Com/Add Ballot 3 |  |  | 2015-11-01 | 2015-12-16 | 0 | Not needed |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-02-17 | 2016-02-26 | 2016-01-01 | 2016-01-11 | -47 |  | 75.68% & 73.87% | 13
PTB - Present to BOT | 2016-05-04 | 2016-05-05 | 2016-02-10 | 2016-02-11 | -84 |  |  | 14
Filing - Filing with Regulators | 2016-05-26 | 2016-06-15 | 2016-06-01 | 2016-06-15 | 6 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Archive | 2016-06-14 | Moved to archives at PMOS meeting 6/14/2016.

## _2009-03 (hidden)
Project | 2009-03 | [5 empty] | Home
Project Name | Emergency Operations
Status | Metrics
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 9
No. of Guidances (see Note 2) | 4
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 4 | EOP-001, EOP-002, EOP-003, and EOP-011
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2009-12-07 | 2010-01-15 |  |  | -40154 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2014-10-28 | 2014-11-06 |  |  | -41940 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2009-06 (hidden)
Project | 2009-06 | [5 empty] | Home
Project Name | Facility Ratings
Status | Metrics-Pre 2013
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 2
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | FAC-008
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2009-01-20 | 2009-03-05 |  |  | -39833 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2011-05-12 | 2011-05-23 |  |  | -40675 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2009-08 (hidden)
Project | 2009-08 | [5 empty] | Home
Project Name | Nuclear Plant Interface Coordination
Status | Metrics-Pre 2009
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 7
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | NUC-001
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2009-02-02 | 2009-03-18 |  |  | -39846 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2009-07-10 | 2009-07-20 |  |  | -40004 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2009-10 (hidden)
Project | 2009-10 | [5 empty] | Home
Project Name | Interpretation − PRC-005-1, R1 − CMPWG
Status | Void
Comments | This project was added for the purpose of metrics. (Not used for metrics - Interpretation)
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 0
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | PRC-005
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2009-03-09 | 2009-04-07 |  |  | -39881 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2009-07-24 | 2009-08-06 |  |  | -40018 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2009-17 (hidden)
Project | 2009-17 | [5 empty] | Home
Project Name | Interpretation of PRC-004-1 and PRC-005-1 for Y-W Electric and Tri-State
Status | Void
Comments | This project was added for the purpose of metrics. (Not used for metrics due to Interpretation)
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 0
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 2 | PRC-004 and PRC-005
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2009-06-30 | 2009-07-31 |  |  | -39994 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2010-11-19 | 2010-12-03 |  |  | -40501 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2009-21 (hidden)
Project | 2009-21 | [5 empty] | Home
Project Name | Cyber Security Ninety-Day Response
Status | Void
Comments | This project was added for the purpose of metrics. Removed from analysis due to 90 special directive
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives
No. of Guidances (see Note 2)
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | CIP-006
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2009-10-13 | 2009-11-12 |  |  | -40099 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2009-12-03 | 2009-12-14 |  |  | -40150 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2010-01 (hidden)
Project | 2010-01 | [5 empty] | Home
Project Name | Training
Status | Metrics
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 4
No. of Guidances (see Note 2) | 3
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | PER-005
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2013-07-19 | 2013-09-03 |  |  | -41474 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2014-01-27 | 2014-02-05 |  |  | -41666 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2010-02 (hidden)
Project | 2010-02 | [5 empty] | Home
Project Name | Connecting New Facilities to the Grid
Status | Metrics
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 1
No. of Guidances (see Note 2) | 1
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 2 | FAC-001 and FAC-002
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2013-08-01 | 2013-09-16 |  |  | -41487 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2014-06-12 | 2014-06-23 |  |  | -41802 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2010-03 (hidden)
Project | 2010-03 | [5 empty] | Home
Project Name | Modeling Data (MOD B)
Status | Metrics
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 17
No. of Guidances (see Note 2) | 2
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 2 | MOD-032 and MOD-033
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2013-09-09 | 2013-10-09 |  |  | -41526 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2014-01-27 | 2014-02-05 |  |  | -41666 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.
Formulas:
Projected or Actual End = +[Projected or Actual Start]+30

## _2010-04 (hidden)
Project | 2010-04 | [5 empty] | Home
Project Name | Demand Data (MOD C)
Status | Metrics
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 10
No. of Guidances (see Note 2) | 4
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | MOD-031
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2013-07-22 | 2013-09-04 |  |  | -41477 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2014-04-25 | 2014-05-05 |  |  | -41754 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2010-04.1 (hidden)
Project | 2010-04.1 | [5 empty] | Home
Project Name | MOD-031 FERC Order No. 804 Directives
Status | Metrics
Comments | This project was added for the purpose of metrics. The baseline final ballot date was taken from the 2015 PTS.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 1 | Order No. 804
No. of Guidances (see Note 2) | 1 | Order No. 804
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | MOD-031
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2015-04-16 | 2015-05-19 |  |  | -42110 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2015-10-06 | 2015-10-15 |  | 2015-07-15 | -42283 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2010-05.1 (hidden)
Project | 2010-05.1 | [5 empty] | Home
Project Name | Protection System (Misoperations)
Status | Metrics
Comments | This project was added for the purpose of metrics. The baseline final ballot date was taken from the 2013 PTS.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 0
No. of Guidances (see Note 2) | 2
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | PRC-004
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2011-06-10 | 2011-07-11 |  |  | -40704 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2014-07-29 | 2014-08-07 |  | 2013-10-30 | -41849 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2010-05.2 (hidden)
Project | 2010-05.2 | [5 empty] | Home
Project Name | Phase 2 of Protection Systems
Status | Metrics
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 1
No. of Guidances (see Note 2) | 2
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 29 | See Implemention Plan for full list
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2014-02-18 | 2014-03-19 |  |  | -41688 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2014-10-28 | 2014-11-06 |  |  | -41940 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2010-05.3 (hidden)
Project | 2010-05.3 | [5 empty] | Home
Project Name | Phase 3 of Protection Systems: Remedial Action Schemes (RAS)
Status | Metrics
Comments | This project was added for the purpose of metrics. The baseline final ballot date was taken from the 2015 PTS.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 0
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 5 | PRC-012, PRC-013, PRC-014, PRC-015, and PRC-016
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2014-02-18 | 2014-03-19 |  |  | -41688 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-04-20 | 2016-04-29 |  | 2016-04-30 | -42480 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2010-07 (hidden)
Project | 2010-07 | [5 empty] | Home
Project Name | Generator Requirements at the Transmission Interface
Status | Metrics-Pre 2013
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 2
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 2 | FAC-003 and PRC-005
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2010-02-12 | 2010-03-15 |  |  | -40221 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2012-04-24 | 2012-05-03 |  |  | -41023 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2010-07.1 (hidden)
Project | 2010-07.1 | [5 empty] | Home
Project Name | Vegetation Management
Status | Metrics
Comments | This project was added for the purpose of metrics. The 2016 PTS was used to establish baseline final ballot date.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 2
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | FAC-003
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2015-08-24 | 2015-09-28 |  |  | -42240 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-01-29 | 2016-02-08 |  | 2016-04-08 | -42398 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2010-09 (hidden)
Project | 2010-09 | [5 empty] | Home
Project Name | Cyber Security Order 706B Nuclear Plant Implementation Plan
Status | Metrics-Pre 2013
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 2
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 8 | CIP-002, CIP-003, CIP-004, CIP-005, CIP-006, CIP-007, CIP-008, and CIP-009
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2009-07-20 | 2009-08-14 |  |  | -40014 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2010-06-22 | 2010-07-02 |  |  | -40351 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2010-10 (hidden)
Project | 2010-10 | [5 empty] | Home
Project Name | FAC Order 729
Status | Metrics-Pre 2013
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 5
No. of Guidances (see Note 2) | 3
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | FAC-013
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2010-03-15 | 2010-04-29 |  |  | -40252 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2011-01-14 | 2011-01-23 |  |  | -40557 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2010-11 (hidden)
Project | 2010-11 | [5 empty] | Home
Project Name | TPL Table 1 Order
Status | Metrics-Pre 2013
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 7
No. of Guidances (see Note 2) | 2
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 4 | TPL-001, TPL-002, TPL-003, and TPL-004
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2010-04-15 | 2010-05-26 |  |  | -40283 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2013-01-22 | 2013-01-31 |  |  | -41296 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2010-12 (hidden)
Project | 2010-12 | [5 empty] | Home
Project Name | Order 693 Directives
Status | Void
Comments | This project was added for the purpose of metrics. Removed due to special directive case
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 5
No. of Guidances (see Note 2) | 2
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 6 | BAL-002, EOP-002, FAC-002, MOD-021, PRC-004, and VAR-001
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2010-06-18 | 2010-07-13 |  |  | -40347 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2010-07-21 | 2010-07-31 |  |  | -40380 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2010-13.1 (hidden)
Project | 2010-13.1 | [5 empty] | Home
Project Name | Phase 1 of Relay Loadability: Transmission
Status | Metrics-Pre 2009
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 19
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2006-01-16 | 2006-02-15 |  |  | -38733 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2008-01-31 | 2008-02-09 |  |  | -39478 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2010-13.2 (hidden)
Project | 2010-13.2 | [5 empty] | Home
Project Name | Phase 2 Relay Loadability: Generation
Status | Metrics-Pre 2013
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 0
No. of Guidances (see Note 2) | 1
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | PRC-025
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2012-10-05 | 2012-11-05 |  |  | -41187 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2013-09-04 | 2013-09-13 |  |  | -41521 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2010-13.3 (hidden)
Project | 2010-13.3 | [5 empty] | Home
Project Name | Phase 3 of Relay Loadability: Stable Power Swings
Status | Metrics
Comments | This project was added for the purpose of metrics. The orignal Order No. 733 SAR was posted on 8/19/2010. This project started must later and was adjusted to the first meeting date of 2/27/2014.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 2
No. of Guidances (see Note 2) | 1
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | PRC-026
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2014-02-27 | 2014-03-29 |  |  | -41697 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2014-12-05 | 2014-12-16 |  |  | -41978 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.
Formulas:
Projected or Actual End = +[Projected or Actual Start]+30

## 2010-14.1 (hidden)
Project | 2010-14.1 | [5 empty] | Home
Project Name | Phase 1 of Balancing Authority Reliability-based Controls: Reserves
Status | Metrics
Comments | This project was added for the purpose of metrics. The 2016 PTS was used to establish baseline final ballot date.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 6
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | BAL-002
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2012-06-04 | 2012-07-03 |  |  | -41064 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2015-09-29 | 2015-10-08 |  | 2016-02-08 | -42276 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## 2010-14.2 (hidden)
Project | 2010-14.2 | [5 empty] | Home
Project Name | Periodic Review of BAL Standards
Status | Void
Comments | This project was added for the purpose of metrics. Not used for metrics b/c periodic review.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 0
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 2 | BAL-005 and BAL-006
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2014-02-21 | 2014-04-07 |  |  | -41691 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## 2010-14.2.1a (hidden)
Project | 2010-14.2.1a | [5 empty] | Home
Project Name | Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001
Status | Archived
Comments | Passed final ballot with 72% approval February 2016. Adopted by NERC BOT in February 2016. Filed with FERC in April 2016.
Deliverable | BAL-005
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | N/A |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 4
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Darrel Richardson
PMOS Liaison | Ken Goldsmith
Affected Standards | 1 | BAL-005
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2014-07-16 | 2014-08-14 | 2014-07-16 | 2014-08-15 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2015-07-30 | 2015-09-14 | 2015-11-20 | 2016-01-04 | 113 |  | 55.97% | 8
CAB - Com/Add Ballot 2 | 2015-11-10 | 2016-01-11 |  |  | -42318 |  | 70.64% | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-01-29 | 2016-02-08 | 2016-01-25 | 2016-02-04 | -4 |  | 72.06% | 13
PTB - Present to BOT | 2016-02-10 | 2016-02-12 | 2016-02-10 | 2016-02-12 | 0 |  |  | 14
Filing - Filing with Regulators | 2016-04-20 | 2016-05-20 | 2016-04-20 | 2016-05-20 | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Explain delay | 2016-05-01 | Going to final ballot end of January 2016 and planned for presentation at February 2016 Board meeting.

## 2010-14.2.1b (hidden)
Project | 2010-14.2.1b | [5 empty] | Home
Project Name | Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001
Status | Archived
Comments | Passed final ballot with 80% approval February 2016. Adopted by NERC BOT in February 2016. Filed with FERC in April 2016.
Deliverable | FAC-001
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | N/A |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | 11
Number of Directives | 7
No. of Guidances (see Note 2) | 1
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Darrel Richardson
PMOS Liaison | Ken Goldsmith
Affected Standards | 1 | FAC-001
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2014-07-16 | 2014-08-14 | 2014-07-16 | 2014-08-14 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2015-11-10 | 2016-01-11 | 2015-11-20 | 2016-01-04 | 10 |  | 75.54% | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-01-29 | 2016-02-08 | 2016-01-25 | 2016-02-04 | -4 |  | 80.15% | 13
PTB - Present to BOT | 2016-02-10 | 2016-02-12 | 2016-02-10 | 2016-02-12 | 0 |  |  | 14
Filing - Filing with Regulators | 2016-04-20 | 2016-05-20 | 2016-04-20 | 2016-05-20 | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes

## 2010-14.2.1c (hidden)
Project | 2010-14.2.1c | [5 empty] | Home
Project Name | Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001
Status | Archived
Comments | Passed final ballot with 94% approval February 2016. Adopted by NERC BOT in February 2016. Filed with FERC in April 2016.
Deliverable | BAL-006
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | N/A |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Darrel Richardson
PMOS Liaison | Ken Goldsmith
Affected Standards | 1 | BAL-006
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2014-07-16 | 2014-08-14 | 2014-07-16 | 2014-08-14 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2015-11-10 | 2016-01-11 | 2015-11-20 | 2016-01-04 | 10 |  | 94.3% | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-01-29 | 2016-02-08 | 2016-01-25 | 2016-02-04 | -4 |  | 94.61% | 13
PTB - Present to BOT | 2016-02-10 | 2016-02-12 | 2016-02-10 | 2016-02-12 | 0 |  |  | 14
Filing - Filing with Regulators | 2016-04-20 | 2016-05-20 | 2016-04-20 | 2016-05-20 | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Explain delay | 2016-05-01 | Going to final ballot end of January 2016 and planned for presentation at February 2016 Board meeting.

## 2010-14.2.2 (hidden)
Project | 2010-14.2.2 | [5 empty] | Home
Project Name | Phase 2 of Balancing Authority Reliability-based Controls - BAL-004-2
Status | Archived
Comments | Filed with regulators on November 10, 2016.
Deliverable | BAL-004
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | N/A |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 4
Directionally consistent with IERP findings (See Note 5) | 0 | N/A
Developer | Darrel Richardson
PMOS Liaison | Ken Goldsmith
Affected Standards | 1 | BAL-004
Last Updated | 2016-12-13
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2015-03-17 | 2015-04-15 | 2015-01-15 | 2015-02-14 | -61 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2015-08-12 | 2015-08-25 | 2015-04-01 | 2015-05-01 | -133 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2015-09-24 | 2015-11-12 | 2015-10-01 | 2015-11-15 | 7 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2015-12-08 | 2015-12-17 | 2015-12-01 | 2015-12-11 | -7 |  |  | 13
PTB - Present to BOT | 2016-02-10 | 2016-02-12 | 2016-05-01 | 2016-05-03 | 81 |  |  | 14
Filing - Filing with Regulators | 2016-11-10 | 2016-11-13 | 2016-06-01 | 2016-06-11 | -162 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Archive Projectg | 2016-12-13 | Directed to archive at December 13, 2016 PMOS Meeting.

## _2010-17 (hidden)
Project | 2010-17 | [5 empty] | Home
Project Name | Proposed Definition of Bulk Electric System
Status | Metrics-Pre 2013
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 7
No. of Guidances (see Note 2) | 2
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | BES Definition
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2010-12-17 | 2011-01-21 |  |  | -40529 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2013-11-08 | 2013-11-18 |  |  | -41586 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2011-INT-01 (hidden)
Project | 2011-INT-01 | [5 empty] | Home
Project Name | Revision of MOD-028-1 to address FPL Request for Interpretation
Status | Void
Comments | This project was added for the purpose of metrics. Removed from metrics b/c Interpretation
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 0
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | MOD-028
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2011-10-03 | 2011-11-16 |  |  | -40819 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2011-12-12 | 2011-12-22 |  |  | -40889 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2012-05 (hidden)
Project | 2012-05 | [5 empty] | Home
Project Name | ATC Revisions (MOD A)
Status | Metrics-Pre 2013
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives
No. of Guidances (see Note 2)
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 6 | MOD-001, MOD-004, MOD-008, MOD-028, MOD-29, and MOD-30
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2013-07-11 | 2013-08-27 |  |  | -41466 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2013-12-11 | 2013-12-20 |  |  | -41619 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2012-09 (hidden)
Project | 2012-09 | [5 empty] | Home
Project Name | IRO Review
Status | Void
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 0
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 8 | IRO-003, IRO-004, IRO-005, IRO-006, IRO-006-EAST, IRO-008, IRO-009, and IRO-010
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2013-08-07 | 2013-09-20 |  |  | -41493 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2012-13 (hidden)
Project | 2012-13 | [5 empty] | Home
Project Name | NUC - Nuclear Plant Interface Coordination
Status | Metrics
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 0
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | NUC-001
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2014-02-12 | 2014-03-13 |  |  | -41682 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2014-06-24 | 2014-07-03 |  |  | -41814 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2012-INT-02 (hidden)
Project | 2012-INT-02 | [5 empty] | Home
Project Name | Interpretation 2012-INT-02 TPL-003-0a and TPL-004-0 for SPCS
Status | Void
Comments | This project was added for the purpose of metrics. Removed from metrics b/c Interpretation
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 0
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 2 | TPL-003 and TPL-004
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2012-06-20 | 2012-07-19 |  |  | -41080 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2013-01-22 | 2013-01-31 |  |  | -41296 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2013-02 (hidden)
Project | 2013-02 | [5 empty] | Home
Project Name | Paragraph 81
Status | Void
Comments | This project was added for the purpose of metrics. Not used due to usual project.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 0
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 36 | Too many to list, see Implementation Plan
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2012-08-03 | 2012-09-04 |  |  | -41124 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2013-01-08 | 2013-01-17 |  |  | -41282 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## 2013-03 (hidden)
Project | 2013-03 | [5 empty] | Home
Project Name | Geomagnetic Disturbance Mitigation
Status | Archived
Comments | FERC issued Order No. 830 on September 22, 2016 approving TPL-007-1 and directing modifications. The SDT will develop revised or new requirements to enhance the benchmark GMD event used in GMD assessments, require collection of GMD data, and establish deadlines for GMD Corrective Action Plans and mitigation measures. Revisions must be filed by May 29, 2018. The SAR was accepted by the Standards Committee on March 15, 2017. The standard was adopted by the NERC Board at their November 2017 meeting and filed on January 22, 2018.
Deliverable | TPL-007-2
Deadline | 2018-05-29
Priority in RSDP, click to see applicable Footnote | Footnote 8, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 4
No. of Guidances (see Note 2) | 13 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Scott Barfield
PMOS Liaison | Jennifer Sterling
Affected Standards | 1 | TPL-007-1
Last Updated | 2018-01-29
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2016-10-20 | 2016-11-09 | 2016-10-20 | 2016-11-09 | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2016-12-16 | 2017-01-20 | 2016-12-20 | 2017-01-19 | 4 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2017-06-28 | 2017-08-11 | 2017-06-15 | 2017-07-30 | -13 |  | Passed | 8
CAB - Com/Add Ballot 2 |  |  | 2017-09-11 | 2017-10-26 | 0 |  | Changed from 9/11 to 9/22 to stagger 2013-03, 2015-09, and 2015-10. | 9
CAB - Com/Add Ballot 3 |  |  | 2017-11-29 | 2018-01-13 | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2017-10-20 | 2017-10-30 | 2018-02-20 | 2018-03-02 | 123 |  | Passed | 13
PTB - Present to BOT | 2017-11-07 | 2017-11-09 | 2018-05-01 | 2018-05-03 | 175 |  | Adopted | 14
Filing - Filing with Regulators | 2017-12-07 | 2017-12-10 | 2018-05-26 | 2018-05-29 | 170 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
No dates provided | 2016-06-01 | Project finished prior to 2015.
Accept Baseline Schedule | 2017-06-14 | Accepted by unamious consent.
Schedule Adjustment | 2017-08-10 | Changed from 9/11 to 9/22 to stagger 2013-03, 2015-09, and 2015-10.
Archive Project | 2018-01-31 | PMOS archived the project now that it is complete.

## _2013-04 (hidden)
Project | 2013-04 | [5 empty] | Home
Project Name | Voltage & Reactive Control
Status | Metrics
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 4
No. of Guidances (see Note 2) | 4
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 2 | VAR-001 and VAR-002
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2013-07-19 | 2013-09-03 |  |  | -41474 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2014-04-24 | 2014-05-05 |  |  | -41753 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2014-01 (hidden)
Project | 2014-01 | [5 empty] | Home
Project Name | Standards Applicability for Dispersed Generation Resources
Status | Metrics
Comments | This project was added for the purpose of metrics. The baseline final ballot date was taken from the 2014 PTS. The baseline was extended in 2015 to 4/15/2015
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 1
P81 Req (2013)
Number of Directives | 0
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 3 | PRC-004, PRC-005, and VAR-002
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2013-11-20 | 2013-12-19 |  |  | -41598 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2015-03-02 | 2015-03-11 |  | 2015-01-15 | -42065 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2014-02 (hidden)
Project | 2014-02 | [5 empty] | Home
Project Name | Critical Infrastructure Protection Standards Version 5 Revisions
Status | Metrics
Comments | This project was added for the purpose of metrics. The baseline final ballot date was taken from the 2014 PTS.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 13
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 10 | CIP-002, CIP-003, CIP-004, CIP-005, CIP-006, CIP-007, CIP-008, CIP-009, CIP-0010, and CIP-0011,
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2014-01-17 | 2014-02-28 |  |  | -41656 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2015-01-23 | 2015-02-02 |  | 2014-10-15 | -42027 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2014-03 (hidden)
Project | 2014-03 | [5 empty] | Home
Project Name | Revisions to TOP and IRO Standards
Status | Metrics
Comments | This project was added for the purpose of metrics. The baseline final ballot date was taken from the 2014 PTS.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 1
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 9 | IRO-001, IRO-002, IRO-008, IRO-010, IRO-014, IRO-017, TOP-001, TOP-002, and TOP-003
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2014-02-21 | 2014-03-24 |  |  | -41691 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2015-01-15 | 2015-01-21 |  | 2014-10-15 | -42019 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2014-04 (hidden)
Project | 2014-04 | [5 empty] | Home
Project Name | Physical Security
Status | Metrics
Comments | This project was added for the purpose of metrics. The baseline final ballot date was taken from the 2015 PTS.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 3
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 1 | CIP-014
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2014-03-21 | 2014-03-28 |  |  | -41719 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2015-04-20 | 2015-04-29 |  | 2015-06-30 | -42114 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2015-02 (hidden)
Project | 2015-02 | [5 empty] | Home
Project Name | Periodic Review of Emergency Operations
Status | Void
Comments | This project was added for the purpose of metrics. Guideline was recommended. Not used b/c periodic review.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 0
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 4 | EOP-004, EOP-005, EOP-006, and EOP-008
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2015-03-27 | 2015-05-11 |  |  | -42090 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## _2015-03 (hidden)
Project | 2015-03 | [5 empty] | Home
Project Name | Periodic Review of System Operating Limit Standards
Status | Void
Comments | This project was added for the purpose of metrics. Not used b/c periodic review.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 0
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 3 | FAC-010, FAC-011, and FAC-014
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2015-05-04 | 2015-06-17 |  |  | -42128 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## 2015-04 (hidden)
Project | 2015-04 | [5 empty] | Home
Project Name | Alignment of Terms
Status | Terminated
Comments | SDT is developing recommendations to present to SC. The Phase II work was completed in February 2016 and the proposed recommendations were submitted for consideration at the March 2016 meeting. The item was pulled from the SC agenda based on a request from the SC chair, Brian Murphy. The SDT reviewed the revisions proposed by the SC chair, and determined to move forward with submitting the recommendations as developed by the SDT. The Phase II recommendation document will be resubmitted for inclusion on the September 2016 SC agenda.
Deliverable | Report on process (Phase II Improvement Report)
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Low |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Lacey Ourso
PMOS Liaison | Andrew Gallo
Affected Standards | 1 | Glossary/ROP
Last Updated | 2016-10-04
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Archive | 2017-01-26 | By PMOS action
Terminated | 2019-01-08 | Status changed to Terminated for metric reporting.

## _2015-06 (hidden)
Project | 2015-06 | [5 empty] | Home
Project Name | Interconnection Reliability Operations and Coordination - IRO-006-East and IRO-009
Status | Metrics
Comments | This project was added for the purpose of metrics.
Deliverable
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013)
Number of Directives | 0
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5)
Developer
PMOS Liaison
Affected Standards | 2 | IRO-006-EAST and IRO-009
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2015-03-16 | 2015-04-15 |  |  | -42079 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2015-07-22 | 2015-07-31 |  |  | -42207 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Metrics Project | 2019-03-01 | This project was added for the purpose of metrics.

## 2015-07 (hidden)
Project | 2015-07 | [5 empty] | Home
Project Name | Internal Communications Capabilities
Status | Archived
Comments | Filing anticipated in late August.
Deliverable | COM-001-3
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | High |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 1
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Darrel Richardson
PMOS Liaison | Brenda Hampton
Affected Standards | 1 | COM-001-3
Last Updated | 2016-10-04
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT | 2015-06-11 | 2015-06-24 | 2015-06-01 | 2015-06-15 | -10 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2015-06-11 | 2015-07-11 | 2015-06-01 | 2015-07-01 | -10 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2015-09-25 | 2015-11-16 | 2015-07-15 | 2015-08-29 | -72 |  |  | 8
CAB - Com/Add Ballot 2 | 2016-03-23 | 2016-05-09 | 2015-10-01 | 2015-11-15 | -174 |  |  | 9
CAB - Com/Add Ballot 3 |  |  | 2016-01-01 | 2016-02-15 | 0 | Not needed |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-06-14 | 2016-06-24 | 2016-04-01 | 2016-04-11 | -74 |  | 83.25% | 13
PTB - Present to BOT | 2016-08-10 | 2016-08-12 | 2016-05-06 | 2016-05-08 | -96 |  |  | 14
Filing - Filing with Regulators | 2016-08-10 | 2016-08-12 | 2016-08-10 | 2016-08-12 | 0 |  |  | 15
PT - Post Approval Training | 2016-09-10 | 2016-10-10 | 2016-09-10 | 2016-10-10 | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Update to SC | 2016-06-15 | Update given to SC concerning delay.
Archived | 2016-12-01 | Project is complete.

## 2015-08a (hidden)
Project | 2015-08a | [5 empty] | Home
Project Name | Emergency Operations
Status | Archived
Comments | Presented to BOT February 2017, preparing the filing.
Deliverable | EOP-005, EOP-006, and EOP-008
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Medium |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 1
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Laura Anderson
PMOS Liaison | Ken Goldsmith
Affected Standards | 3 | EOP-005, EOP-006, and EOP-008
Last Updated | 2017-03-06
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review | 2016-06-14 | 2016-06-27 | 2016-01-11 | 2016-01-21 | -155 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2015-07-21 | 2015-08-19 | 2015-07-15 | 2015-08-14 | -6 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2016-06-29 | 2016-08-12 | 2016-01-25 | 2016-03-10 | -156 |  |  | 8
CAB - Com/Add Ballot 2 | 2016-10-26 | 2016-12-09 | 2016-04-04 | 2016-05-19 | -205 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-12-28 | 2017-01-06 | 2016-06-06 | 2016-06-16 | -205 |  | 83.65% (EOP-005) & 80.56% (EOP-006) | 13
PTB - Present to BOT | 2017-02-08 | 2017-02-10 | 2016-08-08 | 2016-08-10 | -184 |  |  | 14
Filing - Filing with Regulators | 2017-03-10 | 2017-03-15 | 2016-09-07 | 2016-09-12 | -184 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Explain delay | 2016-06-06 | The SDT slowed development.
Archived | 2017-03-15 | PMOS WECC Meeting

## 2015-08b (hidden)
Project | 2015-08b | [5 empty] | Home
Project Name | Emergency Operations
Status | Archived
Comments | Presented to BOT February 2017, preparing the filing.
Deliverable | EOP-004
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Medium |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 1
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Laura Anderson
PMOS Liaison | Ken Goldsmith
Affected Standards | 1 | EOP-004
Last Updated | 2017-03-06
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review | 2016-07-14 | 2016-07-28 | 2016-04-08 | 2016-04-18 | -97 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2015-07-21 | 2015-08-19 | 2015-07-15 | 2015-08-14 | -6 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2016-07-25 | 2016-09-08 | 2016-04-18 | 2016-06-02 | -98 |  |  | 8
CAB - Com/Add Ballot 2 | 2016-11-18 | 2017-01-06 | 2016-06-27 | 2016-08-11 | -144 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2017-01-24 | 2017-02-02 | 2016-08-22 | 2016-09-01 | -155 |  |  | 13
PTB - Present to BOT | 2017-02-08 | 2017-02-10 | 2016-10-31 | 2016-11-02 | -100 |  |  | 14
Filing - Filing with Regulators | 2017-03-10 | 2017-03-15 | 2016-11-30 | 2016-12-05 | -100 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Explain delay in project | 2016-05-01 | The delay was to reduce industry burden by simplifying the event reporting process such that a single form and submission system satisfies both EOP-004 and the U.S. Department of Energy’s reporting requirements, the Project 2015-08 EOP SDT is collaborating with the U.S. Department of Energy to harmonize reporting requirements/reports. This collaboration has changed the project schedule for EOP-004. The project’s PMOS representative, Ken Goldsmith, supports this project timeline change.
Archived | 2017-03-15 | PMOS WECC meeting.

## 2015-09 (hidden)
Project | 2015-09 | [5 empty] | Home
Project Name | Establish and Communicate System Operating Limits
Status | Archived
Comments | NERC Board adopted FAC-003-5, FAC-011-4, FAC‐014‐3, IRO‐008‐3, TOP‐001‐6, PRC-002-3, PRC-023-5, PRC-026 and the retirement of FAC-010 on May 13, 2021. NERC will file with FERC in late June.
Deliverable | CIP-014-3, FAC-003-5, FAC-011-4, FAC-013-3, PRC-002-3, PRC-023-5, PRC-026 and the retirement of FAC-010
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 11, Medium |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 1
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Latrice Harkness
PMOS Liaison | Ken Lanehome
Affected Standards | 7 | CIP-014-3, FAC-003-5, FAC-011, FAC-013-3, PRC-002-3, PRC-023-5, PRC-026-1 and the retirement of FAC-010
Last Updated | 2021-09-22
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  | 2016-04-04 | 2016-04-14 | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2015-08-20 | 2015-09-21 | 2015-08-20 | 2015-09-21 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2016-07-14 | 2016-08-12 | 2016-07-08 | 2016-08-07 | -6 |  |  | 6
CP2 - Comment Period 2 | [7 empty] | 7
CIB - Com/Ballot 1 (Initial) | 2017-09-29 | 2017-11-13 | 2017-09-22 | 2017-11-05 | -7 |  | Posting date changed see notes 8/10 and 8/25. | 8
CAB - Com/Add Ballot 2 | 2018-08-24 | 2018-10-17 | 2018-01-17 | 2018-03-02 | -219 |  |  | 9
CAB - Com/Add Ballot 3 | 2020-06-19 | 2020-08-03 | 2019-08-26 | 2019-10-10 | -298 | Other | 6/26/19 baseline starts here | 10
CAB - Com/Add Ballot 4 | 2020-10-23 | 2020-12-07 | 2019-12-18 | 2020-02-01 | -310 |  |  | 11
CAB - Com/Add Ballot 5 | 2021-02-19 | 2021-04-05 |  |  | -44246 |  |  | 12
FB - Final Ballot | 2021-04-19 | 2021-05-10 | 2020-02-11 | 2020-02-21 | -433 | Other |  | 13
PTB - Present to BOT | 2021-05-12 | 2021-05-13 | 2020-05-13 | 2020-05-15 | -364 |  |  | 14
Filing - Filing with Regulators | 2021-05-25 | 2021-05-25 | 2020-06-14 | 2020-06-17 | -345 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Explain delay | 2016-05-01 | The apparent delay in the project is due to missing an earlier update to the PMOS Annual Project Calendar. Baseline Schedule has not been adjusted.
Developer change | 2017-01-13 | Transition from Lacey Ourso to Darrel Richardson.
Developer change | 2017-04-01 | Added Al McMeekin to the project.
Added SDT schedule | 2017-07-20 | Updated initial, additional, final, BOT, and filing projected dates.
Schedule Adjustment | 2017-08-10 | Changed from 9/7 to 9/12 to stagger 2013-03, 2015-09, 2015-10, and 2016-02c.
Accept Baseline Realignment | 2017-08-10 | The project baseline was over a year behind (454 days as measured by the planned final ballot) in the original schedule due to developing additional information in support of the team's approach. The team also split off the IROL portion of the project. Whether this will be a 2015-09b, 2015-09.1, or a new project is yet to be determined.
Schedule Adjustment | 2017-08-25 | The SOL team needed additional time to complete reviews of whitepapers; therefore, adjusted their schedule from 9/12 as accepted by the PMOS on August 10 to 9/30. The change does not impact their December team meeting plans.
Informal definition posting | 2017-09-29 | The informal posting of the definitions is not reflected in the above dates grid.
Developer change | 2018-03-01 | Al McMeeking and Darrel Richardson were replaced by Katherin Street.
Developer change | 2018-04-25 | Katherin Street was replaced by Darrel Richardson.
Updated Proposed Schedule | 2018-06-21 | Project going to 3rd ballot week of 7/16/2018, adjusted final ballot, BOT, and filing accordingly.
Standards added | 2018-07-10 | Added CIP-014-3 FAC-003-5, FAC-013-3, PRC-023-5, and PRC-026-2 to affected and deliverable standards.
Developer change | 2018-10-30 | Latrice Harkness will be assuming the developer role from Darrel as he is working in a different area now.
Schedule Correction | 2018-12-07 | A 3rd ballot was shown as unplanned, however, it should have been updated to the 2nd ballot. The planned/projected schedule for the 2nd ballot was updated.
SC Action | 2019-03-20 | The SC determined that is was within the scope of the SAR to open TOP-001 and IRO-008.
Accept Baseline Realignment | 2019-06-26 | Accepted at the June 26 PMOS Meeting (2nd re-baseline)
Meeting with FERC | 2019-09-24 | The baseline posting for August 2019 was postponed to meet with FERC in September resulting in a delay.
NERC Standards | 2020-04-22 | The SC requested that we consider the Covid-19, the project was slowed down and a complexity factor was added.
PMOS Liaison Update | 2020-05-06 | There is a delay in the vote based on some issues.
Standards Developer | 2020-08-31 | The ballot was extended due to non-binding polls not reaching quorum

## 2015-09b (hidden)
Project | 2015-09b | [5 empty] | Home
Project Name | Establish and Communicate System Operating Limits
Status | Archived
Comments | This project will not re-open for phase 2. Therefore, this project is closed.
Deliverable | IROL Stds.
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 11, Medium |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 1
No. of Guidances (see Note 2) | 1
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Latrice Harkness
PMOS Liaison | Ken Lanehome (primary), Rebecca Darrah (secondary)
Affected Standards | 0 | N/A
Last Updated | 2021-07-23
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Bifurcate Project | 2017-03-31 | Split the IRO portion into this section for tracking.
Worksheet created | 2017-08-10 | PMOS suggested visibility on this IROL portion.
Worksheet made visible | 2018-04-25 | PMOS requested that the IRO portion be tracked going forward.
PMOS update | 2020-12-08 | Need a backup PMOS liaison

## 2015-10 (hidden)
Project | 2015-10 | [5 empty] | Home
Project Name | Single Points of Failure TPL-001
Status | Archived
Comments | The standard was approved by industry with a 66.67% vote and adopted by the NERC Board of Trustees at its November 2018 meeting. The standard was filed with regulatory authorities on December 7, 2018.
Deliverable | TPL-001-5
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 8, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 2 | 2 directives at P40 & P89 (Click this link for FERC Order)
No. of Guidances (see Note 2) | 0
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Latrice Harkness
PMOS Liaison | Mark Pratt
Affected Standards | 1 | TPL-001-4
Last Updated | 2019-01-23
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2015-11-12 | 2015-12-01 | 2016-01-18 | 2016-02-01 | 67 |  |  | 1
Nominations - DT | 2016-07-22 | 2016-08-05 | 2016-07-25 | 2016-08-08 | 3 |  |  | 2
QR - Quality Review |  |  | 2016-05-30 | 2016-06-09 | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2015-11-12 | 2015-12-17 | 2015-11-12 | 2015-12-17 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 | 2016-05-26 | 2016-06-24 | 2016-06-15 | 2016-07-15 | 20 | Expanded Scope |  | 5
CP1 - Comment Period 1 | 2017-04-25 | 2017-05-24 | 2017-04-25 | 2017-05-24 | 0 | Other | Team added informal comment period | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2017-09-08 | 2017-10-23 | 2017-07-05 | 2017-08-18 | -65 |  | Held at 9/7 to stagger 2013-03 and 2015-09. | 8
CAB - Com/Add Ballot 2 | 2018-02-23 | 2018-04-23 | 2017-10-18 | 2017-12-01 | -128 |  | Period extended from 4/9 to 4/23 due to changes | 9
CAB - Com/Add Ballot 3 | 2018-07-30 | 2018-09-14 |  |  |  |  | Additional period | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2018-10-11 | 2018-10-22 | 2018-01-08 | 2018-01-17 | -276 |  |  | 13
PTB - Present to BOT | 2018-11-06 | 2018-11-08 | 2018-02-01 | 2018-02-03 | -278 |  |  | 14
Filing - Filing with Regulators | 2018-12-06 | 2018-12-09 | 2018-03-01 | 2018-03-04 | -280 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Expansion of Scope | 2016-06-14 | FERC directives added (P40 & P89) additional scoping in addition to industry comments following the second SAR posting. The MOD references are being updated due to some retiring in July 2016.
Developer change | 2017-01-13 | Transition from Lacey Ourso to Soo Jin Kim until a new developer is assigned.
Accept Schedule | 2017-04-27 | Accepted by PMOS.
Schedule deviation | 2017-06-13 | Baseline initial ballot of 7/5/2017 moved to 9/7/2017 due addressing comments and scope of SAR. Schedule accounts for SC not meeting in August.
Schedule Adjustment | 2017-08-10 | No adjustment required 2013-03, 2015-09, and 2016-02 were staggered to spread postings out.
Schedule Adjustment | 2018-09-13 | PMOS agreed to re-baseline if project did not go to final ballot following the September 2018 posting.
Schedule Adjustment | 2018-10-31 | No re-baselining required since standard passed and will go to the NERC Board in November 2018.
Archive | 2018-12-12 | The PMOS archived the project as it was filed on December 7, 2018.

## 2015-INT-01 (hidden)
Project | 2015-INT-01 | [5 empty] | Home
Project Name | Interpretation of CIP-002-5.1 for Energy Sector Security Consortium (EnergySec)
Status | Archived-Not for Metrics
Comments | Interpretation passed. FERC Approved, RD docket. (Interpretation - not used for metrics analysis)
Deliverable | Interpretation CIP-002-5.1
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Low |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Al McMeekin
PMOS Liaison | Brian Murphy and Andrew Gallo
Affected Standards | 1 | CIP-002-5.1
Last Updated | 2017-02-09
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  | 2016-04-15 | 2016-04-29 | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2016-07-27 | 2016-08-06 |  |  | -42578 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2016-07-27 | 2016-09-12 | 2016-07-25 | 2016-09-08 | -2 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-10-13 | 2016-10-24 | 2016-10-04 | 2016-10-14 | -9 |  | 91.31% | 13
PTB - Present to BOT | 2016-11-15 | 2016-11-17 | 2016-11-15 | 2016-11-17 | 0 |  |  | 14
Filing - Filing with Regulators | 2016-11-28 | 2016-11-28 | 2016-12-28 | 2016-12-31 | 30 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Transfer RFI to the CIP SDT and update the SC | 2016-06-14 | Schedule updated to CIP SDT timeline.
Add CIP Schedule for approval | 2016-07-20 | Update SC that schedule was approved by SDT, SDT leadership, developer, and PMOS Liaison.
Archive Project | 2017-01-18 | Standard was filed on 11/28/2016 and may come off active monitoring by PMOS

## 2015-INT-02 (hidden)
Project | 2015-INT-02 | [5 empty] | Home
Project Name | Interpretation of CIP-007-5 for Foxguard Solutions
Status | Terminated
Comments | Currently on hold. SC approved RFI and for the interpretation drafting team to be formed in April 2016.
Deliverable | CIP-007-5
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | N/A |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives |  | N/A
No. of Guidances (see Note 2) |  | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Lacey Ourso
PMOS Liaison | Brian Murphy
Affected Standards |  | CIP-007-5
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  | 2016-05-15 | 2016-06-14 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  | 2016-09-15 | 2016-10-30 | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Archive | 2016-07-13 | PMOS agreed to archive. Project was eliminated.

## 2015-INT-03 (hidden)
Project | 2015-INT-03 | [5 empty] | Home
Project Name | Interpretation of TOP-002-2.1b for FMPP
Status | Terminated
Comments | Currently on hold. Interpretation drafting team recommendations were submitted to the SC in February 2016.
Deliverable | TOP-002-2.1b
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Low |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Lacey Ourso
PMOS Liaison | Brian Murphy
Affected Standards | 1 | TOP-002-2.1b
Last Updated
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT | 2015-12-15 | 2016-01-05 | 2015-12-15 | 2016-01-05 | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  | 2016-04-15 | 2016-05-30 | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  | 2016-08-10 | 2016-08-12 | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Last Status | 2016-02-01 | IDT nominees to be presented at February 2016 SC meeting.

## 2016-EPR-01 (hidden)
Project | 2016-EPR-01 | [5 empty] | Home
Project Name | Enhanced Periodic Review of Personnel Performance, Training, and Qualifications Standards
Status | Archived
Comments | The team will be requesting the Standards Committee at the June 14, 2017 meeting to accept a SAR to revise a Standard and to activate Project 2017-02.
Deliverable | PER-003-1 and PER-004-2
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Medium
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Darrel Richardson
PMOS Liaison | Mike Brytowski
Affected Standards | PER-003-1 and PER-004-2, but PER-001-0.2 was not evaluated due to retirement on April 17, 2017.
Last Updated | 2017-06-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2016-02-10 | 2016-02-23 | 2016-02-10 | 2016-02-23 | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2017-01-10 | 2017-02-23 | 2017-01-23 | 2017-03-08 | 13 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
PMOS request | 2017-12-13 | List only the EPR nomination period and recommendation posting dates.
Archive Project | 2017-06-14 | Project 2017-02 initiated to address the EPR recommendation(s).

## 2016-EPR-02 (hidden)
Project | 2016-EPR-02 | [5 empty] | Home
Project Name | Enhanced Periodic Review of Voltage and Reactive Standards
Status | Archived
Comments | The periodic review team (PRT) responded to industry comments that affirm the PRT's recommendations. The PRT maintained its initial recommendation that the standards are sufficient to protect reliablity and although some things could be cleaned up, the recommendation is to not open the standards for revisions (i.e., yellow rating). The PRT will present their recommendations for acceptance to the Standards Committee on June 14, 2017 and to re-affirm the two VAR standards.
Deliverable | VAR-001-4.1 & VAR-002-4
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Medium
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Scott Barfield-McGinnis
PMOS Liaison | Amy Casuscelli
Affected Standards | VAR-001-4.1 & VAR-002-4
Last Updated | 2017-06-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2016-02-10 | 2016-02-23 | 2016-02-10 | 2016-02-23 | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2017-02-28 | 2017-04-13 | 2017-01-31 | 2017-03-17 | -28 | Other |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
PMOS request | 2017-12-13 | List only the EPR nomination period and recommendation posting dates.
Delay - Other | 2017-02-08 | Team cleaned up templates via conference calls after in-person meeting adding two weeks, plus the Standards Committee's Standing Review Team asked for a minimum of two weeks to review.
Archive Project | 2017-06-14 | Recommendations accepted by the SC and the standards were re-affirmed.

## 2016-01 (hidden)
Project | 2016-01 | [5 empty] | Home
Project Name | Modifications to TOP and IRO Standards
Status | Archived
Comments | Preparing for final ballot in Dec 2016. NOPR issued June 18, 2015 (under previous project 2014-03). Final Rule issued November 19, 2015 with three directives with an associated 18 month regulatory filing deadline. The SC authorized posting at the June 2016 SC meeting. Standards passed additional ballot ending October 17 2016 and will be posted for final ballot early December 2016.
Deliverable | TOP/IRO Standards
Deadline | FERC deadline of July 27, 2017
Priority in RSDP, click to see applicable Footnote | High |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Mark Olson
PMOS Liaison | Rod Kinard
Affected Standards | 2 | TOP-001 and IRO-002
Last Updated | 2016-12-13
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT | 2016-01-22 | 2016-02-04 | 2016-04-18 | 2016-05-02 | 87 |  |  | 2
QR - Quality Review | 2016-05-10 | 2016-05-23 | 2016-06-27 | 2016-07-07 | 48 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2016-01-22 | 2016-02-22 | 2016-03-07 | 2016-04-06 | 45 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2016-06-20 | 2016-08-03 | 2016-07-11 | 2016-08-25 | 21 |  | IRO-002-5 (67.25%) TOP-001-4 (64.59%) | 8
CAB - Com/Add Ballot 2 | 2016-08-31 | 2016-10-17 | 2016-10-24 | 2016-12-08 | 54 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-12-02 | 2016-12-12 | 2017-01-17 | 2017-01-27 | 46 |  |  | 13
PTB - Present to BOT | 2017-02-07 | 2017-02-09 | 2017-02-07 | 2017-02-09 | 0 |  |  | 14
Filing - Filing with Regulators | 2017-03-09 | 2017-03-12 | 2017-03-09 | 2017-03-12 | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Periodic Update | 2016-08-21 | Developer updated FERC deadline from 5/19/17 to 7/27/17
Archive Projectg | 2016-12-13 | Directed to archive at December 13, 2016 PMOS Meeting.

## 2016-02a (hidden)
Project | 2016-02a | [5 empty] | Home
Project Name | Modifications to CIP Standards
Status | Archived
Comments | Petition was filed on March 3, 2017 requesting approval. TD at Lows resulted in a balloted CIP-003-7(i), which was not captured in the dates. "(i)" was dropped in the BOT presentation and filing and the standard was filed as CIP-003-7
Deliverable | LERC Definition & CIP-003-7
Deadline | Directive: March 31, 2017 (LERC only) (March 31 in SAR)
Priority in RSDP, click to see applicable Footnote | High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 1
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Al McMeekin
PMOS Liaison | Ken Lanehome and Ash Mayfield
Affected Standards | 1 | CIP-003-7
Last Updated | 2017-04-11
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT | 2016-03-10 | 2016-03-24 | 2016-03-10 | 2016-03-24 | 0 |  |  | 2
QR - Quality Review | 2016-06-30 | 2016-07-06 | 2016-06-30 | 2016-07-07 | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2016-03-23 | 2016-04-21 | 2016-03-23 | 2016-04-21 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 | 2016-06-01 | 2016-06-30 | 2016-06-01 | 2016-07-01 | 0 | Expanded Scope |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2016-07-21 | 2016-09-06 | 2016-07-25 | 2016-09-08 | 4 |  |  | 8
CAB - Com/Add Ballot 2 | 2016-10-21 | 2016-12-05 | 2016-10-17 | 2016-12-01 | -4 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-12-09 | 2016-12-19 | 2017-01-05 | 2017-01-15 | 27 |  | 87.95% | 13
PTB - Present to BOT | 2017-02-08 | 2017-02-10 | 2017-02-08 | 2017-02-10 | 0 |  |  | 14
Filing - Filing with Regulators | 2017-03-03 | 2017-03-06 | 2017-03-28 | 2017-03-31 | 25 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Archived comments | 2016-06-10 | Order 822 was issued on January 21, 2016. The SC authorized posting the SAR and to request nominations for additional team members at March 9, 2016 meeting. The SAR posting ended April 21, 2016 and the SDT is reviewing the comments received. A CIP Technical Conference was held on April 19, 2016 in Atlanta. Seven additional members were appointed to the SDT at the April 20, 2016 SC meeting. Initial SDT meeting May 24-26, 2016 in Atlanta.
Added CIP Schedule for approval | 2016-07-20 | Update SC that schedule was approved by SDT, SDT leadership, developer, and PMOS Liaison. Second SAR posting was required due to expansion of scope.
Liaison Change | 2017-03-15 | Updated B. Murpy and A. Gallow to K. Lanehome and A. Mayfield
Archived | 2017-04-01 | Project was filed with regulators.

## 2016-02b (hidden)
Project | 2016-02b | [5 empty] | Home
Project Name | Modifications to CIP Standards
Status | Archived
Comments | CIP-012-1 was approved by industry and the NERC Board adopted the standard at its August 2018 meeting and filed with regulatory authorities on September 18, 2018.
Deliverable | Directives, Control Center Comm Nets (CIP-012-1)/ Control Center definition
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 8, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 2
No. of Guidances (see Note 2) |  | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Jordan Mallory
PMOS Liaison | Ken Lanehome, Ash Mayfield, and Kirk Rosener
Affected Standards | 1 | CIP-012-1
Last Updated | 2018-09-24
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review | 2016-10-20 | 2016-10-30 | 2016-10-20 | 2016-10-30 | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2016-03-23 | 2016-04-21 |  |  | -42452 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2017-02-10 | 2017-03-13 | [5 empty] | 6
CP2 - Comment Period 2 | 2017-08-14 | 2017-09-12 | 2016-12-02 | 2017-01-16 | -255 |  | Informal for definition | 7
CIB - Com/Ballot 1 (Initial) | 2017-07-27 | 2017-09-11 | 2017-03-31 | 2017-05-15 | -118 |  |  | 8
CAB - Com/Add Ballot 2 | 2017-10-27 | 2017-12-11 | 2017-08-15 | 2017-09-29 | -73 |  | Does not include the informal 21 day comment on Implementation Guidance ending on 12/11/2017 | 9
CAB - Com/Add Ballot 3 | 2018-03-16 | 2018-04-30 | [5 empty] | 10
CAB - Com/Add Ballot 4 | 2018-05-18 | 2018-07-02 | [5 empty] | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2018-08-02 | 2018-08-09 | 2017-10-17 | 2017-10-27 | -289 |  |  | 13
PTB - Present to BOT | 2018-11-06 | 2018-11-08 | 2017-11-07 | 2017-11-09 | -364 |  |  | 14
Filing - Filing with Regulators | 2018-12-01 | 2018-12-04 | 2017-12-28 | 2017-12-31 | -338 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Archived comments | 2016-06-10 | Order 822 was issued on January 21, 2016. The SC authorized posting the SAR and to request nominations for additional team members at March 9, 2016 meeting. The SAR posting ended April 21, 2016 and the SDT is reviewing the comments received. A CIP Technical Conference was held on April 19, 2016 in Atlanta. Seven additional members were appointed to the SDT at the April 20, 2016 SC meeting. Initial SDT meeting May 24-26, 2016 in Atlanta.
Added CIP Schedule for approval | 2016-07-20 | Update SC that schedule was approved by SDT, SDT leadership, developer, and PMOS Liaison.
Liaison Change | 2017-03-15 | Updated B. Murpy and A. Gallow to K. Lanehome and A. Mayfield
Developer Change | 2017-04-01 | Replaced Al McMeekin with Mat Bunch and Katherine Street.
Change in Approach | 2017-06-27 | Team decided to create CIP-012-1 and not modiifying CIP-006 for Communcation Networks.
Developer Change | 2018-02-14 | Replaced Katherine Street with Jordan Mallory
Developer Change | 2018-06-13 | Mat Bunch was removed from the project.
Archive Project | 2018-10-18 | Project archived per instructions at the September 13, 2018 PMOS meeting.
Formulas:
Projected or Actual End = [Projected or Actual Start]+10
Projected or Actual End = +[Projected or Actual Start]+3
Baseline End = [Baseline Start]+10
Baseline End = +[Baseline Start]+3

## 2016-02c (hidden)
Project | 2016-02c | [5 empty] | Home
Project Name | Modifications to CIP Standards
Status | Archived
Comments | The standard posted for final ballot passed with a 96.28 %. The NERC Board adopted the standard during its May 2020 Board meeting.
Deliverable | CIP-002-6 - Address TO Control Centers Performing Transmission Operator (TOP) Obligations.
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 8, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 1
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Jordan Mallory
PMOS Liaison | Ken Lanehome (primary), Kirk Rosener (secondary) and Ash Mayfield (tertiary)
Affected Standards | 11 | CIP-002-5.1, CIP-003-6, CIP-004-6, CIP-005-5, CIP-006-6, CIP-007-6, CIP-008-5, CIP-009-6, CIP-010-2, CIP-011-2, CIP-012-1
Last Updated | 2020-06-22
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review | 2016-10-20 | 2016-10-30 | 2016-10-20 | 2016-10-30 | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2016-03-23 | 2016-04-21 | [5 empty] | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2017-03-14 | 2017-04-11 |  |  |  |  | Added to schedule, reduced period - SDT needed feedback | 6
CP2 - Comment Period 2 | 2018-06-14 | 2018-07-13 |  |  |  |  | IROL for CIP-002 | 7
CIB - Com/Ballot 1 (Initial) | 2017-09-14 | 2017-10-30 | 2016-12-02 | 2017-01-15 | -286 |  | See notes for 8/10 and 8/25. | 8
CAB - Com/Add Ballot 2 | 2018-03-16 | 2018-04-30 | 2017-03-31 | 2017-05-14 | -350 |  |  | 9
CAB - Com/Add Ballot 3 | 2018-08-23 | 2018-10-09 | 2017-08-15 | 2017-09-28 | -373 |  | Going back to initial ballot | 10
CAB - Com/Add Ballot 4 | 2019-11-01 | 2019-12-16 |  |  |  |  | Ballot Pools re-opened | 11
CAB - Com/Add Ballot 5 | 2019-12-06 | 2019-12-16 | [5 empty] | 12
FB - Final Ballot | 2020-03-26 | 2020-04-05 | 2017-10-17 | 2017-10-27 | -891 |  |  | 13
PTB - Present to BOT | 2020-05-13 | 2020-05-14 | 2017-11-07 | 2017-11-09 | -918 |  |  | 14
Filing - Filing with Regulators | 2020-06-12 | 2020-06-15 | 2017-12-28 | 2017-12-31 | -897 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Archived comments | 2016-06-10 | Order 822 was issued on January 21, 2016. The SC authorized posting the SAR and to request nominations for additional team members at March 9, 2016 meeting. The SAR posting ended April 21, 2016 and the SDT is reviewing the comments received. A CIP Technical Conference was held on April 19, 2016 in Atlanta. Seven additional members were appointed to the SDT at the April 20, 2016 SC meeting. Initial SDT meeting May 24-26, 2016 in Atlanta.
Added CIP Schedule for approval | 2016-07-20 | Update SC that schedule was approved by SDT, SDT leadership, developer, and PMOS Liaison.
Liaison Change | 2017-03-15 | Updated B. Murpy and A. Gallow to K. Lanehome and A. Mayfield
Developer Change | 2017-04-01 | Replaced Al McMeekin with Mat Bunch and Katherine Street.
Schedule Adjustment | 2017-08-10 | The original 5/15/2017 planned posting was accepted for 9/18 to stagger 2013-03, 2015-09, and 2015-10.
Schedule Adjustment | 2017-08-25 | The posting was advanced due to 2015-09 (SOL) being moved from its 9/12 posting to 9/30.
Developer Change | 2018-02-14 | Replaced Katherine Street with Jordan Mallory
SC Action | 2018-06-13 | The SC accepted the SAR to address recommended revisions to CIP-002 provided by Project 2015-09 Establish and Communicate System Operating Limits (FAC SOL) SDT; authorize the Project 2016-02 SDT to revise the CIP Reliability Standards based on the modifications provided by the FAC SOL SDT; and authorize posting of the SAR for a 30-day informal comment period.
Developer Change | 2018-06-13 | Mat Bunch was removed from the project leaving Jordan Mallory.
Schedule Adjustment | 2020-03-18 | Final Ballot delayed to April 2020.
Filed with FERC | 2020-06-12 | Filed it with FERC on Friday, June 12, 2020.
Archive Project | 2020-06-22 | PMOS Archived the project following the filing.

## 2016-02d
Project | 2016-02d | [5 empty] | Home
Project Name | Modifications to CIP Standards
Status | Posted
Comments | The draft version 5 of the project successfully completed its industry comment and ballot period on November 29, 2023, with the ballot passing. Final ballot from April 3 - 12.
Deliverable
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 11, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 1 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Alison Oswald
PMOS Liaison | Ruida Shu (primary), Kirk Rosener (secondary)
Affected Standards | 5 | CIP-004, CIP-005, CIP-006, CIP-007 and CIP-010
Last Updated | 2024-04-10
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Pandemic | 90 | 1
AS2 - Additional SAR 2 | 2019-02-28 | 2019-03-29 |  |  |  | Pandemic | 90 | 2
QR - Quality Review | [5 empty] | Change in Developer | 30 | 3
SP1 - SAR/PR/WP Posting 1 | 2019-05-30 | 2019-06-28 | 2019-05-30 | 2019-06-28 | 0 | Change in Developer | 30 | 4
SP2 - SAR Revise/Response |  |  | 2019-08-27 | 2019-10-26 |  | N/A |  | 5
SDT - Dev Time |  |  | 2019-12-25 | 2020-11-19 | 0 | Intentional Hold/Delay | 30 | 5
CP1 - Comment Period 1 | 2019-08-09 | 2019-09-26 |  |  |  | Intentional Hold/Delay | 30 | 6
CP2 - Comment Period 2 | 2019-11-01 | 2019-12-01 |  |  |  | Intentional Hold/Delay | 30 | 7
CIB - Com/Ballot 1 (Initial) | 2021-01-21 | 2021-03-22 | 2020-11-19 | 2021-01-03 | -63 | Intentional Hold/Delay | 30 | 8
CAB - Com/Add Ballot 2 | 2021-06-30 | 2021-08-20 | 2021-03-04 | 2021-04-18 | -118 | Intentional Hold/Delay | 30 | 9
CAB - Com/Add Ballot 3 | 2022-01-24 | 2022-03-10 |  |  |  | Intentional Hold/Delay | 30 | 10
CAB - Com/Add Ballot 4 | 2022-08-10 | 2022-09-26 |  |  |  | N/A | 0 | 11
CAB - Com/Add Ballot 5 | 2023-10-04 | 2023-11-17 |  |  |  | N/A | 0 | 12
FB - Final Ballot | 2024-04-03 | 2024-04-12 | 2021-05-18 | 2021-05-28 | -1051 | N/A | 0 | 13
PTB - Present to BOT | 2024-05-09 | 2024-05-09 |  |  |  | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
[6 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | -630 | Calculated CF Date: | 2022-07-22
PTS Change Control
Reason for Update | Date | Notes
Segmented project | 2017-08-08 | This fourth segment of the project was made to address all remaining V5TAG issues: Cyber Asset and BES CA (BCA) definitions, Network and Externally Accessible Devices (ESP, ERC, IRA), Obligations, Virtualization, and CIP Exceptional Circumstances.
Assign PMOS Liaison | 2017-10-12 | Assigned Kirk Rosener to support Ken Lanehome and Ash Mayfield.
Developer Change | 2018-02-14 | Replaced Katherine Street with Jordan Mallory
Developer Change | 2018-06-13 | Mat Bunch was removed from the project.
Accept baseline schedule | 2018-09-13 | PMOS accepted the baseline following appointment of additional members in July 2018.
Delay | 2018-09-01 | Project delayed from August 2018 to January 2019 (tentatively) for 2018-02, CIP-008 to finish.
SDT Augmented | 2019-05-22 | The SC accepted the recommended slate of candidates.
Re-baseline | 2019-06-26 | PMOS accepted the baseline for virtualization now that other focus areas are complete.
NERC Standards | 2020-04-22 | The SC requested that we consider the Covid-19, the project was slowed down and a complexity factor was added.
PMOS Liaison/NERC Staff | 2020-05-06 | Posting is dependent on the Supply Chain (FERC directive and deadline (Dec. 2020) and BCSI management posting times. This will delay the baseline listed above.
PMOS Liaison | 2020-06-16 | The Critical Path is the Supply Chain Project, add a complexity factor (project codepency with another project).
PMOS Liaison | 2020-08-05 | Intentional delay for the Sept 2020 posting. The CIP SDT is waiting on the Supply Chain (2019-03) project to complete before seeking acceptance of posting from the SC.
Formulas:
Calculated Start = [Calculated End, row above]+60
Calculated Start = +[Calculated End, row above]+60
Calculated End = [Calculated Start]+60
Calculated End = +[Calculated Start]+(B9*30)+(B14*60)
Projected or Actual End = +[Projected or Actual Start]+30
Time Impact = D22+(E32-D22)+SUM(H19:[Time Impact, row above])
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2016-02e (hidden)
Project | 2016-02e | [5 empty] | Home
Project Name | Modifications to CIP Standards
Status | Archived
Comments | CIP-003 passed Final Ballot on April 29 at 91.44%. The standard was adopted by the NERC Board of Trustees in May 2019 and was filed on May 21, 2019.
Deliverable | CIP-003-8 (FERC Order No. 843 Malicious Code Example Directive)
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 8, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Jordan Mallory
PMOS Liaison | Ken Lanehome, Ash Mayfield, and Kirk Rosener
Affected Standards | 1 | CIP-003-7
Last Updated | 2019-06-26
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2016-03-23 | 2016-04-21 |  |  | -42452 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2018-08-23 | 2018-10-09 | 2018-08-23 | 2018-10-07 | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  | 2018-11-22 | 2019-01-06 | 0 |  | Passed on initial, not needed | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2019-04-18 | 2019-04-29 | 2019-01-25 | 2019-02-04 | -83 |  |  | 13
PTB - Present to BOT | 2019-05-06 | 2019-05-08 | 2019-02-06 | 2019-02-08 | -89 |  |  | 14
Filing - Filing with Regulators | 2019-05-21 | 2019-05-23 | 2019-03-06 | 2019-03-08 | -76 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Segmented project | 2018-07-30 | CIP-003 for malicous code was segmented into its own tracking worksheet.
Accept Baseline | 2018-10-31 | PMOS accepted the baseline provided by the SDT.
Archive | 2019-06-26 | The PMOS archived the project as it was filed on May 21, 2019.
Formulas:
Baseline End = +[Baseline Start]+45

## 2016-03 (hidden)
Project | 2016-03 | [5 empty] | Home
Project Name | Cyber Security Supply Chain Management
Status | Archived
Comments | The petition was filed on September 26, 2017.
Deliverable | New and revised Standard(s)
Deadline | 2017-09-27
Priority in RSDP, click to see applicable Footnote | Footnote 8, High |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 1
No. of Guidances (see Note 2) |  | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Mark Olson
PMOS Liaison | Brenda Hampton
Affected Standards | 3 | CIP-005-6, CIP-010-3, and CIP-013-1
Last Updated | 2017-10-03
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT | 2016-07-29 | 2016-08-18 | 2016-07-29 | 2016-08-18 | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2016-10-20 | 2016-11-18 | 2016-10-20 | 2016-11-21 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2017-01-19 | 2017-03-06 | 2017-01-19 | 2017-03-06 | 0 |  |  | 8
CAB - Com/Add Ballot 2 | 2017-05-02 | 2017-06-15 | 2017-04-12 | 2017-05-26 | -20 |  | CIP-005-6 89.84% CIP-010-3 82.92% CIP-013-1 88.64% | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2017-07-11 | 2017-07-20 | 2017-06-21 | 2017-06-30 | -20 |  | CIP-005-6 88.79% CIP-010-3 81.40% CIP-013-1 884.19% | 13
PTB - Present to BOT | 2017-08-09 | 2017-08-11 | 2017-08-09 | 2017-08-11 | 0 |  |  | 14
Filing - Filing with Regulators | 2017-09-26 | 2017-09-26 | 2017-09-24 | 2017-09-27 | -2 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Create project record | 2016-08-01 | Added project to PTS.
Periodic Update | 2016-08-21 | Added FERC deadline.
Baseline Schedule | 2016-11-30 | SDT determined the schedule.
Present Schedule to SC | 2017-03-15 | Accepted the SDT project schedule.
Removed Liaison | 2017-04-14 | Removed R. Kinard due to resigning from PMOS.
Removed Liaison | 2017-07-27 | A. Kimmey due to leaving company.
Archive Project | 2017-10-12 | PMOS Archived the project as it was file on 9/26/2017.
Formulas:
Baseline End = +[Baseline Start]+32
Projected or Actual End = +[Projected or Actual Start]+2
Note on E33: FERC Deadline

## 2016-04 (hidden)
Project | 2016-04 | [5 empty] | Home
Project Name | Modifications to PRC-025-1
Status | Archived
Comments | Providing the SC an update on a non-substantive correction (Vlowside to Vhighside) to the Guidelines and Technical Basis before filing.
Deliverable | PRC-025-2
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 9, Medium |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | Yes
Developer | Scott Barfield-McGinnis
PMOS Liaison | Charles Yeung
Affected Standards | 1 | PRC-025-1
Last Updated | 2018-03-14
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2016-09-16 | 2016-09-28 | 2016-09-16 | 2016-09-28 | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2016-09-16 | 2016-10-18 | 2016-09-16 | 2016-10-18 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 | 2017-03-20 | 2017-04-03 | 2017-03-02 | 2017-04-01 | -18 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2017-07-25 | 2017-09-07 | 2017-07-26 | 2017-09-08 | 1 |  |  | 8
CAB - Com/Add Ballot 2 | 2017-10-30 | 2017-12-14 | 2017-10-24 | 2017-12-07 | -6 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2018-01-09 | 2018-01-18 | 2018-01-09 | 2018-01-18 | 0 |  |  | 13
PTB - Present to BOT | 2018-02-07 | 2018-02-09 | 2018-02-07 | 2018-02-09 | 0 |  |  | 14
Filing - Filing with Regulators | 2018-03-07 | 2018-03-10 | 2018-03-07 | 2018-03-10 | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
SC Authorized Posting | 2016-09-14 | SAR and SAR SDT nominations.
Accept Baseline Schedule | 2017-07-27 | Accepted by PMOS.
Archive Project | 2018-03-14 | PMOS Archived the project following the filing.
Formulas:
Baseline End = +[Baseline Start]+30
Projected or Actual End = +[Projected or Actual Start]+44

## 2017-01 (hidden)
Project | 2017-01 | [5 empty] | Home
Project Name | Modifications to BAL-003-1.1
Status | Archived
Comments | The standard passed at 100%. The project documents went to the Board in November 2019 and was filed on December 19, 2019.
Deliverable | BAL-003-2
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 8, Medium |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Laura Anderson
PMOS Liaison | Amy Casuscelli & Linda Lynch
Affected Standards | 1 | BAL-003-1.1
Last Updated | 2020-02-14
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2017-06-19 | 2017-07-03 | 2017-06-19 | 2017-07-03 | 0 |  |  | 1
Nominations - DT | 2017-07-27 | 2017-08-09 | 2017-07-27 | 2017-08-09 | 0 |  | Supplemental Nominations | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2017-06-19 | 2017-07-18 | 2017-06-19 | 2017-07-18 | 0 |  | By NERC RS | 4
SP2 - SAR/PR/WP Posting 2 | 2017-11-02 | 2017-12-01 | 2017-11-02 | 2017-12-01 | 0 |  | By NWPP FRSG | 5
CP1 - Comment Period 1 | 2018-09-06 | 2018-09-20 |  |  |  |  | Unscheduled posting | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2018-12-04 | 2019-01-17 | 2018-11-06 | 2019-01-09 | -28 |  | Passed at 96.41% | 8
CAB - Com/Add Ballot 2 |  |  | 2019-02-18 | 2019-04-03 | 0 |  | Balloting again due to comments | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2019-10-10 | 2019-10-24 | 2019-04-16 | 2019-04-26 | -177 |  | 100% | 13
PTB - Present to BOT | 2019-11-06 | 2019-11-09 | 2019-05-09 | 2019-05-12 | -181 |  |  | 14
Filing - Filing with Regulators | 2019-12-09 | 2019-12-12 | 2019-06-09 | 2019-06-12 | -183 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Created Project in PTS | 2017-05-10 | Created Project record.
Assign PMOS Liaison | 2017-06-14 | Amy Casuscelli accepted appointment as PMOS liaison.
Assign PMOS Liaison | 2017-10-12 | Add Linda Lynch to support Amy Casuscelli.
Updated Standard Number | 2018-06-06 | Changed standard from BAL-003-1 to BAL-003-1.1.
Accept baseline | 2018-07-18 | PMOS accepted baseline project schedule.
Schedule adjustment | 2019-03-20 | The schedule moved out three months due to the IFRO study needed to ensure the SDT proposed changes do not create an issue.
Additional Ballot | 2019-07-09 | Decision made to go to an additional ballot 2 rather than final ballot.
No Additional Ballot | 2019-10-09 | Fill in the outcome of the Oct 8-9 SDT meeting.
Extended Ballot | 2019-10-20 | The ballot was extended to provide stakeholders adequate time to review the updated documents.
Archive Project | 2020-01-29 | Archived at Jan 2020 meeting of PMOS.
Formulas:
Baseline End = +[Baseline Start]+10
Baseline End = [Baseline Start]+3
Projected or Actual End = [Projected or Actual Start]+3
Projected or Actual Start = +[Projected or Actual End, row above]+30

## 2017-01b
Project | 2017-01b | [5 empty] | Home
Project Name | Modifications to BAL-003-1.1
Status | On Hold
Comments | The project is currently on hold.
Deliverable | BAL-003-3
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 11, Medium |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Darrel Richardson
PMOS Liaison | Pamela Hunter (Primary), Charles Yeung (Backup)
Affected Standards | 1 | BAL-003-2
Last Updated | 2024-04-10
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Pandemic | 90 | 1
AS2 - Additional SAR 2 | [5 empty] | Pandemic | 90 | 2
QR - Quality Review | [5 empty] | Posting Conflict | 7 | 3
SP1 - SAR/PR/WP Posting 1 | 2021-03-29 | 2021-04-27 | 2021-03-29 | 2021-04-27 | 0 | Research Required | 180 | 4
SP2 - SAR Revise/Response |  |  | 2021-06-26 | 2021-08-25 |  | N/A |  | 5
SDT - Dev Time |  |  | 2021-10-24 | 2021-12-23 | 0 | Research Required | 180 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2022-07-25 | 2022-09-08 | 2022-07-25 | 2022-09-08 | 0 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2023-05-23 | 2023-06-01 | 2023-05-23 | 2023-06-01 | 0 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | [5 empty] | N/A | 0 | 13
PTB - Present to BOT | [5 empty] | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
[6 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | Need FB Date | Calculated CF Date: | 1901-06-30
PTS Change Control
Reason for Update | Date | Notes
Created Project in PTS | 2019-03-07 | Created Project record per action item from PMOS 2/13/2019 meeting.
Baseline | 2019-05-15 | PMOS accepted baseline as presented.
NERC Standards | 2020-04-22 | The SC requested that we consider the Covid-19, the project was slowed down and a complexity factor was added.
PMOS Liaison | 2020-05-06 | Most of the team members are participating in daily operations, affected by Covid-19 procedures. This has caused a delay in the developing timeline.
PMOS Liaison | 2020-06-16 | The next posting is for the technical white paper, and the paper is being written by the Resources Subcommittee (RS).
Standards Developer | 2020-09-23 | Consider adding the Complexity Factor to this project since it did start in 2019.
PMOS Liaison | 2020-12-08 | The technical white paper will be posted in Jan 25, 2021. The drafting team added a technical white paper posting, and delayed the initial ballot posting.
PMOS Liaison | 2020-12-08 | An informal comment period for Phase II of Project 2017-01 Modifications to BAL-003 White Paper is open through 8 p.m. Eastern, Tuesday, April 27, 2021
Intentional Delay | 2022-04-01 | SAR posting was delayed due to pandemic work loads - Will not be reflected in complexity factor calculation due to SAR posting date.
Posting Conflict | 2022-04-01 | Delayed posting due to conflict of other projects
Research required | 2022-04-01 | This project require research
Project placed on hold | 2023-02-01 | This project require research - research/develop technical justification for using the median vs the mean FRM determination over the past two years in Attachment A.
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2017-02 (hidden)
Project | 2017-02 | [5 empty] | Home
Project Name | Modifications to Personnel Performance, Training, and Qualifications Standards
Status | Archived
Comments | NERC filed a petition for approval of PER-003 on July 23, 2018. Project archived by PMOS on Spetmber 13, 2018.
Deliverable | PER-003-2, retire PER-004-2
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 8, Medium |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Darrel Richardson
PMOS Liaison | Mike Brytowski
Affected Standards | 2 | PER-003-1 & PER-004-2
Last Updated | 2018-09-13
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  | EPR SDT appointed as SDT | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2017-06-21 | 2017-07-24 | 2017-06-21 | 2017-07-24 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2018-01-22 | 2018-03-07 | 2018-01-22 | 2018-03-07 | 0 |  | 97.5% | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2018-04-03 | 2018-04-12 | 2018-04-27 | 2018-05-06 | 24 |  |  | 13
PTB - Present to BOT | 2018-05-09 | 2018-05-11 | 2018-05-09 | 2018-05-11 | 0 |  |  | 14
Filing - Filing with Regulators | 2018-07-23 | 2018-07-23 | 2018-06-09 | 2018-06-11 | -44 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Created Project in PTS | 2017-05-10 | Created Project record.
Assign PMOS Liaison | 2017-06-14 | Mike Brytowski accepted appointment as PMOS liaison.
Accept Baseline | 2018-01-31 | PMOS accepted baseline.
Archive Project | 2018-09-13 | PMOS archived project as it was filed on July 23, 2018
Formulas:
Baseline End = +[Baseline Start]+9
Projected or Actual End = +[Projected or Actual Start]+2

## 2017-03 (hidden)
Project | 2017-03 | [5 empty] | Home
Project Name | Periodic Review of FAC-008-3 Standard
Status | Archived
Comments | The periodic review team recommendation was to reaffirm with an action to revise, but at a later time. The Standards Efficiency Review Project 2018-03 partially revised the standard, therefore, this project is being archived.
Deliverable | PR Recommendations
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 9, Low (was Medium previously) |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Jordan Mallory
PMOS Liaison | Mark Pratt
Affected Standards | 1 | FAC-008-3
Last Updated | 2019-12-18
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2017-05-10 | 2017-05-23 | 2017-05-10 | 2017-05-23 | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2017-10-30 | 2017-12-13 | 2017-10-30 | 2017-12-13 | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Created Project in PTS | 2017-05-10 | Created Project record.
Assign PMOS Liaison | 2017-06-14 | Mark Pratt accepted appointment as PMOS liaison.
Developer Change | 2019-09-13 | Project transitioned from Al McMeekin to Mat Bunch.
Developer Change | 2019-09-27 | Mat Bunch was removed from the project and Jordan Mallory added.
Project Archived | 2019-12-18 | Archived due to SER 2018-03 revising the standard.

## 2017-04 (hidden)
Project | 2017-04 | [5 empty] | Home
Project Name | Periodic Review of Interchange Scheduling and Coordination Standards
Status | Archived
Comments | The periodic review team recommendation was to reaffirm with an action to revise, but at a later time. The Standards Efficiency Review Project 2018-03 partially revised the standard, therefore, this project is being archived.
Deliverable | PR Recommendations
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 9, Low (was Medium previously) |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Laura Anderson
PMOS Liaison | Charles Yeung
Affected Standards | 4 | INT-004, INT-006, INT-009, and INT-010
Last Updated | 2019-12-18
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2017-05-02 | 2017-05-15 | 2017-05-02 | 2017-05-15 | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2018-01-10 | 2018-02-23 | [5 empty] | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT | 2020-02-05 | 2020-02-07 | [5 empty] | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Created Project in PTS | 2017-05-10 | Created Project record.
Assign PMOS Liaison | 2017-06-14 | Charles Yeung accepted appointment as PMOS liaison.
Archive Project | 2019-12-18 | Archived due to SER 2018-03 revising the standard.
Formulas:
Projected or Actual End = +[Projected or Actual Start]+2

## 2017-05 (hidden)
Project | 2017-05 | [5 empty] | Home
Project Name | Periodic Review NUC-001-3
Status | Archived
Comments | The NUC periodic review is being closed because the Project 2017-07 Standards Alignment with Registration is presented to the BOT in February 2020. The 2017-07 SDT is proposing another version of the NUC standards, so there’s no need for this periodic review to move forward.
Deliverable | PR Recommendations
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 9, Low (was Medium previously) |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Jordan Mallory
PMOS Liaison | Amy Casuscelli and Colby Bellville
Affected Standards | 1 | NUC-001-3
Last Updated | 2019-12-18
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2017-05-10 | 2017-05-23 | 2017-05-10 | 2017-05-23 | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2017-12-15 | 2018-01-29 | 2017-12-04 | 2018-01-17 | -11 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT | 2020-02-05 | 2020-02-07 | [5 empty] | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Created Project in PTS | 2017-05-10 | Created Project record.
Assign PMOS Liaison | 2017-06-14 | Amy Casuscelli accepted appointment as PMOS liaison.
Assign PMOS Liaison | 2017-10-12 | Assigned Colby Bellville to support Amy Casuscelli (new SC vice chair)
Developer Change | 2019-09-27 | Mat Bunch was removed from the project and Jordan Mallory added.
Archive Project | 2019-12-18 | Project archived due to standard changes to NUC-001 in Project 2017-07.
Formulas:
Baseline End = +[Baseline Start]+44
Projected or Actual End = +[Projected or Actual Start]+2

## 2017-06 (hidden)
Project | 2017-06 | [5 empty] | Home
Project Name | Project 2017-06 Modifications to BAL-002-2
Status | Archived
Comments | NERC filed a petition for approval on August 17, 2018. The project was archived by the PMOS on September 13, 2018.
Deliverable | BAL-002-3
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 8, Medium |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Darrel Richardson
PMOS Liaison | Ken Lanehome
Affected Standards | 1 | BAL-002-2
Last Updated | 2018-09-13
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2017-06-20 | 2017-07-03 | 2017-06-20 | 2017-07-03 | 0 |  |  | 1
Nominations - DT | 2017-07-27 | 2017-08-09 | 2017-07-27 | 2017-08-09 | 0 |  | Supplemental Nominations | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2017-06-20 | 2017-07-20 | 2017-06-20 | 2017-07-20 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2018-03-22 | 2018-05-08 | [5 empty] | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2018-06-29 | 2018-07-08 | [5 empty] | 13
PTB - Present to BOT | 2018-08-15 | 2017-08-17 | [5 empty] | 14
Filing - Filing with Regulators | 2018-08-17 | 2018-08-20 | [5 empty] | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Created Project in PTS | 2017-05-30 | Created Project record.
Assign PMOS Liaison | 2017-06-14 | Ken Lanehome accepted appointment as PMOS liaison.
SAR | 2018-02-14 | SC accepts the final SAR.
Accept Baseline | N/A | Project schedule baseline was never submitted to PMOS.
Archive Project | 2018-09-13 | PMOS archived project as it was filed on August 17, 2018.
Formulas:
Projected or Actual End = +[Projected or Actual Start]+9

## 2017-07 (hidden)
Project | 2017-07 | [5 empty] | Home
Project Name | Stds Alignment with Registration
Status | Pending Regulatory Filing
Comments | Project 2017-07 Standards Alignment with Registration posted final ballot January 14-23. The BOT adoption at the February 2020 meeting.
Deliverable | FAC-002-3, IRO-010-3, MOD-031-3, MOD-033-2, NUC-001-4, PRC-006-4, and TOP-003-4
Deadline
Priority in RSDP, click to see applicable Footnote | Footnote 9, Low |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Laura Anderson
PMOS Liaison | Mike Brytowski
Affected Standards | 7 | Standards with PSE, IA, or LSE (FAC-002, INT-004, IRO-010, MOD-031, MOD-032, NUC-001, and TOP-003)
Last Updated | 2020-03-18
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index | Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other
Nominations - SAR / PR | 2017-08-01 | 2017-08-14 | 2017-08-01 | 2017-08-14 | 0 |  |  | 1 | 0 | 2017-08-01 | 2017-08-14 | 2017-08-01 | 2017-08-14 | 0
Nominations - DT | 2018-05-01 | 2018-05-14 | [5 empty] | 2 | 0 | 2018-05-01 | 2018-05-14
QR - Quality Review |  |  |  |  | 0 |  |  | 3 | 0 |  |  |  |  | 0
SP1 - SAR/PR/WP Posting 1 | 2017-08-01 | 2017-08-30 | 2017-08-01 | 2017-08-30 | 0 |  |  | 4 | 0 | 2017-08-01 | 2017-08-30 | 2017-08-01 | 2017-08-30 | 0
SP2 - SAR/PR/WP Posting 2 | 2017-12-11 | 2018-01-09 | 2017-12-07 | 2018-01-06 | -4 |  |  | 5 | 0 | 2017-12-11 | 2018-01-09 | 2017-12-07 | 2018-01-06 | -4
CP1 - Comment Period 1 | 2018-02-01 | 2018-03-02 | 2018-02-01 | 2018-03-02 | 0 |  |  | 6 | 0 | 2018-02-01 | 2018-03-02 | 2018-02-01 | 2018-03-02 | 0
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7 | 0 |  |  |  |  | 0
CIB - Com/Ballot 1 (Initial) | 2019-10-29 | 2019-12-12 | 2019-10-28 | 2019-12-12 | -1 |  | New Baseline? | 8 | 0 | 2019-10-29 | 2019-12-12 | 2018-09-17 | 2018-11-01 | -407
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9 | 0 |  |  |  |  | 0
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10 | 0 |  |  |  |  | 0
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11 | 0 |  |  |  |  | 0
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12 | 0 |  |  |  |  | 0
FB - Final Ballot | 2020-01-09 | 2020-01-19 | 2020-01-06 | 2020-01-16 | -3 |  |  | 13 | 0 | 2020-01-09 | 2020-01-19 | 2018-12-04 | 2018-12-14 | -401
PTB - Present to BOT | 2020-02-06 | 2020-02-08 | 2020-02-06 | 2020-02-09 | 0 |  |  | 14 | 0 | 2020-02-05 | 2020-02-07 | 2019-02-05 | 2019-02-08 | -365
Filing - Filing with Regulators | 2020-03-07 | 2020-03-10 | 2020-03-07 | 2020-03-10 | 0 |  |  | 15 | 0 |  |  | 2019-03-07 | 2019-03-10 | 0
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16 | 0 |  |  |  |  | 0
PTS Change Control
Reason for Update | Date | Notes
Assign PMOS Liaison | 2017-07-27 | Mike Brytowski accepted appointment as PMOS liaison.
SC Action | 2018-06-13 | SC appoint drafting team as recommended by NERC staff.
Accept Baseline | 2018-09-13 | PMOS accepted based line as presented to the members.
Schedule adjustment | 2018-10-31 | The PMOS removed the "projected schedule" as it was inaccurate and misleading.
Reactivated | 2019-08-01 | Project moved off of Hold following the SER work.
| 2020-03-18 | The Standard was approved by the Board at the Feb 2020 meeting.
Archive Project | 2020-03-18 | PMOS Archived the project following the filing.
Formulas:
Baseline End = +[Baseline Start]+13
Projected or Actual End = +[Projected or Actual Start]+10
Baseline Start = +[Baseline Start, row above]+30

## 2017-08 (hidden)
Project | 2017-08 | [5 empty] | Home
Project Name | Open - Available
Status | Void
Comments
Deliverable | CIP-014-4
Deadline
Priority in RSDP, click to see applicable Footnote
P81 Req (2013)
Number of Directives
No. of Guidances (see Note 2)
Directionally consistent with IERP findings (See Note 5)
Developer | Mat Bunch
PMOS Liaison
Affected Standards
Last Updated | 2017-07-17
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Assign PMOS Liaison | 2017-07-27

## 2018-01 (hidden)
Project | 2018-01 | [5 empty] | Home
Project Name | Canadian-specific Revisions to TPL-007-2
Status | Archived
Comments | The standard passed on initial ballot at 100% and was adopted by the NERC Board last November. The standard has been filed with Canadian authorties and an informational filing with FERC.
Deliverable | TPL-007-3
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 10, Medium |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Mat Bunch
PMOS Liaison | Charles Yeung
Affected Standards | 1 | TPL-007-2
Last Updated | 2019-03-07
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2018-03-30 | 2018-04-19 | [5 empty] | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2018-03-30 | 2018-04-30 | 2018-03-30 | 2018-04-30 |  |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2018-08-10 | 2018-09-06 | 2018-08-10 | 2018-09-09 | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2018-10-02 | 2018-11-15 | 2018-10-05 | 2018-11-19 | 3 |  |  | 8
CAB - Com/Add Ballot 2 |  |  | 2018-12-06 | 2019-01-20 | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2018-11-29 | 2018-12-10 | 2019-01-24 | 2019-02-03 | 56 |  |  | 13
PTB - Present to BOT | 2019-02-07 | 2019-02-09 | 2019-02-07 | 2019-02-09 | 0 |  |  | 14
Filing - Filing with Regulators | 2019-03-11 | 2019-03-13 | 2019-03-07 | 2019-03-09 | -4 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Assign PMOS Liaison | 2018-04-25 | C. Yeung acccept to follow project.
Accept baseline schedule | 2018-09-13 | PMOS accepted the baseline schedule as presented to the members.
Corrected BOT Date | 2018-10-03 | Baseline incorrectly listed BOT delivery for May 2019 and it should have been Feb 2019.
Archive Project |  | Archiving anticipated at March 20 meeting.
Formulas:
Baseline End = +[Baseline Start]+30
Projected or Actual End = [Projected or Actual Start]+2
Projected or Actual End = +[Projected or Actual Start]+2
Projected or Actual Start = [Projected or Actual End, row above]+30

## 2018-02 (hidden)
Project | 2018-02 | [5 empty] | Home
Project Name | Modifications to CIP-008 Cyber Security Incident Reporting
Status | Archived
Comments | The standard has been filed with regulatory authorities.
Deliverable | CIP-008-6
Deadline | 2019-04-01
Priority in RSDP, click to see applicable Footnote | Footnote 10, High |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 1 | Order No. 848 (1 Directive, 4 elements)
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Alison Oswald
PMOS Liaison | Colby Bellville & Amy Casuscelli
Affected Standards | 1 | CIP-008-5
Last Updated | 2019-03-07
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2018-08-10 | 2018-08-29 | 2018-08-10 | 2018-08-30 |  |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2018-08-10 | 2018-09-10 | 2018-08-10 | 2018-09-09 |  |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2018-10-03 | 2018-10-22 | 2018-10-04 | 2018-10-24 | 1 |  |  | 8
CAB - Com/Add Ballot 2 | 2018-11-15 | 2018-11-29 | 2018-11-14 | 2018-11-29 | -1 |  |  | 9
CAB - Com/Add Ballot 3 | [7 empty] | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2019-01-15 | 2019-01-22 | 2019-01-14 | 2019-01-19 | -1 |  |  | 13
PTB - Present to BOT | 2019-02-06 | 2019-02-08 | 2019-02-06 | 2019-02-08 | 0 |  |  | 14
Filing - Filing with Regulators | 2019-03-10 | 2019-03-12 | 2019-03-10 | 2019-03-12 | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
SC Action | 2018-08-09 | SCEC authorized posting of the SAR and solicitation of nominations.
Project added to PTS | 2018-08-10 | Added project for tracking by PMOS.
Assign PMOS Liaison | 2018-09-13 | PMOS appointed Colby Belleville and Amy Casuscelli to the project.
SC Action | 2018-10-02 | SCEC authorized posting with shortened (waiver) posting periods.
Accept Baseline | 2018-10-31 | PMOS accepted the baseline schedule (periods are compressed as approved by SC).
Archive Projec | 2019-03-20 | Archived by PMOS action.
Formulas:
Baseline End = +[Baseline Start]+20
Projected or Actual Start = +[Projected or Actual End, row above]+30
Projected or Actual End = +[Projected or Actual Start]+2
Baseline Start = +[Baseline End, row above]+30

## 2018-03 (hidden)
Project | 2018-03 | [5 empty] | Home
Project Name | Standards Efficiency Review Retirements (SER-Phase I)
Status | Archived
Comments | The Project 2018-03 standard drafting team has been recalled to reconsider retirement of Requirements R7 and R8 of FAC-008-3 per the FERC Order issued on September 17, 2020.
Deliverable | Retirements Only
Deadline
Priority in RSDP, click to see applicable Footnote | N/A |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Laura Anderson
PMOS Liaison | Mark Pratt (primary), Michael Brytowski (secondary)
Affected Standards | 1 | FAC-008-3
Last Updated | 2021-01-27
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2017-11-14 | 2017-11-30 | [5 empty] | 1
Nominations - DT | 2018-08-28 | 2018-09-17 | [5 empty] | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2018-08-28 | 2018-09-26 | [5 empty] | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2018-06-07 | 2018-07-10 | [5 empty] | 6
CP2 - Comment Period 2 | 2019-03-07 | 2019-03-22 |  |  |  |  | PH II SURVEY | 7
CIB - Com/Ballot 1 (Initial) | 2019-02-27 | 2019-04-12 | 2019-02-26 | 2019-04-12 | -1 |  |  | 8
CAB - Com/Add Ballot 2 |  |  | 2019-04-22 | 2019-06-06 | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2019-04-22 | 2019-05-02 | 2019-07-22 | 2019-08-01 | 91 |  |  | 13
PTB - Present to BOT | 2019-08-15 | 2019-08-18 | 2019-08-15 | 2019-08-18 | 0 |  |  | 14
Filing - Filing with Regulators | 2019-09-14 | 2019-09-16 | 2019-09-14 | 2019-09-16 | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
New Project | 2018-08-22 | SC accepted the SAR and nominations for posting.
SC Action | 2019-01-23 | SC appointed team and authorized project.
Baseline | 2019-02-13 | Accepted baseline schedule.
SC Action | 2019-02-20 | SC authorized posting and initial ballot.
BOT Adoption | 2019-05-08 | NERC Board adopted retirements.
Archive Project | 2019-06-26 | The project documents were filed on June 7, 2019.
Revive this project | 2020-10-29 | We will keep the PMOS liaison assignment if the project comes back.
Formulas:
Baseline End = +[Baseline Start]+45
Projected or Actual End = +[Projected or Actual Start]+3
Projected or Actual Start = +[Projected or Actual Start, row above]+30
Baseline Start = +[Baseline Start, row above]+30

## 2018-03b (hidden)
Project | 2018-03b | [5 empty] | Home
Project Name | Standards Efficiency Review Retirements (SER-Phase Ib)
Status | Archived
Comments | Initial 45-day posting with 10-day ballot period was posted November 30, 2020, and the ballot passed with over 95% approval. The next steps are as follows: SDT will review comments received during the recent posting period, and post for a 10-day final ballot, target is January 19, 2021, and send it to the NERC BOT for approval in February 4, 2021.
Deliverable
Deadline |  |  |  |  | N/A | Months to deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Reserved for Future Use | 0
P81 Req (2013) | Test P81
Number of Directives | 1 | Enter # in column B and description here. This value is 1 of 2 items that calculate the project baseline.
No. of Guidances (see Note 2) |  | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5) | Test IERP
Developer | Laura Anderson
PMOS Liaison | Mark Pratt (primary), Michael Brytowski (secondary)
Affected Standards | 1 | Enter number of Affected Standards in column B and the Standard here (e.g. TOP-001-4). This value is 2 of 2 items that calculate the project baseline.
Last Updated | 2021-05-03
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impact to Schedule | Time Impact | Index
SP1 - SAR/PR/WP Posting 1 | [5 empty] | N/A | 0 | 1
SP2 - SAR/PR/WP Posting 2 | [5 empty] | N/A | 0 | 2
QR - Quality Review | [5 empty] | N/A | 0 | 3
SP1 - SAR/PR/WP Posting 1 | [5 empty] | N/A | 0 | 4
SDT - Dev Time | [5 empty] | N/A | 0 | 5
CP1 - Comment Period 1 | 2020-11-30 | 2021-01-13 | 2020-11-30 | 2021-01-13 | 0 | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | [5 empty] | N/A | 0 | 8
CAB - Com/Add Ballot 2 | [5 empty] | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2021-01-19 | 2021-01-28 | 2021-01-19 | 2021-01-28 | 0 | N/A | 0 | 13
PTB - Present to BOT | 2021-02-04 | 2021-02-04 |  |  |  | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
[6 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | 0 | Calculated CF Date: | 2021-01-28
PTS Change Control
Reason for Update | Date | Notes
Project revived | 2020-10-02 | FERC issued an order remanding, review R7 and R8.
Passed initial ballot >95% | 2021-01-13 | Will proced to final ballot 01/19/2021-01/28/2021; BOT for adoption 02/04/2021
Formulas:
Time Impact = D22+(E31-D22)+SUM(H19:[Time Impact, row above])
Note on D22: Enter SC SAR date here
Note on F35: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date.

## 2018-04 (hidden)
Project | 2018-04 | [5 empty] | Home
Project Name | Modifications to PRC-024-2
Status | Pending Regulatory Filing
Comments | The standards passed industry balloting at 82.47%. The standard was approved by the Board in February.
Deliverable | PRC-024-3
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | N/A |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | N/A
Number of Directives | 0 | N/A
No. of Guidances (see Note 2) | 0 | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Latrice Harkness & Alison Oswald
PMOS Liaison | Linda Lynch
Affected Standards | 1 | PRC-024-2
Last Updated | 2020-03-18
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2018-12-19 | 2019-01-18 | [5 empty] | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2018-12-19 | 2019-01-18 | [5 empty] | 4
SP2 - SAR/PR/WP Posting 2 | 2019-06-27 | 2019-07-26 |  |  |  |  | Supl. SAR | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2019-04-17 | 2019-05-31 | 2019-04-17 | 2019-06-01 | 0 |  |  | 8
CAB - Com/Add Ballot 2 | 2019-09-20 | 2019-11-04 | 2019-06-17 | 2019-08-01 | -95 |  |  | 9
CAB - Com/Add Ballot 3 |  |  | 2019-08-15 | 2019-09-29 | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2019-12-04 | 2019-12-13 | 2019-10-14 | 2019-10-24 | -51 |  |  | 13
PTB - Present to BOT | 2019-12-27 | 2019-12-30 | 2019-11-07 | 2019-11-10 | -50 |  |  | 14
Filing - Filing with Regulators | 2020-01-29 | 2020-01-31 | 2019-12-10 | 2019-12-12 | -50 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16 | 0
PTS Change Control
Reason for Update | Date | Notes
New Project | 2018-09-13 | Project is indefinitely on hold due to SC rejecting the SARs.
Re-initiated | 2018-12-12 | The SC authorized the SAR (revised by SCPS) to move forward.
SC Action | 2019-01-31 | Appointment of drafting team.
Tentative Baseline Schedule | 2019-02-13 | A draft baseline schedule was shared with the PMOS.
Accept Baseline | 2019-06-26 | PMOS accepted the proposed baseline as presented.
SC Action | 2019-06-26 | SC authorized posting of supplemental SAR.
Developer Change | 2019-09-27 | Mat Bunch was removed from the project and Latrice Harkness and Alison Oswald were added.
Update | 2020-03-18 | Board approval Feb 2020. NERC legal is working on the FERC filing in March 2020.
Archive Project | 2020-03-18 | PMOS Archived the project following the filing.
Formulas:
Baseline End = +[Baseline Start]+45
Projected or Actual Start = +[Projected or Actual Start, row above]+23
Projected or Actual Start = +[Projected or Actual End, row above]+30
Projected or Actual End = +[Projected or Actual Start]+3
Baseline Start = +[Baseline End, row above]+30

## 2019-01 (hidden)
Project | 2019-01 | [5 empty] | Home
Project Name | Modifications to TPL-007-3
Status | Archived
Comments | The TPL-007-4 – Transmission System Planned Performance for Geomagnetic Disturbance Events passed final ballot at 78.95%. Project 2019-01 was approved by the Board in February.
Deliverable | TPL-007-4
Deadline | 2020-06-30 |  |  |  | -46 | Months to deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 1 | FERC Order No. 851
Reserved for Future Use | 0 | N/A
Reserved for Future Use | N/A
Developer | Alison Oswald
PMOS Liaison | Michael Brytowski
Affected Standards | 1 | TPL-007-3
Last Updated | 2020-03-18
0
0 | [8 empty] | Can delete this after discussion
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index | Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impact to Schedule | Time Impact
AS1 - Additional SAR 1 | [5 empty] | N/A | 0 | 1 | SP1 - SAR/PR/WP Posting 1
AS2 - Additional SAR 2 | 2019-02-25 | 2019-03-26 |  |  |  | N/A |  | 2 | SP2 - SAR/PR/WP Posting 2 | 2019-02-25 | 2019-03-26
QR - Quality Review | [5 empty] | N/A |  | 3 | QR - Quality Review |  |  |  |  | 0
SP1 - SAR/PR/WP Posting 1 | 2019-02-25 | 2019-03-26 | 2019-02-25 | 2019-03-27 | 0 | N/A |  | 4 | SP1 - SAR/PR/WP Posting 1 | 2019-02-25 | 2019-03-26
SDT - Dev Time |  |  | 2019-05-26 | 2019-08-24 | 0 | N/A |  | 5 | SDT - Dev Time
CP1 - Comment Period 1 | [5 empty] | N/A |  | 6 | CP1 - Comment Period 1 |  |  |  |  | 0
CP2 - Comment Period 2 | [5 empty] | N/A |  | 7 | CP2 - Comment Period 2 |  |  |  |  | 0
CIB - Com/Ballot 1 (Initial) | 2019-07-26 | 2019-09-09 | 2019-08-24 | 2019-10-08 | 29 | N/A |  | 8 | CIB - Com/Ballot 1 (Initial) | 2019-07-26 | 2019-09-09 | 2019-07-29 | 2019-09-12 | 3
CAB - Com/Add Ballot 2 |  |  | 2019-12-07 | 2020-01-21 | 0 | N/A |  | 9 | CAB - Com/Add Ballot 2 |  |  | 2019-10-21 | 2019-12-05 | 0
CAB - Com/Add Ballot 3 | [5 empty] | N/A |  | 10 | CAB - Com/Add Ballot 3 |  |  | 2020-01-23 | 2020-03-08 | 0
CAB - Com/Add Ballot 4 | [5 empty] | N/A |  | 11 | CAB - Com/Add Ballot 4 |  |  |  |  | 0
CAB - Com/Add Ballot 5 | [5 empty] | N/A |  | 12 | CAB - Com/Add Ballot 5 |  |  |  |  | 0
FB - Final Ballot | 2019-11-11 | 2019-11-22 | 2020-02-20 | 2020-03-01 | 101 | N/A |  | 13 | FB - Final Ballot | 2019-11-11 | 2019-11-22 | 2020-04-20 | 2020-04-30 | 161
PTB - Present to BOT | 2020-02-04 | 2020-02-07 |  |  |  | N/A |  | 14 | PTB - Present to BOT | 2020-02-04 | 2020-02-07 | 2020-05-13 | 2020-05-16 | 99
Filing - Filing with Regulators | 2020-03-08 | 2020-03-11 |  |  |  | N/A |  | 15 | Filing - Filing with Regulators | 2020-03-08 | 2020-03-11 | 2020-06-15 | 2020-06-18 | 99
0 | [5 empty] | N/A |  | 16 | Complexity Final Ballot Date |  |  |  |  | 0
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | 100 | Calculated CF Date: | 2020-03-01
PTS Change Control
Reason for Update | Date | Notes
Accept SAR | 2019-02-20 | Standards Committee accepted the SAR for posting
PMOS Liaison Assigned | 2019-03-20 | M. Brytowski and S. Cavote volunteered to follow the project.
Accept Baseline | 2019-05-15 | PMOS accepted the proposed baseline as presented
PMOS Liaison Removed | 2019-09-09 | S. Cavote resigned from the PMOS.
Standard Passed | 2019-09-09 | Team did not vary from FERC directive, which led to high support and no need for two additional ballots.
Complexity Factors | 2020-03-13 | Applied Complexity Factors to all 2019 projects to capture 5-year review.
Update | 2020-03-18 | The Standard was approved by the Board at the Feb 2020 meeting.
Archive Project | 2020-03-18 | PMOS Archived the project following the filing.
Note on D22: Enter SC SAR date here
Note on F35: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date.

## 2019-02 (hidden)
Project | 2019-02 | [5 empty] | Home
Project Name | BES Cyber System Information Access Management
Status | Archived
Comments | This project is pending FERC approval.
Deliverable | CIP-004-7 and CIP-011-3
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 11, Medium |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | N/A
Reserved for Future Use | 0 | N/A
Reserved for Future Use | N/A
Developer | Jordan Mallory
PMOS Liaison | Kirk Rosener (primary), Colby Bellville (secondary)
Affected Standards | 2 | CIP-004 and CIP-0011
Last Updated | 2021-10-13
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | 2019-08-22 | 2019-09-20 |  |  |  | Action Deferred | 30 | 1
AS2 - Additional SAR 2 |  |  |  |  | 0 | Supplemental members | 60 | 2
QR - Quality Review | 2020-05-27 | 2020-06-08 |  |  |  | Pandemic | 90 | 3
SP1 - SAR/PR/WP Posting 1 | 2019-03-28 | 2019-04-26 | 2019-03-28 | 2019-04-26 | 0 | N/A | 0 | 4
SDT - Dev Time | 2019-06-26 | 2019-12-23 | 2019-06-25 | 2019-10-23 | -1 | N/A | 0 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2019-12-20 | 2020-02-03 | 2019-10-23 | 2019-12-07 | -58 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2020-08-06 | 2020-09-21 | 2020-02-06 | 2020-03-22 | -182 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | 2021-03-25 | 2021-05-10 |  |  |  | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 | N/A | 0 | 12
FB - Final Ballot | 2021-06-02 | 2021-06-11 | 2020-04-21 | 2020-05-01 |  | N/A | 0 | 13
PTB - Present to BOT | 2021-11-03 | 2021-11-04 |  |  |  | N/A | 0 | 14
Filing - Filing with Regulators | 2021-12-07 | 2021-12-07 |  |  |  | N/A | 0 | 15
0 | [5 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | -226 | Calculated CF Date: | 2020-10-28
PTS Change Control
Reason for Update | Date | Notes
Accept SAR | 2019-03-20 | Standards Committee Action
Assign PMOS Liaison | 2019-05-15 | Colby Bellville and Kirk Rosner were appointed as liaisons to the project.
Appoint SDT | 2019-05-22 | The SC appointed the slate of nominees based on changes during the meeting.
SAR Accepted | 2019-07-24 | SC accepted SAR and authorized solicitation for a drafting team.
Accept Baseline | 2019-09-18 | PMOS accepted baseline as presented.
Appoint SDT | 2019-10-23 | SC appointed supplemental members to the SDT.
Project Delay | 2019-11-20 | SC differred action until December 2019.
Complexity Factors | 2020-03-13 | Applied Complexity Factors to all 2019 projects to capture 5-year review.
NERC Standards | 2020-04-22 | The SC requested that we consider the Covid-19, the project was slowed down and a complexity factor was added.
Dates updated | 2020-08-05 | Projected Start/End Dates updated to reflect current schedule status. New Ballot 2, Final Ballot and BOT projected dates reflect SDT updates to the Standards aligning with Industry Comments received on the previous SDT draft versions.
Note on F35: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date.

## 2019-03 (hidden)
Project | 2019-03 | [5 empty] | Home
Project Name | Cyber Security Supply Chain Risks
Status | Archived
Comments | The project passed final ballot on October 16, 2020 and was approved by the NERC board during the November 2020 meeting.
Deliverable | CIP-005-6, CIP-010-3, and CIP-013-1
Deadline | 2020-12-25 |  |  |  | -40 | Months to deadline
Priority in RSDP, click to see applicable Footnote | 0 |  | Priority (1-Low, 2-Med, 3-High ) |  | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 1 | This project will address the directives issued by FERC in Order No. 850. This project will also address NERC staff recommendation from the Supply Chain Report.
Reserved for Future Use | 0 | N/A
Reserved for Future Use | N/A
Developer | Alison Oswald/Jordan Mallory
PMOS Liaison | Masuncha Bussey (primary), Kirk Rosener (secondary) and Linda Lynch (tertiary)
Affected Standards | 3 | CIP-005-6, CIP-010-3, and CIP-013-1
Last Updated | 2021-01-08
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Pandemic | 90 | 1
AS2 - Additional SAR 2 | 2019-07-02 | 2019-08-01 |  |  |  | N/A | 0 | 2
QR - Quality Review | 2020-04-15 | 2020-04-22 |  |  |  | N/A | 0 | 3
SP1 - SAR/PR/WP Posting 1 | 2019-07-02 | 2019-08-01 | 2019-10-23 | 2019-11-22 | 113 | N/A | 0 | 4
SDT - Dev Time |  |  | 2020-01-21 | 2020-08-18 | 0 | N/A | 0 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2020-01-27 | 2020-03-12 | 2020-08-18 | 2020-10-02 | 204 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2020-05-08 | 2020-06-22 | 2020-12-01 | 2021-01-15 | 207 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | 2020-07-28 | 2020-09-10 |  |  |  | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2020-10-07 | 2020-10-16 | 2021-02-14 | 2021-02-24 | 130 | N/A | 0 | 13
PTB - Present to BOT | 2020-11-04 | 2020-11-05 |  |  |  | N/A | 0 | 14
Filing - Filing with Regulators | 2020-12-26 | 2020-12-29 |  |  |  | N/A | 0 | 15
0 | [5 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | 221 | Calculated CF Date: | 2021-05-25
PTS Change Control
Reason for Update | Date | Notes
Accept SAR | 2019-06-26 | Standards Committee accepted the SAR submitted by NERC in response to Order 850.
New Project | 2019-07-10 | Setup PTS for tracking.
Assign Liason | 2019-08-07 | Kirk Rosener (Primary) and Sean Cavote (Backup) volunteered as PMOS Liaisons.
Assign Liason | 2019-09-18 | Removed Sean Cavote and added Linda Lynch as the new primary liaison.
Revised SAR | 2019-10-23 | Accepted by SC.
Complexity Factors | 2020-03-13 | Applied Complexity Factors to all 2019 projects to capture 5-year review.
NERC Standards | 2020-04-22 | The SC requested that we consider the Covid-19, the project was slowed down and a complexity factor was added.
Note on B6: Order becomes in effect 60 days after publication in the Federal Register. Published on October 26, 2018, 60 days is 12/25/2018. Deadline is 24 months after publication.
Note on D22: Enter SC SAR date here
Note on F35: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date.

## 2019-04
Project | 2019-04 | [5 empty] | Home
Project Name | Modifications to PRC-005-6
Status | On Hold
Comments | This project is on posting hold until after July 2024. The DT will continue to conduct DT meetings, but at a slower pace. We are now in the process of scheduling an in-person meeting with the entire SDT, and anticipating that it’ll be during the month of May in Raleigh, NC.
Deliverable | PRC-005
Deadline |  |  |  |  | None | Months to deadline
Priority in RSDP, click to see applicable Footnote | Footnote 11, Low |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | N/A
Reserved for Future Use | 0 | N/A
Reserved for Future Use | N/A
Developer | Elsa Prince
PMOS Liaison | Joseph Gatten (primary), Sarah Habriga (backup)
Affected Standards | 1 | PRC-005-6
Last Updated | 2024-04-10
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | 2020-06-02 | 2020-07-08 |  |  |  | Pandemic | 90 | 1
AS2 - Additional SAR 2 | 2021-01-14 | 2021-02-12 |  |  |  | Pandemic | 90 | 2
QR - Quality Review | [5 empty] | SAR - Revised/Additional Posting | 60 | 3
SP1 - SAR/PR/WP Posting 1 | 2019-07-30 | 2019-08-28 | 2019-07-30 | 2019-08-29 | 0 | SAR - Revised/Additional Posting | 60 | 4
SP2 - SAR Revise/Response |  |  | 2019-10-28 | 2019-12-27 |  | Schedule Too Aggressive | 90 | 5
SDT - Dev Time |  |  | 2020-02-25 | 2020-04-25 | 0 | SAR - Revised/Additional Posting | 60 | 5
CP1 - Comment Period 1 | [5 empty] | Research Required | 180 | 6
CP2 - Comment Period 2 | [5 empty] | Supplemental members | 60 | 7
CIB - Com/Ballot 1 (Initial) | 2023-05-25 | 2023-07-10 | 2023-05-25 | 2023-07-10 | 0 | RSDP Priority Decrease | 60 | 8
CAB - Com/Add Ballot 2 | 2024-01-02 | 2024-02-15 |  |  |  | Posting Conflict | 7 | 9
CAB - Com/Add Ballot 3 | [5 empty] | Additional Outreach | 30 | 10
CAB - Com/Add Ballot 4 | [5 empty] | Pandemic | 90 | 11
CAB - Com/Add Ballot 5 | [5 empty] | Cross-Coordination (Parallel) | 90 | 12
FB - Final Ballot | 2024-04-04 | 2024-04-14 | 2023-09-04 | 2023-09-14 | -213 | Highly Technical | 90 | 13
PTB - Present to BOT | [7 empty] | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
0 |  |  |  |  | 0 | N/A |  | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | 844 | Calculated CF Date: | 2026-08-06
PTS Change Control
Reason for Update | Date | Notes
Standards Committee | 2019-06-26 | SC accepted the SAR and authorized posting for formal comment. SAR was submitted by the NAGF.
Assign Liason | 2019-08-07 | Mark Pratt (Primary) and Linda Lynch (Backup) volunteered as PMOS Liaisons
SDT Appointment | 2019-11-20 | SC appointed the standard drafting team.
Complexity Factors | 2020-03-13 | Applied Complexity Factors to all 2019 projects to capture 5-year review.
Update | 2020-03-18 | The baseline schedule will be developed during the call scheduled on Mar 20, 2020.
NERC Standards | 2020-04-22 | The SC requested that we consider the Covid-19, the project was slowed down and a complexity factor was added.
Posting Conflict | 2022-04-01 | Delayed posting due to conflict of other projects
Intentional Delay | 2022-04-01 | SAR posting was delayed due to pandemic
Additional Outreach | 2022-04-01 | Additional team members appointed (supplemental members)
Higly technical | 2023-03-06 | Highly technical and additional outreach is needed
Note on D22: Enter SC SAR date here
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date.

## 2019-05 (hidden)
Project | 2019-05 | [5 empty] | Home
Project Name | Modifications to PER-003
Status | Archived
Comments | At the July 21, 2021 SC meeting the PER-003 SAR was rejected. The SAR submitters will be notified and the project will be disbanded until the PCGC finishes their task force work to look into the CEHs.
Deliverable | PER-003
Deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) |  | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | N/A
Reserved for Future Use | 0 | N/A
Reserved for Future Use | N/A
Developer | Alison Oswald
PMOS Liaison | Colby Bellville (primary), Charles Yeung (secondary)
Affected Standards | 1 | PER-003
Last Updated | 2021-10-18
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Pandemic | 90 | 1
AS2 - Additional SAR 2 | [5 empty] | N/A | 0 | 2
QR - Quality Review | [5 empty] | N/A | 0 | 3
SP1 - SAR/PR/WP Posting 1 | 2019-08-01 | 2019-08-30 | 2019-08-01 | 2019-08-31 | 0 | N/A | 0 | 4
SDT - Dev Time |  |  | 2019-10-30 | 2019-12-29 | 0 | N/A | 0 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) |  |  | 2019-12-29 | 2020-02-12 | 0 | N/A | 0 | 8
CAB - Com/Add Ballot 2 |  |  | 2020-04-12 | 2020-05-27 | 0 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2021-07-21 | 2021-07-21 | 2020-06-26 | 2020-07-06 | -390 | N/A | 0 | 13
PTB - Present to BOT | [5 empty] | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
0 | [5 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | -290 | Calculated CF Date: | 2020-10-04
PTS Change Control
Reason for Update | Date | Notes
NERC Standards | 2020-04-30 | Due to Covid-19, Standards recommended placing this project on hold.
Standards Committee | 2019-07-24 | SC accepted the SAR and authorized posting for informal comment.
Assign Liason | 2019-08-07 | Colby Bellville (Primary) and Kirk Rosener (Backup) volunteered as PMOS Liaisons
Appoint SDT | 2019-10-23 | SC appointed the drafting team.
Complexity Factors | 2020-03-13 | Applied Complexity Factors to all 2019 projects to capture 5-year review.
Liaison Update | 2020-06-16 | PCGC is discussing the CEH requirements, project is on hold. The PCGC is still working on the question of how many continuing education hours that the new one system operator credential would need for renewal every three years.
Note on D22: Enter SC SAR date here
Note on F35: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date.

## 2019-06 (hidden)
Project | 2019-06 | [5 empty] | Home
Project Name | Cold Weather
Status | Archived
Comments | The SDT made a few non-substantive changes and posted for final ballot on May 18, 2021. This project is completed and has been filed with FERC.
Deliverable | EOP-011, IRO-010, TOP-003.
Deadline |  |  |  |  | N/A | Months to deadline
Priority in RSDP, click to see applicable Footnote | Footnote 11, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | N/A
Reserved for Future Use | 0 | N/A
Reserved for Future Use | N/A
Developer | Jordan Mallory
PMOS Liaison | Quinn Morrison (primary), Mike Brytowski (secondary)
Affected Standards | 3 | EOP-011, IRO-010, TOP-003.
Last Updated | 2021-08-05
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | 2020-02-19 | 2020-03-19 |  |  |  | SAR - Revised/Additional Posting | 60 | 1
AS2 - Additional SAR 2 | 2020-04-22 | 2020-05-21 |  |  |  | SAR - Revised/Additional Posting | 60 | 2
QR - Quality Review | [5 empty] | Pandemic | 90 | 3
SP1 - SAR/PR/WP Posting 1 | 2019-10-04 | 2019-11-03 | 2019-10-04 | 2019-11-03 | 0 | Schedule Too Conservative | -90 | 4
SDT - Dev Time | 2020-09-24 | 2021-03-23 | 2020-01-02 | 2020-06-30 | -266 | N/A | 0 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2021-01-27 | 2021-03-12 | 2020-06-30 | 2020-08-14 | -211 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2021-05-31 | 2021-07-15 | 2020-10-13 | 2020-11-27 | -230 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2021-05-18 | 2021-05-27 | 2020-12-27 | 2021-01-06 | -142 | N/A | 0 | 13
PTB - Present to BOT | 2021-06-11 | 2021-06-12 |  |  |  | N/A | 0 | 14
Filing - Filing with Regulators | 2021-06-17 | 2021-06-17 |  |  |  | N/A | 0 | 15
0 | [5 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: | 0 | 0 | 0 | 0 | -21 | Calculated CF Date: | 2021-05-06
PTS Change Control
Reason for Update | Date | Notes | 0 | 0 | 0 | 0 | 0
SC Authorized SAR | 2019-10-02 | The Standards Committee held a special call to authorize the SAR.
Created Project | 2019-10-04 | Created project in the tracker and assigned Jordan Mallory as the developer
Assign PMOS Liaison | 2019-11-13 | Quinn Morrison (pri) and Michael Brytowski (sec) accepted the liaison role on the project.
Complexity Factors | 2020-03-13 | Applied Complexity Factors to all 2019 projects to capture 5-year review.
PMOS | 2020-04-23 | PMOS recommends extending the comment period from 5/21 to 6/1.
NERC Standards | 2020-04-22 | The SC requested that we consider the Covid-19, the project was slowed down and a complexity factor was added.
Feb 2021 Extreme Weather Event in ERCOT | 2021-03-02 | NERC Board and upper management directed that this project is a top priority. The schedule has been modified, 25-day ballot instead of 45-days to make the June 11 Board meeting.
Notice of Request to Waive the SPM by Action without a Meeting | 2021-03-22 | Annoncement sent to request to shorten the next formal comment and ballot period(s) prior to final ballot for draft standards EOP-011-2, IRO-010-4, and TOP-003-5, from 45 days to 25 days, with a ballot and non-binding poll during the last 10 days of the 25-day period.
Note on B22: Enter SC SAR date here
Note on D22: Enter SC SAR date here
Note on F35: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date.

## 2020-01 (hidden)
Project | 2020-01 | [5 empty] | Home
Project Name | Modifications to MOD-032-1
Status | Terminated
Comments | UPDATE: Project 2020-01 Modifications to MOD-032 was rejected by the SC in December 2020 and the team is disbanded.The SAR drafting team members divided up into several sub-groups and developed a list of ‘Major Themes’. Formal meetings were held on August 17th and September 8th to update the SAR. Posting date to be determined. The SAR team will be asking the SC for guidance on the procedure for closing out the SAR and moving it to the SDT status.
Deliverable | MOD-032-2
Deadline |  |  |  |  | None | Months to deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | N/A
Reserved for Future Use | 0 | N/A
Reserved for Future Use | N/A
Developer | Chris Larson
PMOS Liaison | Linda Lynch (primary), Quinn Morrison (secondary)
Affected Standards | 1 | MOD-032-1
Last Updated | 2021-01-08
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Pandemic | 90 | 1
AS2 - Additional SAR 2 | [5 empty] | N/A | 0 | 2
QR - Quality Review | [5 empty] | N/A | 0 | 3
SP1 - SAR/PR/WP Posting 1 | 2020-03-24 | 2020-04-24 | 2020-03-24 | 2020-04-23 | 0 | N/A | 0 | 4
SDT - Dev Time |  |  | 2020-06-22 | 2020-08-21 | 0 | N/A | 0 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) |  |  | 2020-08-21 | 2020-10-05 | 0 | N/A | 0 | 8
CAB - Com/Add Ballot 2 |  |  | 2020-12-04 | 2021-01-18 | 0 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2020-12-09 | 2020-12-09 | 2021-02-17 | 2021-02-27 | 70 | N/A | 0 | 13
PTB - Present to BOT | [5 empty] | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
0 | [5 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: | 0 | 0 | 0 | 0 | 170 | Calculated CF Date: | 2021-05-28 | 0 | 0 | 0
PTS Change Control
Reason for Update | Date | Notes | 0 | 0 | 0 | 0 | 0
PMOS | 2020-04-23 | PMOS recommends to not start during the first week of June 2020. The intent is to stagger the projects by priority.
NERC Standards | 2020-04-22 | The SC requested that we consider the Covid-19, the project was slowed down and a complexity factor was added.
PMOS Chair | 2020-10-28 | Note that we have overlapping postings with other projects (Jan/Feb 2021). Consider delaying/stagging the dates.
Standards Update | 2020-12-09 | Project 2020-01 Modifications to MOD-032 was rejected by the SC in December 2020 and the team is disbanded.
Note on D22: Enter SC SAR date here
Note on F35: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2020-02
Project | 2020-02 | [5 empty] | Home
Project Name | Modifications to PRC-024 (Generator Ride-through)
Status | SDT Development
Comments | Details on Draft: New standard PRC-029 to address IBRs. Will be focused on IBR performance and performance measurement. Still working on the initial draft and assuring performance is measured against actual performance data and not based on unit capabilities or equipment/controller settings. SDT is focused on addressing IBR voltage ride-through for legacy/new IBR equipment. Anticipate Posting: Initial Draft of modified PRC-024 and new PRC-029 to proceed to the Standards Committee in March; requesting approval to post for 25-day formal comment period and ballot in late March. Other: Identified as part of 2024 directives from Order 901. Final draft required by FERC to be approved by Nov 4, 2024.
Deliverable | PRC-024
Deadline |  |  |  |  | N/A | Months to deadline
Priority in RSDP, click to see applicable Footnote | Footnote 11, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | N/A
Reserved for Future Use |  | N/A
Reserved for Future Use | N/A
Developer | Jamie Calderon
PMOS Liaison | Pamela Hunter (Primary), Anthony Westenkirchner (Backup), Darrel Grumman (Backup)
Affected Standards | 1 | PRC-024
Last Updated | 2024-04-10
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [7 empty] | 1
AS2 - Additional SAR 2 | [5 empty] | Research Required | 180 | 2
QR - Quality Review | [7 empty] | 3
SP1 - SAR/PR/WP Posting 1 | 2022-05-31 | 2020-05-13 | 2022-05-31 | 2022-06-30 | 0 | Supplemental members | 60 | 4
SP2 - SAR Revise/Response |  |  | 2022-08-29 | 2022-10-28 |  | Intentional Hold/Delay | 30 | 5
SDT - Dev Time |  |  | 2022-12-27 | 2023-02-25 | 0 | Standard Developer Change | 30 | 5
CP1 - Comment Period 1 | [5 empty] | SAR - Supplemental | 60 | 6
CP2 - Comment Period 2 | [5 empty] | Supplemental members | 60 | 7
CIB - Com/Ballot 1 (Initial) | 2024-03-27 | 2024-04-22 | 2023-02-25 | 2023-04-11 | -396 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2024-05-20 | 2024-06-03 | 2023-06-10 | 2023-07-25 | -345 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | 2024-07-01 | 2024-07-15 |  |  |  | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2024-07-18 | 2024-07-24 | 2023-08-24 | 2023-09-03 | -329 | N/A | 0 | 13
PTB - Present to BOT | [5 empty] | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
0 | [5 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | 95 | Calculated CF Date: | 2024-10-27
PTS Change Control
Reason for Update | Date | Notes
PMOS Liaison | 2020-04-23 | PMOS recommends to not start during the first week of June. The intent is to stagger the projects by priority.
NERC Standards | 2020-04-22 | The SC requested that we consider the Covid-19, the project was slowed down and a complexity factor was added.
PMOS Liaison | 2020-06-16 | Project scope will probably be revised, and a new project will be created. Project timeline TBD.
PMOS Liaison | 2020-12-08 | Two projects potential split will occur - MOD and PRC. Rebecca will be the primary liaison for one of the two. Linda will keep one project.
NERC Standards | 2022-05-10 | Revised transmission-connected dynamic reactive resources (TCDRR) SAR accepted by SC at April 20 meeting. SDT began revisions to PRC-024 and drafting Technical Rationale. here is a new SAR proposing a ride-through standard, which would replace/revise PRC-024-3. This be submitted to the SC on May 18. The next steps for Project 2020-02 will be coordinated appropriately.
NERC Standards | 2024-04-10 | Original SAR posted on March 20, 2020. Based on that scope of work the DT began to revise PRC-024 to add TCDRR and revise requirements. The new "Ride-through" SAR was posted on May 31, 2022. And the PTS project baseline was updated to reflect this new SAR posting date.
Note on D22: Enter SC SAR date here
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days
Note on H36: Elsa Prince: CF Date adjusts Baseline Final Ballot End Date. Delete this comment when activating project.

## Template Old (hidden)
Project | Test | [5 empty] | Home
Project Name | Test
Status | SAR
Comments | Test Comment
Deliverable | Test-001-1
Deadline | 2020-01-01 |  |  |  | -52 | Months to deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Project has been Re-Baselined? (0-No, 1-Yes) | 0
P81 Req (2013) | Test P81
Number of Directives | 0 | Enter # in column B and description here
No. of Guidances (see Note 2) | 0 | Enter number in column B and text here.
Directionally consistent with IERP findings (See Note 5) | Test IERP
Developer | Test Developer (Add hyperlink for email)
PMOS Liaison | Test PMOS
Affected Standards | 0 | Enter number of Affected Standards in column B and the Standard here (e.g. TOP-001-4)
Last Updated
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2024-04-15 15:19 | 2024-04-29 15:19 | 2024-04-22 15:19 | 2024-05-06 15:19 | 7 |  |  | 1
Nominations - DT | 2024-05-20 15:19 | 2024-06-03 15:19 | 2024-05-27 15:19 | 2024-06-10 15:19 | 7 |  |  | 2
QR - Quality Review | 2024-06-24 15:19 | 2024-07-08 15:19 | 2024-07-01 15:19 | 2024-07-15 15:19 | 7 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2024-07-29 15:19 | 2024-08-28 15:19 | 2024-08-05 15:19 | 2024-09-04 15:19 | 7 |  |  | 4
SP2 - SAR/PR/WP Posting 2 | 2024-09-18 15:19 | 2024-10-18 15:19 | 2024-09-25 15:19 | 2024-10-25 15:19 | 7 |  |  | 5
CP1 - Comment Period 1 | 2024-11-08 15:19 | 2024-12-08 15:19 | 2024-11-15 15:19 | 2024-12-15 15:19 | 7 |  |  | 6
CP2 - Comment Period 2 | 2024-12-29 15:19 | 2025-01-28 15:19 | 2025-01-05 15:19 | 2025-02-04 15:19 | 7 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2025-02-18 15:19 | 2025-04-04 15:19 | 2025-02-25 15:19 | 2025-04-11 15:19 | 7 |  |  | 8
CAB - Com/Add Ballot 2 | 2025-04-25 15:19 | 2025-06-09 15:19 | 2025-05-02 15:19 | 2025-06-16 15:19 | 7 |  |  | 9
CAB - Com/Add Ballot 3 | 2025-06-30 15:19 | 2025-08-14 15:19 | 2025-07-07 15:19 | 2025-08-21 15:19 | 7 |  |  | 10
CAB - Com/Add Ballot 4 | 2025-09-04 15:19 | 2025-10-19 15:19 | 2025-09-11 15:19 | 2025-10-26 15:19 | 7 |  |  | 11
CAB - Com/Add Ballot 5 | 2025-11-09 15:19 | 2025-12-24 15:19 | 2025-11-16 15:19 | 2025-12-31 15:19 | 7 |  |  | 12
FB - Final Ballot | 2026-01-14 15:19 | 2026-01-24 15:19 | 2026-01-21 15:19 | 2026-01-31 15:19 | 7 |  |  | 13
PTB - Present to BOT | 2026-02-14 15:19 | 2026-02-16 15:19 | 2026-02-21 15:19 | 2026-02-23 15:19 | 7 |  |  | 14
Filing - Filing with Regulators | 2026-03-09 15:19 | 2026-03-12 15:19 | 2026-03-16 15:19 | 2026-03-19 15:19 | 7 |  |  | 15
PT - Post Approval Training | 2026-04-02 15:19 | 2026-04-05 15:19 | 2026-04-09 15:19 | 2026-04-12 15:19 | 7 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Formulas:
Test = +[Projected or Actual End, row above]+21
Projected or Actual End = +[Test]+14
Baseline Start = +[Test]+7
Baseline Start = +[Baseline End, row above]+21
Baseline End = +[Baseline Start]+14
Note on B19: Add the new project, then goto the dashboard and construct the project with conditional formatting. Change only this date as needed for testing conditional formatting of new projects. Delete this note wihen finished and associated dates, then fill in with appropriate project dates.

## 2020-03 (hidden)
Project | 2020-03 | [5 empty] | Home
Project Name | Supply Chain Low Impact Revisions
Status | Archived
Comments | Final ballot occurred 10/26 – 11/04. The NERC board adopted the standard during the November 16th board meeting.
Deliverable | CIP-003-8
Deadline |  |  |  |  | N/A | Months to deadline
Priority in RSDP, click to see applicable Footnote | Footnote 11, High |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | N/A
Reserved for Future Use |  | N/A
Reserved for Future Use | N/A
Developer | Alison Oswald
PMOS Liaison | Kirk Rosener (primary), Ken Lanehome (secondary)
Affected Standards | 1 | CIP-003-8
Last Updated | 2023-01-05
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Pandemic | 90 | 1
AS2 - Additional SAR 2 | [5 empty] | Pandemic | 90 | 2
QR - Quality Review | [5 empty] | SAR - Revised/Additional Posting | 60 | 3
SP1 - SAR/PR/WP Posting 1 | 2020-04-03 | 2020-06-03 | 2020-04-03 | 2020-05-03 | 0 | Posting Conflict | 7 | 4
SDT - Dev Time |  |  | 2020-07-02 | 2020-08-31 | 0 | Pandemic | 90 | 5
CP1 - Comment Period 1 | [5 empty] | Cross-Coordination (Finish-Start) | 90 | 6
CP2 - Comment Period 2 | [5 empty] | Supplemental members | 60 | 7
CIB - Com/Ballot 1 (Initial) | 2021-08-27 | 2021-10-11 | 2020-08-31 | 2020-10-15 | -361 | Posting Conflict | 7 | 8
CAB - Com/Add Ballot 2 | 2022-02-07 | 2022-03-17 | 2020-12-14 | 2021-01-28 | -420 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | 2022-07-06 | 2022-08-05 |  |  |  | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2022-10-26 | 2022-11-04 | 2021-02-27 | 2021-03-09 | -606 | N/A | 0 | 13
PTB - Present to BOT | [5 empty] | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
0 | [5 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: | 0 | 0 | 0 | 0 | -111 | Calculated CF Date: | 2022-07-16
PTS Change Control
Reason for Update | Date | Notes | 0 | 0 | 0 | 0 | 0
SC Action | 2020-03-18 | SC Authorized SAR posting and solicitation of SAR DT.
NERC Standards | 2020-04-22 | The SC requested that we consider the Covid-19, the project was slowed down and a complexity factor was added.
Supplemental members | 2020-07-30 | From July 30, 2020, additional members were added from low impact entities
SAR - Revised/Additional Posting | 2021-12-20 | SAR posting was extended
Pandemic | 2021-12-20 | Pandemic continued to exist
Posting conflict | 2022-05-04 | Due to so many project posting at once, this posting has been postponed.
Note on D22: Enter SC SAR date here
Note on F35: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2020-04 (hidden)
Project | 2020-04 | [5 empty] | Home
Project Name | Modifications to CIP-012-1
Status | Approved
Comments | The final ballot closed on December 8th, 2023. The ballot passed with 88.36% approval on the Standard and 90.19% on the Implementation Plan. Next step would be presenting to BOT for adoption on December 12, 2023. Then file with FERC.
Deliverable | CIP-012-2
Deadline |  |  |  |  | N/A | Months to deadline
Priority in RSDP, click to see applicable Footnote | Footnote 11, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 1 | N/A
Reserved for Future Use |  | N/A
Reserved for Future Use | N/A
Developer | Ben Wu
PMOS Liaison | Sarah Habriga (primary), Jennifer Richardson (secondary)
Affected Standards | 1 | CIP-012
Last Updated | 2023-12-18
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Pandemic | 90 | 1
AS2 - Additional SAR 2 | [5 empty] | Pandemic | 90 | 2
QR - Quality Review | 2021-03-09 | 2021-03-17 |  |  |  | Action Deferred | 30 | 3
SP1 - SAR/PR/WP Posting 1 | 2020-04-08 | 2020-06-11 | 2020-04-08 | 2020-06-11 | 0 | Supplemental members | 60 | 4
SDT - Dev Time |  |  | 2020-08-10 | 2020-11-08 | 0 | Standard Developer Change | 30 | 5
CP1 - Comment Period 1 | [5 empty] | Posting Conflict | 7 | 6
CP2 - Comment Period 2 | [5 empty] | Supplemental members | 60 | 7
CIB - Com/Ballot 1 (Initial) | 2021-04-26 | 2021-06-09 | 2020-11-08 | 2020-12-23 | -169 | Supplemental members | 60 | 8
CAB - Com/Add Ballot 2 | 2021-11-30 | 2022-01-24 | 2021-02-21 | 2021-04-07 | -282 | Supplemental members | 60 | 9
CAB - Com/Add Ballot 3 | 2022-10-03 | 2022-11-29 |  |  |  | N/A | 0 | 10
CAB - Com/Add Ballot 4 | 2023-09-19 | 2023-11-03 |  |  |  | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2023-11-28 | 2023-12-07 | 2021-05-07 | 2021-05-17 | -935 | N/A | 0 | 13
PTB - Present to BOT | 2023-12-12 | 2023-12-12 |  |  |  | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
[6 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | -447 | Calculated CF Date: | 2022-09-16
PTS Change Control
Reason for Update | Date | Notes | 0 | 0 | 0 | 0 | 0
SC Action | 2020-03-18 | SC authorized SAR posting and solicitation of SAR DT.
NERC Standards | 2020-04-22 | The SC requested that we consider the Covid-19, the project was slowed down and a complexity factor was added.
PMOS Liaison | 2020-06-16 | Team nomination approval in Aug 2020.
Standards Developer | 2020-08-24 | SC cancelled the Aug 2020 meeting. Anticipate the nominations will occur in the Sept 2020 SC meeting.
Posting Conflict | 2021-11-30 | Extended posting for extra 10 days due to holiday season
Formulas:
Calculated Start = +[Calculated End, row above]+60
Calculated End = +[Calculated Start]+(B9*30)+(B14*60)
Calculated End = +[Calculated Start]+45
Time Impact = D22+(E31-D22)+SUM(H19:[Time Impact, row above])
Note on F35: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2020-05 (hidden)
Project | 2020-05 | [5 empty] | Home
Project Name | Modifications to FAC-001-3 and FAC-002-2
Status | Archived
Comments | The project passed final ballot with an 85.63% approval on April 22, 2022. NERC BOT adopted the Standards on May 12, 2022.
Deliverable | FAC-001-3, FAC-002-3
Deadline |  |  |  |  | N/A | Months to deadline
Priority in RSDP, click to see applicable Footnote | Footnote 11, Medium |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | N/A
Reserved for Future Use |  | N/A
Reserved for Future Use | N/A
Developer | Alison Oswald
PMOS Liaison | Anthony Westenkirchner (primary), Cristhian Godoy (secondary)
Affected Standards | 2 | FAC-001-2 and FAC-002-2.
Last Updated | 2022-06-06
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Pandemic | 90 | 1
AS2 - Additional SAR 2 | [5 empty] | Pandemic | 90 | 2
QR - Quality Review | [5 empty] | Posting Conflict | 7 | 3
SP1 - SAR/PR/WP Posting 1 | 2020-11-12 | 2020-12-12 | 2020-11-12 | 2020-12-12 | 0 | Posting Conflict | 7 | 4
SDT - Dev Time |  |  | 2021-02-10 | 2021-06-10 | 0 | Schedule Too Aggressive | 90 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2021-12-07 | 2022-01-31 | 2021-06-10 | 2021-07-25 | -180 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2022-03-09 | 2022-04-22 | 2021-09-23 | 2021-11-07 | -167 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2022-04-13 | 2022-04-22 | 2021-12-07 | 2021-12-17 | -127 | N/A | 0 | 13
PTB - Present to BOT | [5 empty] | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
0 | [5 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: | 0 | 0 | 0 | 0 | 158 | Calculated CF Date: | 2022-09-27
PTS Change Control
Reason for Update | Date | Notes | 0 | 0 | 0 | 0 | 0
SC Action | 2020-09-24 | SC authorized SAR posting and solicitation of SAR DT.
Posting Conflict | 2021-12-07 | Delayed posting
Posting Conflict | 2021-12-07 | Extended due to holidays
Note on D22: Enter SC SAR date here
Note on F35: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2020-06
Project | 2020-06 | [5 empty] | Home
Project Name | Verifications of Models and Data for Generators
Status | SDT Development
Comments | Additional Ballot 1 for IBR Glossary Terms ended on 04/08. IBR definition passed (67%), and IBR Unit definition did not pass (61%). NERC and DT will determine next steps and DT will review industry comments. This project is classified as medium except for the IBR definitions, which are high priority.
Deliverable | MOD-026, MOD-027
Deadline |  |  |  |  | N/A | Months to deadline
Priority in RSDP, click to see applicable Footnote | Footnote 11, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Reserved for Future Use | 0
Reserved for Future Use
Number of Directives | 0 | N/A
Reserved for Future Use |  | N/A
Reserved for Future Use | N/A
Developer | Chris Larson
PMOS Liaison | Sarah Habriga (primary), Ellese Murphy (secondary)
Affected Standards | 2 | MOD-026-1 and MOD-027-1
Last Updated | 2024-04-10
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Pandemic | 90 | 1
AS2 - Additional SAR 2 | [5 empty] | Pandemic | 90 | 2
QR - Quality Review | [5 empty] | Highly Technical | 90 | 3
SP1 - SAR/PR/WP Posting 1 | 2020-12-16 | 2021-01-15 | 2020-12-16 | 2021-01-15 | 0 | Research Required | 180 | 4
SP2 - SAR Revise/Response |  |  | 2021-03-16 | 2021-05-15 |  | SAR - Revised/Additional Posting | 60 | 5
SDT - Dev Time | 2021-03-16 | 2021-07-14 | 2021-07-14 | 2021-11-11 | 120 | Additional Comment/Ballot | 60 | 5
CP1 - Comment Period 1 | [5 empty] | Additional Comment/Ballot | 60 | 6
CP2 - Comment Period 2 | [5 empty] | Additional Comment/Ballot | 60 | 7
CIB - Com/Ballot 1 (Initial) | 2022-05-30 | 2022-07-06 | 2021-11-11 | 2021-12-26 | -200 | Highly Technical | 90 | 8
CAB - Com/Add Ballot 2 | 2022-11-21 | 2023-01-18 | 2022-02-24 | 2022-04-10 | -270 | Highly Technical | 90 | 9
CAB - Com/Add Ballot 3 | 2023-06-07 | 2023-07-22 | 2022-06-09 | 2022-07-24 | -363 | N/A |  | 10
CAB - Com/Add Ballot 4 | 2023-11-16 | 2024-01-09 | 2022-09-22 | 2022-11-06 | -420 | N/A | 0 | 11
CAB - Com/Add Ballot 4 | 2024-02-23 | 2024-04-08 | 2023-01-05 | 2023-02-19 | -414
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2024-12-01 | 2024-12-11 | 2022-05-10 | 2022-05-20 | -936 | N/A | 0 | 13
PTB - Present to BOT | [5 empty] | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
0 | [5 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: | 0 | 0 | 0 | 0 | -66 | Calculated CF Date: | 2024-10-06
PTS Change Control
Reason for Update | Date | Notes | 0 | 0 | 0 | 0 | 0
SC Action | 2020-09-24 | SC authorized SAR posting and solicitation of SAR DT.
NERC Standards | 2021-03-15 | SAR DT will be presented at the March 17 SC meeting
NERC Standards | 2021-10-18 | Updated project baseline for March 2022 initial posting
NERC Standards | 2022-02-14 | Updated initial posting to April 2022
NERC Standards | 2022-05-10 | Updated initial posting to May 2022
NERC Standards | 2022-09-14 | Updated additional posting to November 2022
NERC Standards | 2023-03-17 | Updated additional posting #2 date to June 2023 for additional outreach for EMT models, Protection Settings
NERC Standards | 2023-10-12 | Informal Comment period for IBR and Power Electronic Device ending 10/24/23
NERC Standards | 2024-01-08 | Added Initial Ballot for IBR Definitions (Add Ballot 4)
Note on D22: Enter SC SAR date here
Note on F37: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2021-01
Project | 2021-01 | [5 empty] | Home
Project Name | Modifications to MOD-025 and PRC-019
Status | SDT Development
Comments | DT is conducting outreach for PRC-019, meeting with DT leadership & NERC Standards Developer once monthly PRC-019 requirement language has a dependency on the proposed IBR definitions, which will have an additional ballot ending April 8 (Project 2020-06). MOD-025 sub-team has a new draft ready for Informal Comment. DT must assess the impact of FERC Order No. 901 and associated NERC Work Plan.
Deliverable | PRC-019, MOD-025
Deadline |  |  |  |  | N/A | Months to deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | N/A
Reserved for Future Use |  | N/A
Reserved for Future Use | N/A
Developer | Chris Larson
PMOS Liaison | Kirk Rosener (primary), Ruida Shu (backup)
Affected Standards | 2 | MOD-025, PRC-019
Last Updated | 2024-04-15
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Pandemic | 90 | 1
AS2 - Additional SAR 2 | [5 empty] | Pandemic | 90 | 2
QR - Quality Review | [5 empty] | Research Required | 180 | 3
SP1 - SAR/PR/WP Posting 1 | 2021-03-04 | 2021-04-02 | 2021-03-04 | 2021-04-03 | 0 | SAR - Revised/Additional Posting | 60 | 4
SP2 - SAR Revise/Response |  |  | 2021-06-02 | 2021-08-01 |  | N/A |  | 5
SDT - Dev Time | 2021-12-15 | 2022-06-01 | 2021-09-30 | 2022-01-28 | -76 | Additional Outreach | 30 | 5
CP1 - Comment Period 1 | [5 empty] | Additional Comment/Ballot | 60 | 6
CP2 - Comment Period 2 | [5 empty] | Additional Comment/Ballot | 60 | 7
CIB - Com/Ballot 1 (Initial) | 2022-09-29 | 2022-11-13 | 2022-01-28 | 2022-03-14 | -244 | RSDP Priority Decrease | 60 | 8
CAB - Com/Add Ballot 2 | 2023-04-25 | 2023-06-09 | 2022-05-13 | 2022-06-27 | -347 | Intentional Hold/Delay | 30 | 9
CAB - Com/Add Ballot 3 | 2024-07-01 | 2024-08-15 |  |  |  | Intentional Hold/Delay | 30 | 10
CAB - Com/Add Ballot 4 | [5 empty] | Cross-Coordination (Finish-Start) | 90 | 11
CAB - Com/Add Ballot 5 | [7 empty] | 12
FB - Final Ballot | 2024-09-14 | 2024-09-24 | 2022-07-27 | 2022-08-06 | -780 | N/A | 0 | 13
PTB - Present to BOT | [5 empty] | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
0 | [5 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: | 0 | 0 | 0 | 0 | 0 | Calculated CF Date: | 2024-09-24
PTS Change Control
Reason for Update | Date | Notes | 0 | 0 | 0 | 0 | 0
SC Action | 2021-01-20 | SC authorized SAR posting and solicitation of SAR DT.
SC Action | 2021-12-15 | SC accepted revised SARs, authorized revisions, and appointed SAR DT as SDT
Response to Comment | 2023-03-17 | Updated date for Additional Ballot to April 2023; Response to Comment for PRC-019 and MOD-025
Update timeline | 2024-03-12 | Update timeline based on IBE Definitions posting and FERC Order 901
Note on D22: Enter SC SAR date here
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2021-02
Project | 2021-02 | [5 empty] | Home
Project Name | Modifications to VAR-002-4.1
Status | SDT Development
Comments | This project is on posting hold until after July 2024. The DT will continue to conduct DT meetings, but at a slower pace. An April 12, 2024 DT meeting is scheduled.
Deliverable | VAR-002
Deadline |  |  |  |  | N/A | Months to deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | N/A
Reserved for Future Use |  | N/A
Reserved for Future Use | N/A
Developer | Laura Anderson
PMOS Liaison | Joseph Gatten (Primary), Anthony Westenkirchner (Backup)
Affected Standards | 1 | VAR-002-4.1
Last Updated | 2024-04-11
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | 2022-04-06 | 2022-05-04 |  |  |  | Pandemic | 90 | 1
AS2 - Additional SAR 2 | 2022-05-02 | 2022-05-31 |  |  |  | SAR - Revised/Additional Posting | 60 | 2
QR - Quality Review | [5 empty] | N/A | 0 | 3
SP1 - SAR/PR/WP Posting 1 |  |  | 2022-04-06 | 2022-05-06 | 0 | N/A | 0 | 4
SP2 - SAR Revise/Response |  |  | 2022-07-05 | 2022-09-03 |  | N/A |  | 5
SDT - Dev Time |  |  | 2022-11-02 | 2023-01-01 | 0 | N/A | 0 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2022-12-05 | 2023-01-13 | 2022-10-31 | 2022-12-14 | -35 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2023-05-10 | 2023-06-23 | 2023-05-10 | 2023-06-23 | 0 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | 2023-09-22 | 2023-11-06 |  |  |  | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2023-12-17 | 2023-12-26 | 2023-07-23 | 2023-08-02 | -147 | N/A | 0 | 13
PTB - Present to BOT | [5 empty] | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
0 | [5 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: | 0 | 0 | 0 | 0 | 4 | Calculated CF Date: | 2023-12-30
PTS Change Control
Reason for Update | Date | Notes | 0 | 0 | 0 | 0 | 0
SC Action | 2021-01-20 | SC authorized SAR posting and solicitation of SAR DT.
SAR - Revised/Additional Posting | 2022-04-01 | SAR posting was extended
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2021-03
Project | 2021-03 | [5 empty] | Home
Project Name | CIP-002 Transmission Owner Control Centers (TOCC)
Status | SDT Development
Comments | Details on Draft: Current/Anticipate Posting: A 45 Day Formal Comment period and additional ballot scheduled for April 2 – May 17, 2024. Webinar scheduled for April 26. Other: This project is assigned 5 SARS and is currently focusing on the TOCC SAR.
Deliverable | CIP-002
Deadline |  |  |  |  | N/A | Months to deadline
Priority in RSDP, click to see applicable Footnote | Footnote 11, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | N/A
Reserved for Future Use |  | N/A
Reserved for Future Use | N/A
Developer | Dominique Love
PMOS Liaison | Ellese Murphy (Primary), Darrel Grumman (Backup)
Affected Standards | 1 | CIP-002
Last Updated | 2024-04-04
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Pandemic | 90 | 1
AS2 - Additional SAR 2 | [5 empty] | Research Required | 180 | 2
QR - Quality Review | [5 empty] | Field Test | 365 | 3
SP1 - SAR/PR/WP Posting 1 | 2021-03-22 | 2021-04-27 | 2021-03-22 | 2021-04-21 | 0 | SAR - Revised/Additional Posting | 60 | 4
SP2 - SAR Revise/Response |  |  | 2021-06-20 | 2021-08-19 |  | N/A |  | 5
SDT - Dev Time | 2021-06-26 | 2021-08-25 | 2021-10-18 | 2021-12-17 | 114 | Change in Developer | 30 | 5
CP1 - Comment Period 1 | 2023-06-13 | 2023-07-13 |  |  |  | SAR - Revised/Additional Posting | 60 | 6
CP2 - Comment Period 2 | [5 empty] | SAR - Supplemental | 60 | 7
CIB - Com/Ballot 1 (Initial) | 2023-10-31 | 2023-06-01 | 2021-12-17 | 2022-01-31 | -683 | Highly Technical | 90 | 8
CAB - Com/Add Ballot 2 | 2024-04-02 | 2023-09-04 | 2022-04-01 | 2022-05-16 | -732 | Additional Comment/Ballot | 60 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2024-12-01 | 2024-12-11 | 2022-06-15 | 2022-06-25 | -900 | N/A | 0 | 13
PTB - Present to BOT | 2024-12-13 | 2024-12-13 |  |  |  | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
0 | [5 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: | 0 | 0 | 0 | 0 | 95 | Calculated CF Date: | 2025-03-16 | 0
PTS Change Control
Reason for Update | Date | Notes | 0 | 0 | 0 | 0 | 0
SC Action | 2021-03-22 | SC authorized SAR posting and solicitation of the SAR DT.
SC Action | 2023-09-20 | SC agenda to ask for authorization to post for a Formal Comment Period and Initial Ballot.
Note on D22: Enter SC SAR date here
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2021-04 (hidden)
Project | 2021-04 | [5 empty] | Home
Project Name | Modifications to PRC-002-2
Status | Filed
Comments | Phase one was completed by the SDT. It got approved by the BOT on February 16, 2023. The petition will be sent to FERC for approval on March 10, 2023.
Deliverable | PRC-002-4
Deadline | 2022-12-31 |  |  |  | N/A | Reserved for Future Use
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | N/A
Reserved for Future Use |  | N/A
Reserved for Future Use | N/A
Developer | Ben Wu
PMOS Liaison | Michael Brytowski (Primary), Charles Yeung (Backup)
Affected Standards | 1 | PRC-002-2
Last Updated | 2023-03-28
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Additional Outreach | 30 | 1
AS2 - Additional SAR 2 | [5 empty] | Pandemic | 90 | 2
QR - Quality Review | [5 empty] | Intentional Hold/Delay | 30 | 3
SP1 - SAR/PR/WP Posting 1 | 2021-06-14 | 2021-07-13 | 2021-06-14 | 2021-07-14 | 0 | N/A | 0 | 4
SDT - Dev Time | 2021-09-11 | 2021-11-10 | 2021-09-12 | 2021-11-11 | 1 | N/A | 0 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2022-06-09 | 2022-07-25 | 2021-11-11 | 2021-12-26 | -210 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2022-09-23 | 2022-11-07 | 2022-02-24 | 2022-04-10 | -211 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2022-12-07 | 2022-12-16 | 2022-05-10 | 2022-05-20 | -211 | N/A | 0 | 13
PTB - Present to BOT | 2023-02-16 | 2023-02-16 |  |  |  | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
0 | [5 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: | 0 | 0 | 0 | 0 | -60 | Calculated CF Date: | 2022-10-17
PTS Change Control
Reason for Update | Date | Notes | 0 | 0 | 0 | 0 | 0
SC Action | 2021-05-20 | SC authorized two SAR postings and solicitation of SAR DT.
Additional Outreach | 2021-06-14 | Additional outreach to solicit more SAR DT members
Intentional Delay | 2021-06-14 | SAR posting was delayed due to pandemic work loads - Will not be reflected in complexity factor calculation due to SAR posting date.
Intentional Delay | 2021-12-15 | Postponed SC action to appoint the Project 2021-04 SAR Drafting Team (DT) as the Project 2021-04 Standard Drafting Team (SDT) due to responses to comments were not ready
Note on D22: Enter SC SAR date here
Note on F35: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2021-04b
Project | 2021-04b | [5 empty] | Home
Project Name | Modifications to PRC-002-2
Status | SDT Development
Comments | This is a high priority project. The SDT met in person at Georgia Power in Atlanta on February 21 and 22, 2024 to finalize the documents (Standard and associated Implementation Plan, as well as the Technical Rationale document). The final draft were sent out for quality review on March 1, 2024. The SDT will meet on March 11, 2024 to review comments received from the Quality Review Team. The second posting is scheduled to start on March 18, 2024 with 25 day posting.
Deliverable | PRC-002-5, PRC-028-1
Deadline | 2024-11-04 |  |  |  | N/A | Reserved for Future Use
Priority in RSDP, click to see applicable Footnote | Footnote 11, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | N/A
Reserved for Future Use |  | N/A
Reserved for Future Use | N/A
Developer | Ben Wu
PMOS Liaison | Michael Brytowski (Primary), Charles Yeung (Backup)
Affected Standards | 2 | PRC-002-2; PRC-028-1
Last Updated | 2024-04-11
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Additional Outreach | 30 | 1
AS2 - Additional SAR 2 | [5 empty] | Pandemic | 90 | 2
QR - Quality Review | [5 empty] | Intentional Hold/Delay | 30 | 3
SP1 - SAR/PR/WP Posting 1 | 2021-06-14 | 2021-07-13 | 2021-06-14 | 2021-07-14 | 0 | N/A | 0 | 4
SP2 - SAR Revise/Response |  |  | 2021-09-12 | 2021-11-11 |  | N/A |  | 5
SDT - Dev Time | 2021-09-11 | 2022-01-09 | 2022-01-10 | 2022-05-10 | 121 | N/A | 0 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2023-07-31 | 2023-09-15 | 2022-05-10 | 2022-06-24 | -447 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2024-03-18 | 2024-04-12 | 2022-08-23 | 2022-10-07 | -573 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2024-08-01 | 2024-08-10 | 2022-11-06 | 2022-11-16 | -634 | N/A | 0 | 13
PTB - Present to BOT | 2024-10-15 | 2024-10-15 |  |  |  | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
0 | [5 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: | 0 | 0 | 0 | 0 | -483 | Calculated CF Date: | 2023-04-15
PTS Change Control
Reason for Update | Date | Notes | 0 | 0 | 0 | 0 | 0
SC Action | 2021-05-20 | SC authorized two SAR postings and solicitation of SAR DT.
Additional Outreach | 2021-06-14 | Additional outreach to solicit more SAR DT members
Intentional Delay | 2021-06-14 | SAR posting was delayed due to pandemic work loads - Will not be reflected in complexity factor calculation due to SAR posting date.
Intentional Delay | 2021-12-15 | Postponed SC action to appoint the Project 2021-04 SAR Drafting Team (DT) as the Project 2021-04 Standard Drafting Team (SDT) due to responses to comments were not ready
Note on D22: Enter SC SAR date here
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2021-05 (hidden)
Project | 2021-05 | [5 empty] | Home
Project Name | Modifications to PRC-023-4
Status | Filed
Comments | The proposed Standard passed final ballot and approved by the Board of Trustees on February 16, 2023. The petition was sent to FERC for adoption.
Deliverable | PRC-023-6
Deadline | 2022-12-31 |  |  |  | N/A | Months to deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | N/A
Reserved for Future Use | N/A | N/A
Reserved for Future Use
Developer | Ben Wu
PMOS Liaison | Anthony Westenkirchner (primary), Claudine Fritz (secondary)
Affected Standards | 1 | PRC-023-4
Last Updated | 2023-04-13
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Additional Outreach | 30 | 1
AS2 - Additional SAR 2 | [5 empty] | Pandemic | 90 | 2
QR - Quality Review | [5 empty] | N/A | 0 | 3
SP1 - SAR/PR/WP Posting 1 | 2021-06-29 | 2021-07-28 | 2021-06-29 | 2021-07-29 | 0 | N/A | 0 | 4
SDT - Dev Time | 2021-09-26 | 2021-11-25 | 2021-09-27 | 2021-11-26 | 1 | N/A | 0 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2022-09-15 | 2022-10-30 | 2021-11-26 | 2022-01-10 | -293 | N/A | 0 | 8
CAB - Com/Add Ballot 2 |  |  | 2022-03-11 | 2022-04-25 | 0 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2023-01-12 | 2023-01-24 | 2022-05-25 | 2022-06-04 | -232 | N/A | 0 | 13
PTB - Present to BOT | 2023-02-16 | 2023-02-16 |  |  |  | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
0 | [5 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | -114 | Calculated CF Date: | 2022-10-02
PTS Change Control
Reason for Update | Date | Notes | 0 | 0 | 0 | 0 | 0
SC Action | 2021-01-23 | SC authorized SAR posting and solicitation of SAR DT.
Additional Outreach | 2021-06-29 | Additional outreach to solicit more SAR DT members
Intentional Delay | 2021-06-29 | SAR posting was delayed due to pandemic work loads - Will not be reflected in complexity factor calculation due to SAR posting date.
Note on F35: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2021-06 (hidden)
Project | 2021-06 | [5 empty] | Home
Project Name | Modifications to IRO-010 and TOP-003
Status | Archived
Comments | IRO-010-5 passed final ballot on 7/21 with 76% & TOP-003-6 passed with 75%. The NERC BOT at their 8/17 meeting is set to adopt the standards and move forward to FERC.
Deliverable | TBD
Deadline |  |  |  |  | N/A | Months to deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Reserved for Future Use | 0
Reserved for Future Use
Number of Directives | 0 | N/A
Reserved for Future Use |  | N/A
Reserved for Future Use
Developer | Josh Blume
PMOS Liaison | Michael Brytowski (Primary), Charles Yeung (Backup)
Affected Standards | 2 | IRO-010; TOP-003
Last Updated | 2023-09-07
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Pandemic | 90 | 1
AS2 - Additional SAR 2 | 2022-01-11 | 2022-02-10 |  |  |  | SAR - Revised/Additional Posting | 60 | 2
QR - Quality Review | [5 empty] | Posting Conflict | 7 | 3
SP1 - SAR/PR/WP Posting 1 | 2021-07-08 | 2021-08-07 | 2021-07-08 | 2021-08-07 | 0 | Schedule Too Conservative | -90 | 4
SDT - Dev Time | 2021-10-06 | 2022-02-03 | 2021-10-06 | 2022-02-03 | 0 | Additional Comment/Ballot | 60 | 5
CP1 - Comment Period 1 | [5 empty] | Posting Conflict | 7 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2022-10-25 | 2022-12-09 | 2022-02-03 | 2022-03-20 | -264 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2023-05-05 | 2023-06-20 |  |  |  | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2023-07-16 | 2023-07-26 | 2023-03-31 | 2023-04-10 | -107 | N/A | 0 | 13
PTB - Present to BOT | 2023-08-10 |  |  |  |  | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
0 | [5 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | 27 | Calculated CF Date: | 2023-08-22
PTS Change Control
Reason for Update | Date | Notes | 0 | 0 | 0 | 0 | 0
SC Action | 2021-01-20 | SC authorized SAR posting and solicitation of SAR DT.
Intentional Delay | 2021-07-08 | SAR posting was delayed due to pandemic work loads - Will not be reflected in complexity factor calculation due to SAR posting date.
Note on D22: Enter SC SAR date here
Note on F35: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2021-07 (hidden)
Project | 2021-07 | [5 empty] | Home
Project Name | Extreme Cold Weather Grid Operations, Preparedness, and Coordination
Status | Filed
Comments | Phase 1 of the project passed final ballot 9/23 – 9/30. The standard we adopted during the October 26th board meeting. The team has started phase 2 drafting work. An Initial ballot for phase 2 is expected in January/February of 2023.
Deliverable | TBD
Deadline | 2022-11-01 |  |  |  | -17 | Months to deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 1 | N/A
Reserved for Future Use |  | N/A
Reserved for Future Use | N/A
Developer | Alison Oswald
PMOS Liaison | Michael Brytowski (Primary), Kirk Rosener (Backup)
Affected Standards | 2 | EOP-011-3, EOP-012-1
Last Updated | 2024-03-12
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Pandemic | 90 | 1
AS2 - Additional SAR 2 | [5 empty] | N/A | 0 | 2
QR - Quality Review | [5 empty] | N/A | 0 | 3
SP1 - SAR/PR/WP Posting 1 | 2021-11-22 | 2021-12-21 | 2021-11-22 | 2021-12-22 | 0 | N/A | 0 | 4
SDT - Dev Time | 2022-02-19 | 2022-04-20 | 2022-02-20 | 2022-07-20 | 1 | N/A | 0 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2022-05-25 | 2022-06-23 | 2022-07-20 | 2022-09-03 | 56 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2022-08-01 | 2022-08-31 | 2022-11-02 | 2022-12-17 | 93 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2022-09-23 | 2022-09-30 | 2023-01-16 | 2023-01-26 | 115 | N/A | 0 | 13
PTB - Present to BOT | 2022-10-26 |  |  |  |  | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
0 | [5 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | 208 | Calculated CF Date: | 2023-04-26
PTS Change Control
Reason for Update | Date | Notes | 0 | 0 | 0 | 0 | 0
SC Action | 2021-11-17 | SC Authorized SAR posting and solicitation of SAR DT.
Note on F35: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2021-07bi (hidden)
Project | 2021-07b | [5 empty] | Home
Project Name | Extreme Cold Weather Grid Operations, Preparedness, and Coordination
Status | Filed
Comments | DT working to address industry comments around “good utility practice” and the staggered implementation of CAPs in R8. Current/Anticipate Posting: Additional comment and ballot in Jan 2024 with Final Ballot in Feb 2024. Note that the ballot and formal commenting period are anticipated to be reduced/condensed to a 10-20 day timeframe. Other: FERC order deadline of February 16, 2024.
Deliverable | EOP-011, TOP-002
Deadline | 2023-11-01 |  |  |  | -5 | Months to deadline
Priority in RSDP, click to see applicable Footnote | Footnote 11, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 1 | N/A
Reserved for Future Use |  | N/A
Reserved for Future Use | N/A
Developer | Alison Oswald
PMOS Liaison | Michael Brytowski (Primary), Kirk Rosener (Backup)
Affected Standards | 2 | EOP-011, TOP-002
Last Updated | 2024-03-12
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Pandemic | 90 | 1
AS2 - Additional SAR 2 | [5 empty] | Cross-Coordination (Finish-Start) | 90 | 2
QR - Quality Review | [5 empty] | Cross-Coordination (Finish-Start) | 90 | 3
SP1 - SAR/PR/WP Posting 1 | 2021-11-22 | 2021-12-21 | 2021-11-22 | 2021-12-22 | 0 | N/A | 0 | 4
SDT - Dev Time | 2022-02-19 | 2022-04-20 | 2022-02-20 | 2022-07-20 | 1 | N/A | 0 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2023-02-28 | 2023-04-13 | 2022-07-20 | 2022-09-03 | -223 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2023-08-24 | 2023-09-12 | 2022-11-02 | 2022-12-17 | -295 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2023-09-29 | 2023-10-06 | 2023-01-16 | 2023-01-26 | -256 | N/A | 0 | 13
PTB - Present to BOT | 2023-10-23 | 2023-10-23 |  |  |  | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
0 | [5 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | 17 | Calculated CF Date: | 2023-10-23
PTS Change Control
Reason for Update | Date | Notes | 0 | 0 | 0 | 0 | 0
SC Action | 2021-11-17 | SC Authorized SAR posting and solicitation of SAR DT.
Note on F35: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2021-07bii (hidden)
Project | 2021-07b | [5 empty] | Home
Project Name | Extreme Cold Weather Grid Operations, Preparedness, and Coordination
Status | Filed
Comments | An initial ballot for EOP-012 completed in July and did not pass. The team will focus on EOP-012 starting in October once final ballot for the other two standards are completed.
Deliverable | EOP-012
Deadline | 2024-02-16 |  |  |  | -1 | Months to deadline
Priority in RSDP, click to see applicable Footnote | Footnote 11, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 1 | N/A
Reserved for Future Use |  | N/A
Reserved for Future Use | N/A
Developer | Alison Oswald
PMOS Liaison | Michael Brytowski (Primary), Kirk Rosener (Backup)
Affected Standards | 1 | EOP-012-1
Last Updated | 2024-03-12
0
0
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Pandemic | 90 | 1
AS2 - Additional SAR 2 | [5 empty] | Cross-Coordination (Finish-Start) | 90 | 2
QR - Quality Review | [5 empty] | Cross-Coordination (Finish-Start) | 90 | 3
SP1 - SAR/PR/WP Posting 1 | 2021-11-22 | 2021-12-21 | 2021-11-22 | 2021-12-22 | 0 | Directive Added to Scope | 60 | 4
SDT - Dev Time | 2022-02-19 | 2022-04-20 | 2022-02-20 | 2022-05-21 | 1 | Cross-Coordination (Finish-Start) | 90 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2023-06-05 | 2023-07-20 | 2022-05-21 | 2022-07-05 | -380 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2023-10-27 | 2023-11-30 | 2022-09-03 | 2022-10-18 | -419 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | 2024-01-10 | 2024-01-22 |  |  |  | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2024-02-05 | 2024-02-09 | 2022-11-17 | 2022-11-27 | -445 | N/A | 0 | 13
PTB - Present to BOT | [5 empty] | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
0 | [5 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | -19 | Calculated CF Date: | 2024-01-21
PTS Change Control
Reason for Update | Date | Notes | 0 | 0 | 0 | 0 | 0
SC Action | 2021-11-17 | SC Authorized SAR posting and solicitation of SAR DT.
Updated Complexity Factors | 2024-03-12 | Added CFs and updated timelines
Note on C28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Waiver
Note on F35: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2021-08
Project | 2021-08 | [5 empty] | Home
Project Name | Modifications to FAC-008-5
Status | SDT Development
Comments | The final draft of the documents were approved for initial posting at the SC's August meeting (August 23, 2023). The initial posting started on September 5, 2023 and closed on October 19, 2023. The SDT will meet in person on November 6 & 7, 2023 to review the results and comments received from the industry. The second posting will probably take place in January, 2024.
Deliverable | FAC-008-6
Deadline | 2023-08-31 |  |  |  | -7 | Months to deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | Enter # in column B and description here. This value is 1 of 2 items that calculate the project baseline. If zero, delete this text.
Reserved for Future Use | N/A
Reserved for Future Use | N/A
Developer | Al McMeekin
PMOS Liaison | Sarah Habriga (primary), Jennifer Richardson (secondary)
Affected Standards | 1 | FAC-008-5
Last Updated | 2024-04-11
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | N/A | 0 | 1
AS2 - Additional SAR 2 | [5 empty] | N/A | 0 | 2
QR - Quality Review | [5 empty] | N/A | 0 | 3
SP1 - SAR/PR/WP Posting 1 | 2021-12-09 | 2022-01-27 | 2021-12-09 | 2022-01-27 | 0 | N/A | 0 | 4
SP2 - SAR Revise/Response |  |  | 2022-03-28 | 2022-05-27 |  | N/A | 0 | 5
SDT - Dev Time |  |  | 2022-07-26 | 2022-09-24 | 0 | N/A | 0 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2023-09-05 | 2023-10-19 | 2022-09-24 | 2022-11-08 | -346 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2024-07-01 | 2024-08-14 |  |  |  | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2024-09-30 | 2024-10-10 | 2023-11-30 | 2023-12-10 | -305 | N/A | 0 | 13
PTB - Present to BOT | [5 empty] | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
[6 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | -305 | Calculated CF Date: | 2023-12-10
PTS Change Control
Reason for Update | Date | Notes
SC Action | 2021-11-17 | SC authorized SAR posting and solicitation of the SAR DT.
Formulas:
Calculated Start = [Calculated End, row above]+60
Calculated Start = +[Calculated End, row above]+60
Calculated End = [Calculated Start]+60
Calculated End = +[Calculated Start]+(B9*30)+(B14*60)
Projected or Actual End = +[Projected or Actual Start]+10
Time Impact = D22+(E32-D22)+SUM(H19:[Time Impact, row above])
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2022-01 (hidden)
Project | 2022-01 | [5 empty] | Home
Project Name | Reporting ACE Definition and Associated Terms
Status | Pending Board Adoption
Comments | Although this project is now lower priority, the preparation of responses to the comments received in the last balloting has been completed by the team. Team was expecting final balloting in December and going to the BOT in February but has not been posted yet. (the project status spreadsheet dates need updating for planned final ballot)
Deliverable | ACE & IIM Definitions
Deadline | 2023-08-09 |  |  |  | -8 | Months to deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | Enter # in column B and description here. This value is 1 of 2 items that calculate the project baseline. If zero, delete this text.
Reserved for Future Use | N/A
Reserved for Future Use | N/A
Developer | Josh Blume
PMOS Liaison | Claudine Fritz (Primary), Ruida Shu (Backup)
Affected Standards | 1 | Enter number of Affected Standards in column B and the Standard here (e.g. TOP-001-4). This value is 2 of 2 items that calculate the project baseline.
Last Updated | 2023-12-22
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Pandemic | 90 | 1
AS2 - Additional SAR 2 | [5 empty] | Pandemic | 90 | 2
QR - Quality Review | [5 empty] | Intentional Hold/Delay | 30 | 3
SP1 - SAR/PR/WP Posting 1 | 2022-02-09 | 2022-03-10 | 2022-02-09 | 2022-03-10 | 0 | Posting Conflict | 7 | 4
SDT - Dev Time | 2022-05-09 | 2022-07-08 | 2022-05-09 | 2022-07-08 | 0 | Posting Conflict | 7 | 5
CP1 - Comment Period 1 | [5 empty] | Posting Conflict | 7 | 6
CP2 - Comment Period 2 | [5 empty] | Intentional Hold/Delay | 30 | 7
CIB - Com/Ballot 1 (Initial) | 2023-01-31 | 2023-03-16 | 2022-07-08 | 2022-08-22 | -207 | Intentional Hold/Delay | 30 | 8
CAB - Com/Add Ballot 2 | 2023-09-16 | 2023-10-31 | 2022-10-21 | 2022-12-05 | -330 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2023-12-10 | 2023-12-20 | 2023-01-04 | 2023-01-14 | -340 | N/A | 0 | 13
PTB - Present to BOT | 2024-02-14 |  |  |  |  | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
[6 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | -49 | Calculated CF Date: | 2023-11-01
PTS Change Control
Reason for Update | Date | Notes
SC Action |  | SC authorized SAR posting and solicitation of the SAR DT.
Intentional Hold | 2023-02-23 | Devloper had another project conflict
Posting conflict | 2023-02-23 | Lower priority posting to Cold Weather
Pandemic | 2022-02-23 | Pandemic impact
Intentional hold by sc | 2023-06-01 | SC held protect untill next sc meeting for posting
2nd intial posting at
Formulas:
Projected or Actual Start = +[Calculated Start]
Projected or Actual End = +[Calculated End]
Projected or Actual End = +[Projected or Actual Start]+44
Calculated Start = +[Calculated End, row above]+60
Calculated End = +[Calculated Start]+(B9*30)+(B14*60)
Calculated End = +[Calculated Start]+45
Time Impact = D22+(E31-D22)+SUM(H19:[Time Impact, row above])
Note on F35: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2022-02
Project | 2022-02 | [5 empty] | Home
Project Name | Modifications to TPL-001-5.1 and MOD-032-1
Status | SDT Development
Comments | The SDT had a meeting on February 12, 2024. The team finished responding to all of the comments received from the second posting. They also reviewed the Standard (MOD-032) and associated Implementation Plan, as well as the Technical Rationale document. This project will not be posted until July, 2024. The SDT has another meeting scheduled for February 26, 2024. The team is working on the outreach to collect feedback before next posting.
Deliverable | MOD-032, TPL-001
Deadline | 2025-12-31 |  |  |  | 20 | Months to deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | Enter # in column B and description here. This value is 1 of 2 items that calculate the project baseline. If zero, delete this text.
Reserved for Future Use | N/A
Reserved for Future Use | N/A
Developer | Ben Wu
PMOS Liaison | Ellese Murphy (Primary), Terri Pyle (Backup)
Affected Standards | 2 | TPL-001-5.1; MOD-032-1
Last Updated | 2024-04-11
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Pandemic | 90 | 1
AS2 - Additional SAR 2 | [5 empty] | N/A | 0 | 2
QR - Quality Review | [5 empty] | N/A | 0 | 3
SP1 - SAR/PR/WP Posting 1 | 2022-02-02 | 2022-03-02 | 2022-02-02 | 2022-03-02 | 0 | N/A | 0 | 4
SP2 - SAR Revise/Response |  |  | 2022-05-01 | 2022-06-30 |  | N/A |  | 5
SDT - Dev Time | 2022-08-29 | 2022-12-27 | 2022-08-29 | 2022-12-27 | 0 | N/A | 0 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2023-05-31 | 2023-07-15 | 2022-12-27 | 2023-02-10 | -155 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2023-10-06 | 2023-11-20 | 2023-04-11 | 2023-05-26 | -178 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | 2024-07-10 | 2024-08-24 |  |  |  | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2024-12-10 | 2024-12-10 | 2023-06-25 | 2023-07-05 | -534 | N/A | 0 | 13
PTB - Present to BOT | [5 empty] | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
[6 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | -434 | Calculated CF Date: | 2023-10-03
PTS Change Control
Reason for Update | Date | Notes
SC Action |  | SC authorized SAR posting and solicitation of the SAR DT.
Formulas:
Calculated Start = [Calculated End, row above]+60
Calculated Start = +[Calculated End, row above]+60
Calculated End = [Calculated Start]+60
Calculated End = +[Calculated Start]+(B9*30)+(B14*60)
Projected or Actual Start = +[Calculated Start]
Projected or Actual End = +[Calculated End]
Time Impact = D22+(E32-D22)+SUM(H19:[Time Impact, row above])
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2022-03
Project | 2022-03 | [5 empty] | Home
Project Name | Energy Assurance with Energy-Constrained Resources
Status | Responding to Comment
Comments | Details on Draft: BAL-007-1 standard is a new standard that is based on the Operations and Operations planning horizon SAR. It looks to address energy reliability assessments for both seasonal and near-term time horizons. Current/Anticipate Posting: BAL-007 Draft #1 concluded initial b on March 11, 2024. Consideration of Comment in progress.
Deliverable | TBD
Deadline | 2023-12-31 |  |  |  | -3 | Months to deadline
Priority in RSDP, click to see applicable Footnote | Footnote 11, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | Enter # in column B and description here. This value is 1 of 2 items that calculate the project baseline. If zero, delete this text.
Reserved for Future Use | N/A
Reserved for Future Use | N/A
Developer | Jordan Mallory; Dominique Love
PMOS Liaison | Joe Gatten (primary), Terri Pyle (backup)
Affected Standards | 1 | Enter number of Affected Standards in column B and the Standard here (e.g. TOP-001-4). This value is 2 of 2 items that calculate the project baseline.
Last Updated | 2024-04-04
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Additional Comment/Ballot | 60 | 1
AS2 - Additional SAR 2 | [5 empty] | Additional Outreach | 30 | 2
QR - Quality Review | [5 empty] | Additional Outreach | 30 | 3
SP1 - SAR/PR/WP Posting 1 | 2022-06-22 | 2022-06-22 | 2022-06-22 | 2022-07-22 | 0 | Standard Developer Change | 30 | 4
SP2 - SAR Revise/Response |  |  | 2022-09-20 | 2022-11-19 |  | Standard Developer Change | 30 | 5
SDT - Dev Time | 2023-02-01 | 2023-08-30 | 2023-01-18 | 2023-03-19 | -14 | Highly Technical | 90 | 5
CP1 - Comment Period 1 | 2023-09-13 | 2023-10-08 |  |  |  | Highly Technical | 90 | 6
CP2 - Comment Period 2 | [5 empty] | Additional Comment/Ballot | 60 | 7
CIB - Com/Ballot 1 (Initial) | 2024-01-25 | 2024-03-11 | 2023-03-19 | 2023-05-03 | -312 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2023-07-02 |  | 2023-07-02 | 2023-08-16 | 0 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2024-12-01 | 2024-12-11 | 2023-09-15 | 2023-09-25 | -443 | N/A | 0 | 13
PTB - Present to BOT | 2024-12-13 |  |  |  |  | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
[6 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | -23 | Calculated CF Date: | 2024-11-18
PTS Change Control
Reason for Update | Date | Notes
SC Action |  | SC authorized SAR posting and solicitation of the SAR DT.
Informal Comment Period | 2023-09-01 | 16 day comment period to solicit feedback on proposed TOP Standard
Formal Comment Period | 2024-01-25 | 45 day formal comment period and initial ballot
Updated timeline | 2024-04-04 | Updated timeline, added complexity factors
Formulas:
Calculated End = +[Calculated Start]+30
Calculated End = [Calculated Start]+60
Calculated Start = [Calculated End, row above]+60
Calculated Start = +[Calculated End, row above]+60
Projected or Actual End = [Projected or Actual Start]+25
Projected or Actual Start = +[Calculated Start]
Time Impact = D22+(E32-D22)+SUM(H19:[Time Impact, row above])
Note on D22: Enter SC SAR date here
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2022-04
Project | 2022-04 | [5 empty] | Home
Project Name | EMT Models in NERC MOD, TPL, and FAC Standards
Status | SDT Development
Comments | Although this is a low priority project at this point, the team is continuing to meet about every two weeks. As the team is looking at revising several standards, the DT is focusing on drafting revisions to FAC-002. Once complete, an informal comment period may be pursued. A new developer as been assigned to the project, Jessica Harris.
Deliverable | FAC-002, MOD-032, TPL-001
Deadline | 2023-12-31 |  |  |  | -3 | Months to deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | Enter # in column B and description here. This value is 1 of 2 items that calculate the project baseline. If zero, delete this text.
Reserved for Future Use | N/A
Reserved for Future Use | N/A
Developer | Jessica Harris
PMOS Liaison | Claudine Fritz (Primary), Charles Yeung (Backup)
Affected Standards | 3 | FAC-002, MOD-032, TPL-001
Last Updated | 2024-04-04
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Research Required | 180 | 1
AS2 - Additional SAR 2 | [5 empty] | Intentional Hold/Delay | 30 | 2
QR - Quality Review | [5 empty] | Intentional Hold/Delay | 30 | 3
SP1 - SAR/PR/WP Posting 1 | 2022-10-17 | 2022-11-16 | 2022-08-11 | 2022-09-10 | -67 | Change in Developer | 30 | 4
SP2 - SAR Revise/Response |  |  | 2022-11-09 | 2023-01-08 |  | RSDP Priority Decrease | 60 | 5
SDT - Dev Time | 2023-01-15 | 2023-07-14 | 2023-03-09 | 2023-09-05 | 53 | RSDP Priority Decrease | 60 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2024-07-01 | 2024-08-15 | 2023-09-05 | 2023-10-20 | -300 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2024-11-13 | 2024-12-28 | 2023-12-19 | 2024-02-02 | -330 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | 2025-03-28 | 2025-05-12 | 2024-04-02 | 2024-05-17 | -360 | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2025-06-11 | 2025-06-21 | 2024-06-16 | 2024-06-26 | -360 | N/A | 0 | 13
PTB - Present to BOT | [5 empty] | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
[6 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | 30 | Calculated CF Date: | 2025-07-21
PTS Change Control
Reason for Update | Date | Notes
SC Action |  | SC authorized SAR posting and solicitation of the SAR DT.
Updated schedule | 2024-04-04 | Updated schedule based on project prrioritization (RSDP) and intentional hold
Formulas:
Calculated End = +[Calculated Start]+30
Calculated End = [Calculated Start]+60
Calculated Start = [Calculated End, row above]+60
Calculated Start = +[Calculated End, row above]+60
Projected or Actual End = [Projected or Actual Start]+180
Projected or Actual Start = [Projected or Actual End, row above]+90
Time Impact = D22+(E32-D22)+SUM(H19:[Time Impact, row above])
Note on D22: Enter SC SAR date here
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2022-05
Project | 2022-05 | [5 empty] | Home
Project Name | Modifications to CIP-008 Reporting Threshold
Status | SDT Development
Comments | The team is beginning to work through revisions to CIP-008 and associated glossary terms. They are taking a big picture view of the issues. The DT plans to conduct a webinar for outreach in May 2024. No formal posting will occur until Q3 2024 or later due to this being a low priority project.
Deliverable | CIP-008
Deadline | 2025-04-15 15:19 |  |  |  | 12 | Months to deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 0 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | Enter # in column B and description here. This value is 1 of 2 items that calculate the project baseline. If zero, delete this text.
Reserved for Future Use | N/A
Reserved for Future Use | N/A
Developer | Alison Oswald
PMOS Liaison | Ellese Murphy (Primary), Ruida Shu (backup)
Affected Standards | 1 | CIP-008
Last Updated | 2024-04-11
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Intentional Hold/Delay | 30 | 1
AS2 - Additional SAR 2 | [5 empty] | Intentional Hold/Delay | 30 | 2
QR - Quality Review | [5 empty] | Intentional Hold/Delay | 30 | 3
SP1 - SAR/PR/WP Posting 1 | 2022-11-02 | 2022-12-05 | 2022-11-02 | 2022-12-02 | 0 | Intentional Hold/Delay | 30 | 4
SP2 - SAR Revise/Response |  |  | 2023-01-31 | 2023-04-01 |  | Intentional Hold/Delay | 30
SDT - Dev Time |  |  | 2023-05-31 | 2023-07-30 | 0 | Intentional Hold/Delay | 30 | 5
CP1 - Comment Period 1 | [5 empty] | Intentional Hold/Delay | 30 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) |  |  | 2023-07-30 | 2023-09-13 | 0 | N/A | 0 | 8
CAB - Com/Add Ballot 2 |  |  | 2023-11-12 | 2023-12-27 | 0 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot |  |  | 2024-01-26 | 2024-02-05 | 0 | N/A | 0 | 13
PTB - Present to BOT | [5 empty] | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
[6 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | Need FB Date | Calculated CF Date: | 2024-09-02
PTS Change Control
Reason for Update | Date | Notes
SC Action |  | SC authorized SAR posting and solicitation of the SAR DT.
SAR Revise | 2024-03-12 | Added Line #23 for SAR Revise/Response
Formulas:
Calculated End = +[Calculated Start]+30
Calculated End = [Calculated Start]+60
Calculated Start = [Calculated End, row above]+60
Calculated Start = +[Calculated End, row above]+60
Time Impact = D22+(E32-D22)+SUM(H19:[Time Impact, row above])
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2023-01
Project | 2023-01 | [5 empty] | Home
Project Name | EOP-004 IBR Event Reporting
Status | Responding to Comment
Comments | Details on Draft: Added/revising IBR event reporting threshold. Current/Anticipated Posting: Informal comment period ended on 03/27. DT will review industry comments and schedule a meeting to discuss in late April or early May.
Deliverable | EOP-004-5
Deadline |  |  |  |  | N/A | Months to deadline
Priority in RSDP, click to see applicable Footnote |  |  | Priority (1-Low, 2-Med, 3-High ) | 2 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | Enter # in column B and description here. This value is 1 of 2 items that calculate the project baseline. If zero, delete this text.
Reserved for Future Use | N/A
Reserved for Future Use | N/A
Developer | Chris Larson
PMOS Liaison | Ruida Shu (Primary), Terri Pyle (Backup),
Affected Standards | 1 | EOP-004
Last Updated | 2024-04-10
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Additional Comment/Ballot | 60 | 1
AS2 - Additional SAR 2 | [5 empty] | Intentional Hold/Delay | 30 | 2
QR - Quality Review | [7 empty] | 3
SP1 - SAR/PR/WP Posting 1 | 2023-02-07 | 2023-03-09 | 2023-02-07 | 2023-03-09 | 0 | N/A | 0 | 4
SP2 - SAR Revise/Response |  |  | 2023-05-08 | 2023-07-07 |  | N/A |  | 5
SDT - Dev Time | 2023-06-01 | 2023-07-25 | 2023-08-06 | 2023-11-04 | 66 | N/A | 0 | 6
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 7
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 8
CIB - Com/Ballot 1 (Initial) | 2023-07-28 | 2023-09-11 | 2023-12-19 | 2024-02-02 | 144 | N/A | 0 | 9
CAB - Com/Add Ballot 2 | 2024-02-12 | 2024-03-28 | 2024-05-02 | 2024-06-16 | 80 | N/A | 0 | 10
CAB - Com/Add Ballot 3 | 2024-07-01 | 2024-08-15 | 2024-09-14 | 2024-10-29 | 75 | N/A | 0 | 11
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 12
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 13
FB - Final Ballot | 2024-09-14 | 2024-09-24 | 2024-11-28 | 2024-12-08 | 75 | N/A | 0 | 14
PTB - Present to BOT | [5 empty] | N/A | 0 | 15
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 16
[6 empty] | N/A | 0
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | 165 | Calculated CF Date: | 2025-03-08
PTS Change Control
Reason for Update | Date | Notes
SC Action | 2023-01-25 | SC authorized SAR posting and solicitation of the SAR DT on January 25, 2023. Posting start on 02/07/2023
Formulas:
Projected or Actual End = +[Projected or Actual Start]+30
Calculated End = +[Calculated Start]+30
Calculated End = [Calculated Start]+60
Calculated Start = [Calculated End, row above]+60
Calculated Start = +[Calculated End, row above]+30
Time Impact = D22+(E32-D22)+SUM(H19:[Time Impact, row above])
Note on D22: Enter SC SAR date here
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2023-02
Project | 2023-02 | [5 empty] | Home
Project Name | Performance of IBRs Standard Authorization Request
Status | SDT Development
Comments | Details on Draft: The team discussed and drafted language around Requirement R4 and R5. Requirement R4 pertains to the analysis section of the standard, the team discussed timeframes and which functional entities are applicable to the requirement. Requirement R5 deals with the mitigation aspect of the standard in relation to the Generator Owner (GO). The previous discussion focused on Corrective Action Plans (CAPs) and how this would be applied to a GO with numerous IBR facilities with the same or similar equipment. The team ended drafting with Requirement R6 corresponding to the correct functional entities to communicate the CAP to and the time period this will be occurring. Current/Anticipate Posting: Anticipated Initial ballot and comment the week of March 25th. This will be a shortened 25 day formal comment and ballot period per the wavier approved on December 13, 2023. Other: Identified as part of 2024 directives from Order 901. Final draft required by FERC to be approved by Nov 4, 2024.
Deliverable | PRC-004-7
Deadline | 2025-04-15 15:19 |  |  |  | 12 | Months to deadline
Priority in RSDP, click to see applicable Footnote | Footnote 11, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 1 | Enter # in column B and description here. This value is 1 of 2 items that calculate the project baseline. If zero, delete this text.
Reserved for Future Use | N/A
Reserved for Future Use | N/A
Developer | Josh Blume
PMOS Liaison | Claudine Fritz (Primary), Terri Pyle (Backup)
Affected Standards | 1 | PRC-004-6
Last Updated | 2024-04-11
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Standard Developer Change | 30 | 1
AS2 - Additional SAR 2 | [5 empty] | Cross-Coordination (Parallel) | 90 | 2
QR - Quality Review | 2024-02-07 | 2024-02-20 |  |  |  | N/A | 0 | 3
SP1 - SAR/PR/WP Posting 1 | 2023-02-07 | 2023-03-09 | 2023-02-07 | 2023-03-09 | 0 | N/A | 0 | 4
SP2 - SAR Revise/Response |  |  | 2023-05-08 | 2023-07-07 |  | N/A |  | 5
SDT - Dev Time | 2023-10-19 | 2024-02-16 | 2023-10-19 | 2024-02-16 | 0 | N/A | 0 | 6
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 7
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 8
CIB - Com/Ballot 1 (Initial) | 2024-03-25 | 2024-04-19 | 2024-04-01 | 2024-05-16 | 7 | N/A | 0 | 9
CAB - Com/Add Ballot 2 | 2024-08-14 | 2024-09-28 | 2024-08-14 | 2024-09-28 | 0 | N/A | 0 | 10
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 12
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 13
FB - Final Ballot | 2024-10-28 | 2024-11-07 | 2024-10-28 | 2024-11-07 | 0 | N/A | 0 | 14
PTB - Present to BOT | [5 empty] | N/A | 0 | 15
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 16
[6 empty] | N/A | 0
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | 120 | Calculated CF Date: | 2025-03-07
PTS Change Control
Reason for Update | Date | Notes
SC Action |  | SC authorized SAR posting and solicitation of the SAR DT.
SC Action | 2023-12-20 | Waiver for shortened Posting and Balloting time periods
Formulas:
Projected or Actual End = +[Projected or Actual Start]+30
Projected or Actual End = +[Calculated End]
Calculated End = +[Calculated Start]+30
Calculated End = [Calculated Start]+60
Calculated Start = [Calculated End, row above]+60
Calculated Start = +[Calculated End, row above]+90
Projected or Actual Start = +[Calculated Start]
Time Impact = D22+(E32-D22)+SUM(H19:[Time Impact, row above])
Note on D22: Enter SC SAR date here
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2023-03
Project | 2023-03 | [5 empty] | Home
Project Name | Internal Network Security Monitoring (INSM)
Status | SDT Development
Comments | Project 2023-03 INSM is currently in Additional Comment period and ballot period is scheduled April 12 through April 17, 2024. The DT unanimously determined to proceed with Project 2023-03 without including EACMS and PACS outside the ESP. A new standard, CIP-015-1, has been created for Internal Network Security Monitoring, rather than modifying CIP-007. The DT incorporated CIP Exceptional Circumstances into proposed Reliability Standard CIP-015-1. Should the current additional comment period with ballot pass, the DT will post the project for final ballot April 24-30, 2024 and present the project to the Board of Trustees at its May 2024 meeting. This project has a regulatory deadline of July 9, 2024.
Deliverable | CIP-005, CIP-010, CIP-013
Deadline | 2025-04-15 15:19 |  |  |  | 12 | Months to deadline
Priority in RSDP, click to see applicable Footnote | Footnote 11, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | Enter # in column B and description here. This value is 1 of 2 items that calculate the project baseline. If zero, delete this text.
Reserved for Future Use | N/A
Reserved for Future Use | N/A
Developer | Laura Anderson
PMOS Liaison | Ruida Shu (Primary), Ron Sporseen (Backup)
Affected Standards | 3 | CIP-005-7, CIP-010-4, CIP-013-2
Last Updated | 2024-04-11
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | N/A | 0 | 1
AS2 - Additional SAR 2 | [5 empty] | N/A | 0 | 2
QR - Quality Review | [5 empty] | N/A | 0 | 3
SP1 - SAR/PR/WP Posting 1 | 2023-04-06 | 2023-05-05 | 2023-04-06 | 2023-05-05 | 0 | N/A | 0 | 4
SP2 - SAR Revise/Response |  |  | 2023-07-04 | 2023-09-02 |  | N/A |  | 5
SDT - Dev Time | 2023-08-31 | 2024-04-29 | 2023-08-31 | 2024-04-29 | 0 | N/A | 0 | 6
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 7
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 8
CIB - Com/Ballot 1 (Initial) | 2023-10-02 | 2023-11-16 | 2023-10-02 | 2023-11-16 | 0 | N/A | 0 | 9
CAB - Com/Add Ballot 2 | 2024-01-08 | 2024-02-22 | 2024-01-08 | 2024-02-22 | 0 | N/A | 0 | 10
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 12
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 13
FB - Final Ballot | 2024-04-19 | 2024-04-29 | 2024-04-19 | 2024-04-29 | 0 | N/A | 0 | 14
PTB - Present to BOT | [5 empty] | N/A | 0 | 15
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 16
[6 empty] | N/A | 0
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | 0 | Calculated CF Date: | 2024-04-29
PTS Change Control
Reason for Update | Date | Notes
SC Action |  | SC authorized SAR posting and solicitation of the SAR DT.
Formulas:
Calculated Start = [Calculated End, row above]+60
Calculated End = [Calculated Start]+60
Calculated End = +[Calculated Start]+45
Projected or Actual End = +[Projected or Actual Start]+45
Time Impact = D22+(E32-D22)+SUM(H19:[Time Impact, row above])
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2023-04
Project | 2023-04 | [5 empty] | Home
Project Name | Modifications to CIP-003
Status | Responding to Comment
Comments | Details on Draft: Team merged CIP-003, Attachment 1, Sections 3 and 6; added three controls for Low Impact Criteria. Updates made to Section 3.1. Configuration diagrams added to Technical Rationale. Current/Anticipated Posting: Formal comment ended on March 14. Other: DT team is revising CIP-003 and planning on additional ballot in May.
Deliverable | CIP-003
Deadline | 2023-10-31 |  |  |  | -5 | Months to deadline
Priority in RSDP, click to see applicable Footnote | Footnote 11, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | Enter # in column B and description here. This value is 1 of 2 items that calculate the project baseline. If zero, delete this text.
Reserved for Future Use | N/A
Reserved for Future Use | N/A
Developer | Chris Larson
PMOS Liaison | Kirk Rosener (primary), Ron Sporseen (Backup)
Affected Standards | 1 | CIP-003-9
Last Updated | 2024-04-15
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | N/A | 0 | 1
AS2 - Additional SAR 2 | [5 empty] | N/A | 0 | 2
QR - Quality Review | [5 empty] | N/A | 0 | 3
SP1 - SAR/PR/WP Posting 1 | 2023-03-31 | 2023-05-15 | 2023-03-31 | 2023-05-15 | 0 | N/A | 0 | 4
SAR - SAR Revise/Response | 2023-07-14 | 2023-08-23 | 2023-07-14 | 2023-09-12 |  | N/A |  | 5
SDT - Dev Time | 2023-10-12 | 2024-01-10 | 2023-10-12 | 2024-01-10 | 0 | N/A | 0 | 6
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 7
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 8
CIB - Com/Ballot 1 (Initial) | 2023-10-23 | 2023-12-07 | 2024-02-24 | 2024-04-09 | 124 | N/A | 0 | 9
CAB - Com/Add Ballot 2 | 2024-01-30 | 2024-03-15 | 2024-07-08 | 2024-08-22 | 160 | N/A | 0 | 10
CAB - Com/Add Ballot 3 | 2024-07-01 | 2024-08-15 |  |  |  | N/A | 0 | 11
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 12
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 13
FB - Final Ballot | 2024-09-14 | 2024-09-24 | 2024-09-21 | 2024-10-01 | 7 | N/A | 0 | 14
PTB - Present to BOT | 2024-12-01 | 2024-12-01 |  |  |  | N/A | 0 | 15
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 16
[6 empty] | N/A | 0
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | 7 | Calculated CF Date: | 2024-10-01
PTS Change Control
Reason for Update | Date | Notes
SC Action |  | SC authorized SAR posting and solicitation of the SAR DT.
SC Action | 2023-06-21 | SC appointed SDT
SC Action | 2023-07-27 | SC authorized revisions to CIP-003-9 via email vote (action without meeting).
Formulas:
Calculated Start = [Calculated End, row above]+60
Calculated Start = +[Calculated End, row above]+30
Calculated End = [Calculated Start]+60
Calculated End = +[Calculated Start]+(B9*30)+(B14*60)+30
Projected or Actual Start = +[Calculated Start]
Projected or Actual End = +[Calculated End]
Projected or Actual End = +[Projected or Actual Start]+45
Time Impact = D22+(E32-D22)+SUM(H19:[Time Impact, row above])
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2023-05
Project | 2023-05 | [5 empty] | Home
Project Name | Modifications to FAC-001 and FAC-002
Status | Nominations & SAR
Comments | Project is on hold and ready to start.
Deliverable | FAC-001, FAC-002
Deadline | 2025-04-15 15:19 |  |  |  | 12 | Months to deadline
Priority in RSDP, click to see applicable Footnote | Low |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | Enter # in column B and description here. This value is 1 of 2 items that calculate the project baseline. If zero, delete this text.
Reserved for Future Use | N/A
Reserved for Future Use | N/A
Developer | Josh Blume
PMOS Liaison | Donovan Crane (Primary), Jason Chandler (Backup)
Affected Standards | 2 | FAC-001-4; FAC-002-4
Last Updated | 2024-04-11
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | Standard Developer Change | 30 | 1
AS2 - Additional SAR 2 | [5 empty] | RSDP Priority Decrease | 60 | 2
QR - Quality Review | [5 empty] | N/A | 0 | 3
SP1 - SAR/PR/WP Posting 1 | 2024-04-15 15:19 | 2024-05-15 15:19 | 2024-04-15 15:19 | 2024-05-15 15:19 | 0 | N/A | 0 | 4
SP2 - SAR Revise/Response |  |  | 2024-07-14 15:19 | 2024-09-12 15:19
SDT - Dev Time | 2024-10-12 15:19 | 2025-03-11 15:19 | 2024-10-12 15:19 | 2025-03-11 15:19 | 0 | N/A | 0 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2025-04-25 15:19 | 2025-06-09 15:19 | 2025-04-25 15:19 | 2025-06-09 15:19 | 0 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2025-09-07 15:19 | 2025-10-22 15:19 | 2025-09-07 15:19 | 2025-10-22 15:19 | 0 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2025-11-21 15:19 | 2025-12-01 15:19 | 2025-11-21 15:19 | 2025-12-01 15:19 | 0 | N/A | 0 | 13
PTB - Present to BOT | [5 empty] | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
[6 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | 90 | Calculated CF Date: | 2026-03-01 15:19
PTS Change Control
Reason for Update | Date | Notes
SC Action |  | SC authorized SAR posting and solicitation of the SAR DT.
Formulas:
Projected or Actual Start = +[Calculated Start]
Projected or Actual End = +[Projected or Actual Start]+30
Projected or Actual End = +[Calculated End]
Calculated Start = [Calculated End, row above]+60
Calculated Start = +[Calculated End, row above]+30
Calculated End = +[Calculated Start]+30
Calculated End = [Calculated Start]+60
Time Impact = D22+(E32-D22)+SUM(H19:[Time Impact, row above])
Note on D22: Enter SC SAR date here
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2023-06
Project | 2023-06 | [5 empty] | Home
Project Name | CIP-014 Risk Assessment Refinement
Status | Nominations & SAR
Comments | This high priority project has the drafting team meeting twice per week. Details on Draft: Currently working initial draft requirements for establishing an annual applicability review for determination of newly applicable stations for a risk assessment. Current/Anticipate Posting: Anticipated initial comment and ballot in April/May 2024. Other: Identified as part of NERC Corporate Goals and anticipate submitting to board by end of 2024.
Deliverable | CIP-014-4
Deadline | 2025-04-15 15:19 |  |  |  | 12 | Months to deadline
Priority in RSDP, click to see applicable Footnote | Footnote 11, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | Enter # in column B and description here. This value is 1 of 2 items that calculate the project baseline. If zero, delete this text.
Reserved for Future Use | N/A
Reserved for Future Use | N/A
Developer | Ben Wu
PMOS Liaison | Claudine Fritz (Primary), Ellese Murphy (Backup)
Affected Standards | 1 | CIP-014-3
Last Updated | 2024-04-11
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | N/A | 0 | 1
AS2 - Additional SAR 2 | [5 empty] | N/A | 0 | 2
QR - Quality Review | [5 empty] | N/A | 0 | 3
SP1 - SAR/PR/WP Posting 1 | 2023-07-26 | 2023-08-25 | 2023-07-26 | 2023-08-25 | 0 | N/A | 0 | 4
SP2 - SAR Revise/Response |  |  | 2023-10-24 | 2023-12-23
SDT - Dev Time | 2024-01-22 | 2024-04-21 | 2024-01-22 | 2024-04-21 | 0 | N/A | 0 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2024-05-17 | 2024-07-01 | 2024-06-05 | 2024-07-20 | 19 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2024-08-02 | 2024-09-16 | 2024-10-18 | 2024-12-02 | 77 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2024-10-16 | 2024-10-26 | 2025-01-01 | 2025-01-11 | 77 | N/A | 0 | 13
PTB - Present to BOT | [5 empty] | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
[6 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | 77 | Calculated CF Date: | 2025-01-11
PTS Change Control
Reason for Update | Date | Notes
SC Action |  | SC authorized SAR posting and solicitation of the DT.
Formulas:
Projected or Actual Start = +[Calculated Start]
Projected or Actual End = +[Projected or Actual Start]+30
Projected or Actual End = +[Calculated End]
Calculated End = +[Calculated Start]+30
Calculated End = [Calculated Start]+60
Calculated Start = [Calculated End, row above]+60
Calculated Start = +[Calculated End, row above]+30
Time Impact = D22+(E32-D22)+SUM(H19:[Time Impact, row above])
Note on D22: Enter SC SAR date here
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2023-07
Project | 2023-07 | [5 empty] | Home
Project Name | Transmission System Planning Performance Requirements for Extreme Weather
Status | Nominations & SAR
Comments | Seeking authorization to post from the SC at its March 20 meeting. If authorized to post, will post same day (March 20) for an initial 45-day comment and ballot period. An anticipated industry webinar to be completed the week of April 8th.
Deliverable | TPL-001-6
Deadline | 2024-12-15 |  |  |  | 8 | Months to deadline
Priority in RSDP, click to see applicable Footnote | Footnote 11, High |  | Priority (1-Low, 2-Med, 3-High ) | 3 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 23 | FERC Order 896
Reserved for Future Use | N/A
Reserved for Future Use | N/A
Developer | Jordan Mallory
PMOS Liaison | Jason Chandler (Primary), Donovan Crane (Backup)
Affected Standards | 1 | TPL-001-5.1
Last Updated | 2024-04-11
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | N/A | 0 | 1
AS2 - Additional SAR 2 | [5 empty] | N/A | 0 | 2
QR - Quality Review | [5 empty] | N/A | 0 | 3
SP1 - SAR/PR/WP Posting 1 | 2024-04-15 15:19 | 2024-05-15 15:19 | 2024-04-15 15:19 | 2024-05-15 15:19 | 0 | N/A | 0 | 4
SP2 - SAR Revise/Response |  |  | 2024-07-14 15:19 | 2024-09-12 15:19
SDT - Dev Time |  |  | 2024-10-12 15:19 | 2024-11-11 15:19 | 0 | N/A | 0 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2024-03-20 | 2024-04-29 | 2024-12-26 15:19 | 2025-02-09 15:19 | 281.6383 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2024-06-19 | 2024-08-05 | 2025-05-10 15:19 | 2025-06-24 15:19 | 325.6383 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | 2024-09-10 | 2024-10-25 |  |  |  | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2024-10-28 | 2024-11-07 | 2025-07-24 15:19 | 2025-08-03 15:19 | 269.6383 | N/A | 0 | 13
PTB - Present to BOT | [5 empty] | N/A | 0 | 14
Filing - Filing with Regulators | 2024-12-15 |  |  |  |  | N/A | 0 | 15
[6 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | 269.6383 | Calculated CF Date: | 2025-08-03 15:19
PTS Change Control
Reason for Update | Date | Notes
SC Action |  | SC authorized SAR posting and solicitation of the DT.
Formulas:
Projected or Actual Start = +[Calculated Start]
Projected or Actual End = +[Projected or Actual Start]+30
Calculated Start = [Calculated End, row above]+60
Calculated Start = +[Calculated End, row above]+30
Calculated End = +[Calculated Start]+30
Calculated End = [Calculated Start]+60
Time Impact = D22+(E32-D22)+SUM(H19:[Time Impact, row above])
Note on D22: Enter SC SAR date here
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## 2023-08
Project | 2023-08 | [5 empty] | Home
Project Name | Modifications of MOD-031 Demand and Energy Data
Status | Nominations & SAR
Comments | SAR accepted by the SC on July 19, 2023. Working to determine a posting date for a 30-day SAR comment period and solicitation for nominations.
Deliverable | TBD
Deadline | 2025-04-15 15:19 |  |  |  | 12 | Months to deadline
Priority in RSDP, click to see applicable Footnote | Low |  | Priority (1-Low, 2-Med, 3-High ) | 1 | Reserved for Future Use | 0
Reserved for Future Use | N/A
Number of Directives | 0 | Enter # in column B and description here. This value is 1 of 2 items that calculate the project baseline. If zero, delete this text.
Reserved for Future Use | N/A
Reserved for Future Use | N/A
Developer | Jessica Harris
PMOS Liaison | Darrel Grumman (Primary); Pamela Hunter (Backup)
Affected Standards | 1 | MOD-031
Last Updated | 2024-04-11
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Calculated Start | Calculated End | No. of Days Ahead or (Behind) Schedule | Complexity Factor (CF) Impacts to Schedule (Start on 1st Row) | Time Impact | Index
AS1 - Additional SAR 1 | [5 empty] | N/A | 0 | 1
AS2 - Additional SAR 2 | [5 empty] | N/A | 0 | 2
QR - Quality Review | [5 empty] | N/A | 0 | 3
SP1 - SAR/PR/WP Posting 1 | 2024-04-15 15:19 | 2024-05-15 15:19 | 2024-04-15 15:19 | 2024-05-15 15:19 | 0 | N/A | 0 | 4
SP2 - SAR Revise/Response |  |  | 2024-07-14 15:19 | 2024-09-12 15:19
SDT - Dev Time | 2024-10-12 15:19 | 2025-01-10 15:19 | 2024-10-12 15:19 | 2025-01-10 15:19 | 0 | N/A | 0 | 5
CP1 - Comment Period 1 | [5 empty] | N/A | 0 | 6
CP2 - Comment Period 2 | [5 empty] | N/A | 0 | 7
CIB - Com/Ballot 1 (Initial) | 2025-02-24 15:19 | 2025-04-10 15:19 | 2025-02-24 15:19 | 2025-04-10 15:19 | 0 | N/A | 0 | 8
CAB - Com/Add Ballot 2 | 2025-07-09 15:19 | 2025-08-23 15:19 | 2025-07-09 15:19 | 2025-08-23 15:19 | 0 | N/A | 0 | 9
CAB - Com/Add Ballot 3 | [5 empty] | N/A | 0 | 10
CAB - Com/Add Ballot 4 | [5 empty] | N/A | 0 | 11
CAB - Com/Add Ballot 5 | [5 empty] | N/A | 0 | 12
FB - Final Ballot | 2025-09-22 15:19 | 2025-10-02 15:19 | 2025-09-22 15:19 | 2025-10-02 15:19 | 0 | N/A | 0 | 13
PTB - Present to BOT | [5 empty] | N/A | 0 | 14
Filing - Filing with Regulators | [5 empty] | N/A | 0 | 15
[6 empty] | N/A | 0 | 16
Delta based on Calculated CF Date and Actual Final Ballot: |  |  |  |  | 0 | Calculated CF Date: | 2025-10-02 15:19
PTS Change Control
Reason for Update | Date | Notes
SC Action |  | SC authorized SAR posting and solicitation of the SAR DT.
Formulas:
Projected or Actual Start = +[Calculated Start]
Projected or Actual End = +[Projected or Actual Start]+30
Projected or Actual End = +[Calculated End]
Calculated Start = [Calculated End, row above]+60
Calculated Start = +[Calculated End, row above]+30
Calculated End = +[Calculated Start]+30
Calculated End = [Calculated Start]+60
Time Impact = D22+(E32-D22)+SUM(H19:[Time Impact, row above])
Note on D22: Enter SC SAR date here
Note on F36: PMOS looks at this date to ascertain what is creating a delta between the Actual Final Ballot end date and the Calculated CF Date and make adjustments. Green +/- 0-45 days Yellow +/- 45-90 days Red +/- 90 or more days

## Footnotes
Home | FOOTNOTES
No. | Description
Note 1 | 2015-2017 RSDP The prioritizations here reflect those prioritizations assigned as part of the 2015-2017 Reliability Standards Development Plan (RSDP). In its approach to prioritizing Reliability Standards projects, the RSDP considered how Reliability Standard family priorities are applied to individual projects and outstanding work. Specific elements included: (1) RISC Category Rankings; (2) regulatory directives; (3) regulatory deadlines; (4) Reliability Standard requirement candidates for retirement; (5) the IERP content and quality assessments; and (6) additional considerations (fill-in-the-blank status and five-year assessment commitments). Some projects were not prioritized in the RSDP, as they were originally anticipated to be complete before the end of the first quarter of 2015, and those projects have an "N/A" designation in this column. Other projects have been added to the Project Tracking Spreadsheet that were not prioritized in the RSDP. These were added in response to regulatory directives that were issued following completion of the RSDP, and they will be prioritized according to the same process during the first quarter of 2015 according to the same process described in the RSDP. Those projects are designated as "Pending Prioritization in 1Q 2015." As discussed in the 2015-2017 RSDP, the prioritization will occur in collaboration between NERC Staff and the Standards Committee.
Note 2 | Refers to guidances from regulatory orders for standards activity to consider, but that do not carry the same effect as a directive.
Note 3 | In the columns at right, in some cases, an "additional ballot" is not indicated for planning purposes, but if consensus is not supported on an initial ballot, or if substantive changes occur, one will be scheduled.
Note 4 | In the columns at right, there are no "plan" milestones in some cases because the project was originally planned to be complete in 2014, and the project's "actual" milestones have extended into 2015).
Note 5 | In the column labeled "directionally consistent with IERP findings," directionally consistent indicates whether the Standard Drafting Team, when the project is completed, considered the recommendations from the Independent Expert Review Project and the Paragraph 81 project. After the Standard Drafting Team has considered the recommendations, the materials posted with the standards will describe the Standard Drafting Team's consideration of the findings.
Note 6 | Baseline - SC Approved project schedule. Current - Standards Developer managed schedule. Proposed - Not approved, used for planning purposes. Archived-Current - Project completed or abandoned. Archived-Baseline - Project completed or abandoned. On Hold - Project is held temporarily (e.g., due to coordination with other projects) Open-Baseline - Reserved for future project. Open-Current - Reserved for future project. N/A - Scheduling is not applicable.
Note 7 | 2016-2018 RSDP The following projects are planned to continue from 2015 along with any 2015 projects that are planned to be completed in that year but need additional time. As in the 2015–2017 RSDP, the approach to prioritizing Reliability Standards projects in this RSDP addressed how Reliability Standard family priorities are applied to individual projects and outstanding work. Specific elements included: (1) RISC Category Rankings; (2) regulatory directives; (3) regulatory deadlines; (4) Reliability Standard requirement candidates for retirement; (5) the IERP content and quality assessments; and (6) additional considerations (fill‐in‐the‐blank status and five‐year assessment commitments). The prioritization gave primary consideration to RISC category rankings, regulatory directives, and regulatory deadlines. Based on the application of these elements, this section prioritizes each Reliability Standard project as high, medium, low, or pending technical committee input.
Note 8 | 2017-2019 RSDP The approach to prioritizing Reliability Standards projects in this RSDP is consistent with previous RSDPs. Specific elements include: (1) RISC Category Rankings; (2) regulatory directives and deadlines; (3) Reliability Standard requirements recommended for retirement; (4) the IERP content and quality assessments; and (5) additional considerations (fill-in-the-blank status and five-year assessment commitments). The prioritization considers RISC category rankings, regulatory directives, and regulatory deadlines. Based on the application of these elements, this section prioritizes each Reliability Standard project as high, medium, low, or pending technical committee input.
Note 9 | 2018-2020 RSDP
Note 10 | 2019-2021 RSDP (Draft)
Note 11 | 2021-2023 RSDP The approach to prioritizing Reliability Standards projects in this RSDP is consistent with previous RSDPs. Specific elements include: (1) RISC Category Rankings; (2) regulatory directives and deadlines; (3) Reliability Standard requirements recommended for retirement; (4) the IERP content and quality assessments; and (5) additional considerations (fill-in-the-blank status and five-year assessment commitments). The prioritization considers RISC category rankings, regulatory directives, and regulatory deadlines. Based on the application of these elements, this section prioritizes each Reliability Standard project as high, medium, low, or pending technical committee input.

## Help
1 | SUMMARY
2 | Tutorial Video (11 min)
3 | Click here to report errors or issues
4 | Tabs along the bottom of the spreadsheet:
5 | Green tab - Home Page listing all active projects
6 | Yellow tabs - Help, Summary Page of projects, and Footnotes (far right tab)
7 | Blue tabs - Indicate an active project.
8 | Red tabs - Indicate a non-active project and are generally not shown, but may be revealed by "unhiding" the tab. If a red tab has an "underscore" preceding the project number (e.g., _YYYY-##) it means the project was added for developing metrics on previous projects not initially populated in this tracker.
9 | Project Number nomenclature: The year started and the sequence (YYYY-##), a letter or .#/.alphabet letter denote the project was split into phases for tracking purposes. Phased projects in the tracker may or may not reflect the project being "Phased" on the www.nerc.com website.
10 | Home Page - Gannt chart of active projects with current or proposed schedules, typically set with the baseline schedule not showing.
11 | Home Page - Filter is OKAY. Sorting will misalign the conditional formatting of the Gannt Chart.
12 | Home Page - Column "B" is a freshness indicator of the underlying project page.
13 | Home Page - Column "C" is the project name with an in document hyperlink to the respective project tab
14 | Home Page - Column "D" lists the deliverables identified on the individual project pages
15 | Home Page - Column "E" lists the number of days early or (late) a project is running based on the approved baseline schedule final ballot date.
16 | Home Page - Column "F" lists the current status of the project "schedule" (See Note 6 in the footnotes for more information).
17 | Home Page - Remaining columns to the right color code the what is anticipated in the project schedule. Proposed means the projected schedule or that it has been completed. If the projects are filtered on "baseline" the PMOS approved schedure is shown. To see previous time or future times, simply "unhide" the applicable columns using the spreadsheet functions.
18