## Subgroup Work Plan Items
RSTC High Priority Work Plan Item | Subgroup Name | Work Plan Item # | Task Name | Task Description | Due Date | Subgroup Priority | Task Status | Comments
X | Electric Vehicle Task Force (EVTF) | 1 | White Paper: Risk Profiles and Prioritization on Motor Vehicle Electrification | A white paper on the list of risks the task force identifies, validates, and prioritizes related to the electrification of motor vehicles. The white paper will be at a high level and the remaining work products reinforce the outcomes of the NERC study on potential BPS impacts from EV charging | 2025-06-30 | High | In Progress
| Electric Vehicle Task Force (EVTF) | 2 | White Paper: Risk Mitigation Strategies to Manage Motor Vehicle Electrification | A white paper on the focused high priority risks from the prioritization white paper also on the EVTF work plan. This paper is to provide recommended risk mitigation strategies that could be employed for all the risks as well as expand upon how utilities and EV manufacturers can ensure BPS Reliability | 2025-06-30 | High | In Progress
| Electric Vehicle Task Force (EVTF) | 3 | Technical Report: EV Charging States and Type Tests | A technical repository of known EV charger type tests, modern EV charging characteristics, and generic responses to EV electrical response to transient stability. This document will also cover model improvements to represent charging and discharging behavior of EVs and EV service equipment that the RSTC LMWG can build upon. | 2025-12-31 | Medium | In Progress
| Electromagnetic Transient Working Group (EMTWG) | 1 | EMT Modeling Standard Monitoring and Support | Monitor and support the activities of Standard Project 2022-04 EMT Modeling |  | Medium | In Progress
| Electromagnetic Transient Working Group (EMTWG) | 3 | Curated EMT Resources Repo | ​Repository of carefully curated EMT modeling and study references (recommended modeling and study practices, including verification, and validation of models, analysis approach and results, references to educational materials, tutorials and workshop presentations, case studies, automation approaches, frequently asked questions (FAQs) gathered from event Q&A sessions, webinars, and other outreach efforts), organized in such a way that a beginner can self-guide their learning curve | 2025-12-31 | High | In Progress
X | Electromagnetic Transient Working Group (EMTWG) | 4 | Whitepaper: Case Study on Adoption of EMT Modeling and Studies in Interconnection and Planning Studies for BPS-connected IBRs | ​Identify TPs and PCs adopting EMT modeling and studies in their interconnection and planning studies for BPS-connected IBR and document challenges and progress. | 2025-03-31 | High | In Progress
| Electromagnetic Transient Working Group (EMTWG) | 5 | White Paper: EMT Analysis in Operations | ​Identify the EMT model use cases in offline operation studies, unique challenges and requirements that differ from interconnection and planning study use cases | 2025-03-31 | High | In Progress
| Electromagnetic Transient Working Group (EMTWG) | 6 | Support IRPS White Paper: Model Benchmarking and Unit Model Validation by providing EMT exampl | Support IRPS White Paper: Model Benchmarking and Unit Model Validation by providing EMT exampl | 2025-12-31 | High | In Progress
| Electromagnetic Transient Working Group (EMTWG) | 7 | White Paper: Real-code EMT model using IEEE/CIGRE Standard DLL Interface | Provide real-world examples and best practices of using the standard DLL interface for optimal accuracy and portability of EMT models. | 2025-12-31 | Medium | In Progress
| Electromagnetic Transient Working Group (EMTWG) | 8 | White Paper: EMT Model Portability and Maintenance | Provide best practices for using industry standard data format for model portability and ease of maintenance to streamline EMT modeling and studies. | 2025-12-31 | Medium | In Progress
| Electromagnetic Transient Working Group (EMTWG) | 9 | White Paper: Uniform IBR Plant Model Interface and Uniform Test Harness | Provide specifications for uniform IBR plant model interface and test harness to harmonize EMT modeling effort, reducing time and effort in testing and integration of IBR plant models into system models. | 2026-06-30 | Medium | In Progress
| Electromagnetic Transient Working Group (EMTWG) | 10 | White Paper: Importance of detailed IBR model in derisking partial plant tripping | Assess and document the importance of detailed IBR plant models to adequately capture partial plant tripping risks during interconnection stage. | 2026-12-31 | Low | In Progress
| EMS Working Group (EMSWG) | 1 | Annual Monitoring and Situational Awareness Conference 2025 | ​Plans, arrangements and agenda for Annual Monitoring and Situational Awareness Conference | 2025-12-31 | Medium | In Progress
| Energy Reliablity Assessment Working Group (ERAWG) | 1 | White Paper - Energy Reliability Assessments – Volume 2 | ​Document methods and processes for developing detailed scenarios to evaluate energy reliability that include criticalinfrastructureinterdependencies | 2024-05-31 | High | Completed
| Energy Reliablity Assessment Working Group (ERAWG) | 2 | Voluntary Peer Review including Tools & Metrics - Energy Reliability Assessments | Discuss best practices, tools, and metrics that are needed to perform Energy Reliability Assessments |  | Medium | In Progress
| Energy Reliablity Assessment Working Group (ERAWG) | 3 | Project 2022-03 Energy Assurance with Energy-Constrained Resources | Providing technical leadership and guidance on matters relating to Energy Reliability Assessments for the Standards drafting team. | 2024-09-30 | High | Completed
| Energy Reliablity Assessment Working Group (ERAWG) | 4 | Project 2024-02 Planning Energy Assurance | Providing technical leadership and guidance on matters relating to Energy Reliability Assessments for the Standards drafting team. |  | High | In Progress
| Energy Reliablity Assessment Working Group (ERAWG) | 5 | Support Study: Reviewing Fuel Availability for Regional Flexible Resources to Support System Variability | As North America increases its reliance on variable energy resources, so too will the grid’s need for firm flexible generation to support and accommodate the intermittent generation. During this transition, flexible generation and the availability of fuel, primarily natural gas, will play a critical role in maintaining reliability and providing Essential Reliability Services, specifically ramping capability. The EGWG would serve as a technical review board for this study. |  | Low | In Progress
| Energy Reliablity Assessment Working Group (ERAWG) | 6 | Create and maintain a Gas-Electric Repository | NERC has long stated that natural gas is essential to the reliability of the grid during the electricity industry’s unprecedented transformation. In partnership with the Department of Energy, NERC’s ERAWG is creating a repository of papers and reports that highlight the interconnectedness of electricity and natural gas and explore approaches to resolve issues between the two energy sectors |  | Low | In Progress
| Event Analysis Subcommittee (EAS) | 1 | 2025 State of Reliability Report | ​Play a lead role in the development of the 2025 State of Reliability Report in coordination with the PAS. | 2025-08-01 | Medium | Not Started
| Event Analysis Subcommittee (EAS) | 2 | Develop Lessons Learned in 2025 | ​Play a lead role in the development and endorsement of Lessons Learned to be published by NERC. | 2025-12-31 | Medium | In Progress
| Event Analysis Subcommittee (EAS) | 3 | Generating Unit Winter Weather Readiness Webinar | ​Generating Unit Winter Weather Readiness Webinar | 2025-10-31 | Medium | Not Started
| Event Analysis Subcommittee (EAS) | 4 | Industry Webinar – Lessons Learned | ​Industry Webinar – Lessons Learned | 2025-12-31 | Medium | In Progress
| Facility Ratings Task Force (FRTF) | 1 | Implementation Guidance on Sustaining Accurate Facility Ratings | ​Discuss the four themes identified by the ERO Enterprise as the primary issues that have impacted and posed challenges to the sustainability of accurate facility ratings, and provide guidance to registered entities to address them. | 2025-12-31 | Medium | In Progress
| Facility Ratings Task Force (FRTF) | 2 | Support Project 2021-08 Modifications to FAC-008 SDT | Support SDT in focusing FAC-008 | 2026-12-31 | Low | In Progress
| Failure Modes and Mechanisms Task Force (FMMTF) | 1 | Failure Modes and Mechanism Diagrams for 2025 | ​Failure Modes and Mechanism Diagrams for 2025 | 2025-12-31 | Medium | In Progress | Ongoing
| Inverter-Based Resource Performance Subcommittee (IRPS) | 1 | White Paper: Model Benchmarking and Unit Model Validation | Provide guidance on model benchmarking and validation practices, criteria and sample reports and templates. | 2025-12-31 | High | In Progress
| Inverter-Based Resource Performance Subcommittee (IRPS) | 2 | White Paper: Best Practices for Testing of IBR Integration | Provide state of the art practices and solutions to test and evaluate IBR design to help derisk integration of IBR projects before commissioning | 2025-12-31 | Medium | In Progress
| Inverter-Based Resource Performance Subcommittee (IRPS) | 3 | IEEE p2800 Monitoring and Support | IEEE 2800-2022 and .2 Monitoring and Support | 2025-12-31 | Low | In Progress | Ongoing, as needed.
X | Inverter-Based Resource Performance Subcommittee (IRPS) | 8 | Reliability Guideline: Recommended Approach to Interconnection Studies for BPS-Connected Inverter-Based Resources | Focused guidance on improving the study process for BPS-connected inverter-based resources, particularly with increasing penetrations of these resources and the growing complexity of performing sufficient studies to ensure BPS reliability. | 2025-12-31 | High | In Progress
| Inverter-Based Resource Performance Subcommittee (IRPS) | 19 | Tracking and Supporting NERC Standard Drafting Activities | IRPS will monitor and support (as needed) NERC Standard Drafting Teams related to modifications for BPS-connected inverter-based resources. Projects currently include: · Project 2021-04 Modifications to PRC-002-2 · Project 2020-02 Modifications to PRC-024 (Generator Ride-Through) · Project 2020-06 Verification of Models and Data for Generators · Project 2021-01 Modifications to MOD-025 and PRC-019 · Project 2022-04 EMT Modeling · Project 2021-02 Modification to VAR-002 · (Future Project) Updates to EOP-004 · (Future Project) IBR Performance Issues IRPS will ensure that past recommendations are addressed in NERC Standards revisions and will submit follow-on SARs if any recommendations outlined in IRPS documentation or NERC reports are not adequately addressed. | 2025-12-31 | Low | In Progress
X | Inverter-Based Resource Performance Subcommittee (IRPS) | 24 | White Paper: BPS-Connected IBR Commissioning Best Practices | ​White paper to highlight best practices for commissioning BPS-connected inverter-based resources to ensure appropriate protection and controls are configured and that models and studies match actual installed operational capabilities. | 2025-06-30 | High | In Progress
| Inverter-Based Resource Performance Subcommittee (IRPS) | 26 | Tracking and Support for FERC Directives | ​Tracking FERC directives related to inverter-based resources and providing any support to NERC and associated activities, where applicable. | 2026-12-31 | Low | In Progress
X | Large Loads Task Force (LLTF) | 1 | White Paper: Characteristics and Risks of Emerging Large Loads | White Paper on the unique characteristics and risks associated with emerging large loads. This paper will leverage the NERC Framework to address known and emerging reliability and security risks to identify, validate, and prioritize potential reliability risks related to the integration of emerging large loads. | 2025-06-30 | High | In Progress
X | Large Loads Task Force (LLTF) | 2 | White Paper: Assessment of gaps in existing practices, requirements, and Reliability Standards for Emerging Large Loads | White Paper assessing whether existing engineering practices, requirements, and Reliability Standards can adequately capture and mitigate reliability impact(s) of large loads interconnected to the BPS. The paper will also highlight gaps in load modeling practices that LMWG can leverage to take further action to improve load modeling | 2025-12-31 | High | In Progress
X | Large Loads Task Force (LLTF) | 3 | Reliability Guideline: Risk Mitigation for Emerging Large Loads | Reliability Guideline identifying risk mitigation including improvements to existing planning, and operation processes and interconnection requirements for large loads. Guidance may include recommended improvements to modeling practices, analyses, coordination and data collection efforts, real time monitoring and event analysis. | 2026-06-30 | High | In Progress
X | Load Modeling Working Group (LMWG) | 1 | Data Center Load Modeling | Develop new approaches to model data centers Refine existing approaches to model data centers Develop potential approaches to differentiate between different types of computational facilities (Crypto mines and data centers | 2025-06-30 | High | In Progress
X | Load Modeling Working Group (LMWG) | 2 | Load Modeling Technical Reference Update and Refinement | Evaluate if the published technical reference last updated in 2016 reflects the current state of the art Update identified existing sections and add new sections where necessary | 2025-12-31 | High | In Progress
| Load Modeling Working Group (LMWG) | 3 | Developing Load Modeling Training Resources | Develop the resources to address the identified gaps Publish and communicate the developed resources | 2025-12-31 | Medium | In Progress
| Load Modeling Working Group (LMWG) | 4 | Electric Vehicle Load Modeling | Refine existing approaches to Electric Vehicles load modeling Enhance approach by integrating EV Load shapes | 2026-12-31 | Low | In Progress
| Load Modeling Working Group (LMWG) | 5 | Verification of the performance of the single-phase induction motor phasor model in main software platforms | Compare performance between the phasor model and the performance model (algebraic formulation) | 2026-12-31 | Low | In Progress
| Load Modeling Working Group (LMWG) | 6 | Heat Pump Model | Include the gas pressure model in a single-phase induction motor model and test performance | 2026-12-31 | Low | Not Started
| Load Modeling Working Group (LMWG) | 7 | Adjustable Speed Drive (ASD) | EPRI and BPA have tested a number of ASDs. EPRI has in the past developed a model for ASD anticipated to be sufficient for large-scale simultations. EPRI is considering a more detailed model for ASD. | 2026-12-31 | Low | Not Started
| Performance Analysis Subcommittee (PAS) | 1 | 2025 State of Reliability Report | Rules of Procedure Section 800 states that NERC will: “conduct and report the results of an independent assessment of the overall reliability and adequacy of the interconnected North American Bulk Power Systems, both as existing and as planned” and “develop reliability performance benchmarks. The final reliability assessment reports shall be approved by the Board for publication to the electric industry and the general public” *Rules of Procedure - https://www.nerc.com/FilingsOrders/us/RuleOfProcedureDL/NERC_ROP_Effective_20190125.pdf - Section 800 | 2025-06-30 | High | In Progress
| Probabilistic Assessment Working Group (PAWG) | 1 | 2025 Probabilistic Assessment (ProbA) | Annual Probabilistic Assessment that incorporated in LTRA. | 2025-09-30 | High | In Progress
| Probabilistic Assessment Working Group (PAWG) | 2 | 2026 Probabilistic Analysis Forum (PAF) | PAWG is planning the fourth PAF (previously 2019, 2021 and 2023 Promotes and discusses industry best practices and approaches of probabilistic-based reliability assessments | 2026-03-31 | High | In Progress
| Probabilistic Assessment Working Group (PAWG) | 3 | Comprehensive PAWG Documents refresh/review | Periodic review of existing documents produced by the PAWG ProbA Technical Guideline Document (2016) Probabilistic Adequacy and Measures Technical Reference Report (2018) | 2025-12-31 | Medium | In Progress
| Real Time Operating Subcommittee (RTOS) | 1 | EIDSN | Monitor development of common tools and act as point of contact for EIDSN |  | Medium | In Progress | On-going
| Real Time Operating Subcommittee (RTOS) | 2 | Frequency Monitor Reporting (Standing RTOS agenda item to discuss). | Frequency Monitor Reporting (Standing RTOS agenda item to discuss). |  | Medium | In Progress | On-going
| Real Time Operating Subcommittee (RTOS) | 3 | Reliability Guideline: Methods for Establishing IROLs | Reliability Guideline: Methods for Establishing IROLs | 2025-12-31 | Medium | In Progress
| Real Time Operating Subcommittee (RTOS) | 4 | IROL Report Recommendations | RTOS to provide recommendations for IROL Report | 2025-12-31 | Medium | In Progress
| Real Time Operating Subcommittee (RTOS) | 5 | TRTOS Scope Review | Triennial review of the RTOS Scope | 2025-12-31 | Low | In Progress
| Reliability Assessment Subcommittee (RAS) | 1 | Long-Term Reliability Assessment (LTRA) | LTRA Required by the NERC ROP Section 800, performed annually | 2025-12-31 | Medium | In Progress
| Reliability Assessment Subcommittee (RAS) | 2 | Winter Reliability Assessment (WRA) | Seasonal Reliability Assessment Required by the NERC ROP Section 800; performed annually | 2025-12-31 | Medium | In Progress
| Reliability Assessment Subcommittee (RAS) | 3 | Summer Reliability Assessment (SRA) | Seasonal Reliability Assessments Required by the NERC ROP Section 800; performed annually | 2025-06-30 | Medium | In Progress
X | Reliability Assessment Subcommittee (RAS) | 4 | ERO Energy Assessments | RAS and PAWG are collaborating to develop new approaches in ERO reliability assessments to adequately address energy risks | 2026-12-31 | High | In Progress
| Reliability Assessment Subcommittee (RAS) | 5 | Winter Storm Elliott Recommendation 10 | Resource Planners and entities that serve load should sponsor joint-regional reliability assessments of electric grid conditions that could occur during extreme cold weather events. The assessment results can be used in power supply planning to reduce the risk of firm load shed. | 2025-06-30 | Medium | In Progress
| Reliability Security and Technology Committee (RSTC) |  | 7 Physical Security Protections for BES Elements | Develop Security Guideline for protection of physical BES infrastructure |  | (2) Normal | Not Started
| Reliability Security and Technology Committee (RSTC) |  | Work Plan item detailed description: White Paper: End-Use Load Electrification | ​Work Plan item detailed description: White Paper: End-Use Load Electrification | 2025-12-31 | (2) Normal | Not Started
| Resources Subcommittee (RS) | 1 | Determine a more efficient method to collect CPS1, BAAL, and DCS data to eliminate voluntary submittal forms | Determine a more efficient method to collect CPS1, BAAL, and DCS data to eliminate voluntary submittal forms |  | Medium | In Progress
X | Resources Subcommittee (RS) | 2 | Support the efforts of the BAL-003-1 SDT | Support the efforts of the BAL-003-1 SDT |  | High | In Progress
| Resources Subcommittee (RS) | 3 | CERTS/NERC (fnet, etc.) real-time applications | Annual review of CERTS/NERC (fnet, etc.) real-time applications |  | Low | In Progress
| Resources Subcommittee (RS) | 4 | Quarterly review of BA’s control performance. | Quarterly review of BA’s control performance. | 2025-12-31 | Medium | In Progress | Ongoing
| Resources Subcommittee (RS) | 5 | Reliability Guidelines and Technical Reference Documents | Periodic review and maintenance of documents assigned to the RS | 2025-12-31 | Medium | In Progress
| Security Integration and Technology Enablement Subcommittee (SITES) | 1 | Whitepaper: New Technology Enablement & Field Testing | Identify strategies to safely and securely trial new technology within BCS environments. Address roadblocks including compliance. | 2025-12-31 | Medium | In Progress | Drafting ongoing
| Security Integration and Technology Enablement Subcommittee (SITES) | 2 | Security Guideline for Distributed Energy Resource Aggregators (DERA) | Rising proliferation of retail level DER, as well as the entry of DERA entities into energy markets to aggregate control of this generation and load, the need is clear for guidance to lay out best practice controls for ensuring the IT & OT systems used by DERA entities are secured against malicious compromise attempts. | 2025-09-30 | Medium | In Progress
| Security Integration and Technology Enablement Subcommittee (SITES) | 3 | Security Guideline for Inverter-Based Resources (IBR) | Due to the rising proliferation of IBR’s, their wide geographical disbursement, numbers, and inclusion in local distribution grids in addition to the bulk power system, a security guideline will serve a valuable need in driving secured implementations of these resources, helping to ensure reliability. | 2025-09-30 | Medium | In Progress
| Security Integration and Technology Enablement Subcommittee (SITES) | 4 | Report: AI Benefit and Risk Assessment for the BPS | Evaluate benefits and cybersecurity risks of AI/ML technology use cases for industry including bulk and distribution sides. Provide recommendations for beneficial use cases, secure and reliable implementation, and mitigating controls for cyber risks. | 2025-12-31 | Low | Not Started
| Security Working Group (SWG) | 1 | CIP Evidence Request Tool (ERT) - Tools to support internal controls initiatives | Ongoing task to support industry users by providing updates and enhancements to the Evidence Request Tool (ERT) tool to faciliate positive compliance outcomes. |  | Medium | In Progress | Ongoing activity; specific tasks may be assigned as topics and needs are identified
X | Security Working Group (SWG) | 2 | CIP Implementation Guidance for Incorporating Synchrophasor Data into Realtime Operations | The Security Working Group has been asked by the Synchronized Measurement Working Group (SMWG) to develop CIP Implementation Guidance for incorporating synchrophasor data into realtime operations. Industry has hesitation to integrate such data under the CIP framework due to a lack of guidance. The SWG is seeking volunteers to join the team to develop CIP Implementation Guidance for integrating synchrophasor data into realtime operations, specifically into BES Cyber Systems used by realtime operating and support personnel for situational awareness. |  | High | In Progress | Sub-team formed (roster slots), next steps TBD
| Security Working Group (SWG) | 3 | NIST National Online Informative References (OLIR) Project | ​NIST National Online Informative References (OLIR) Project Phase 1: Map NIST CSF to CIP Standards - Complete Phase 2: Map NIST 800-53 to CIP standards |  | Medium | In Progress
X | Security Working Group (SWG) | 4 | Rewrite of existing Physical ‘Security Guideline for the Electricity Sector: Assessments and Resiliency Measures for Extreme Events’ | Re-write existing Security Guideline; Topic of general best practices for physical security for all assets, not just CIP014 assets and not just extreme events | 2025-09-30 | Medium | In Progress
| Security Working Group (SWG) | 5 | Review and rewrite of ‘Security Guideline: Primer for Cloud Solutions and Encrypting BCSI’ | Review and retire or rewrite existing Security Guideline; Current guideline is from 2020 | 2025-12-31 | Medium | In Progress
| Security Working Group (SWG) | 6 | Review of Technical Reference Documents | Review and retire or rewrite existing SWG TRDs |  | Medium | In Progress | On-going
| Supply Chain Working Group (SCWG) | 1 | Respond to FERC SCRM NOPR | Evaluate existing applicable NERC Reliability Standards and federal supply chain guidelines and best practices (e.g., NIST and CISA) | 2026-06-30 | High | Not Started
| Supply Chain Working Group (SCWG) | 2 | Revisions to Security Guideline Procurement Language | Draft security guideline is currently posted for industry comment |  | Medium | In Progress
| Supply Chain Working Group (SCWG) | 3 | Security Guideline: Vendor Incident Response | Revise to add metrics and place on RG/SG Template |  | Medium | In Progress
| Supply Chain Working Group (SCWG) | 4 | Provide input and feedback to NERC staff on supply chain-related security topics | As NERC staff determine the need for NERC Alerts, responses to Board initiatives, and RISC priorities, the SCWG provides a source of industry experts to develop, evaluate, and review potential solutions. |  | High | In Progress
| Supply Chain Working Group (SCWG) | 5 | Report SCWG activities to RSTC | Develop and provide collaborative reports to RSTC using standard formats; develop and provide presentations on specific topics as needed. | 2025-12-31 | Medium | In Progress | On-going
| Supply Chain Working Group (SCWG) | 6 | Respond to supply-chain related directives and requests from the NERC RSTC | When the RSTC identifies a topic or issue pertaining to supply chain security, the SCWG provides a source of experienced industry experts to assist in developing, documenting, and implementing viable solutions or recommendations. |  | Medium | In Progress
X | Synchronized Measurement Working Group (SMWG) | 1 | Roadmap for Integrating Synchrophasors into Real-time Operations – White Paper | Get an industry consensus and help RCs plan better in utilizing PMU technology in real-time operations | 2025-12-31 | High | In Progress
X | Synchronized Measurement Working Group (SMWG) | 2 | Addition of Oscillation As a Category in RCIS (Support RTOS) | Help RCs Coordinate and Mitigate Inter-area Oscillations in Real-time | 2025-12-31 | High | In Progress
| Synchronized Measurement Working Group (SMWG) | 3 | CIP Implementation Guidance for Synchrophasor Systems (Support SWG & SITES) | Help the industry better prepared to protect the synchrophasor systems appropriately as they move into real-time operational use for decision making | 2025-06-30 | High | In Progress
| Synchronized Measurement Working Group (SMWG) | 4 | Grid Oscillations Events Report-out | Grid Oscillation Events Reporting |  | Medium | In Progress | On-going
| Synchronized Measurement Working Group (SMWG) | 5 | Consolidation the Two Oscillation Papers | Consolidate two SMS/SMWG previously developed oscillation papers | 2025-06-30 | Medium | In Progress
| Synchronized Measurement Working Group (SMWG) | 6 | PMU Data Accuracy Maintenance Manual | Develop Data Accuracy Maintenance Manual | 2025-12-31 | Medium | In Progress
| Synchronized Measurement Working Group (SMWG) | 7 | Role-Based Synchrophasor Training | Develop Tailored Training Materials for Different Stakeholders in Utility | 2025-12-31 | High | In Progress
| System Planning Impacts from Distributed Energy Resources (SPIDERWG) | A3 | White Paper: Modeling of DER Aggregator and DERMS Functional Impacts | White paper to explore the modeling, verification, and study impacts of a DER aggregator and DERMS functions in planning simulations.​ | 2025-06-30 | Low | In Progress | In progress.
X | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | A4 | Reliability Guideline: DER Forecasting Practices and Relationship to BPS Studies | ​Update from older guidance materials to refocus on DER forecasting practices. Will link various forecasting and projection methods to the BPS study needs. | 2025-06-30 | High | In Progress
X | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | A5 | Reliability Guideline: Detection of Aggregate DER Response during Grid Distrubances | ​Identified in the Standards Review white paper, this reliability guideline will provide state-of-the-art detection methods to assign higher confidence values for the response of aggregate DERs during many different grid conditions. | 2025-12-31 | High | In Progress
| System Planning Impacts from Distributed Energy Resources (SPIDERWG) | A6 | Reliability Guideline: Recommended Approaches for Developing Underfrequency Load Shedding Programs with Increasing DER Penetration | Triennial review of SPIDERWG’s reliability guideline for UFLS Programs. Due this year per RSTC Charter. | 2025-06-30 | High | In Progress
| System Planning Impacts from Distributed Energy Resources (SPIDERWG) | C15 | SPIDERWG EOP-004 SAR | ​SAR EOP-004-4 Ensure the reporting of aggregate loss of DER is sent to NERC for large disturbances. |  | Medium | On Hold
| System Planning Impacts from Distributed Energy Resources (SPIDERWG) | C16 | SPIDERWG EOP-005 SAR | SAR EOP-005 to revise the standard to establish telemetry requirements for DERs and/or Distribution Providers (DPs). | 2025-03-31 | High | In Progress
| System Planning Impacts from Distributed Energy Resources (SPIDERWG) | C18 | SPIDERWG PRC-006 SAR | ​SAR PRC-006-3 Clairty on imbalance equations | 2025-06-30 | High | In Progress
| System Planning Impacts from Distributed Energy Resources (SPIDERWG) | C20 | Reliability Guideline: Detection of Aggregate DER Response during Grid Disturbances | Identified in the Standards Review white paper, this reliability guideline will provide state-of-the-art detection methods to assign higher confidence values for the response of aggregate DERs during many different grid | 2025-06-30 | Medium | In Progress
| System Planning Impacts from Distributed Energy Resources (SPIDERWG) | C21 | Technical Reference Document: Clarity of DER in OPAs and RTAs | Technical reference document that outlines C19’s industry comments and SPIDERWG’s technical opinion in lieu of returning a SAR document to the RSTC. | 2025-03-31 | Medium | In Progress
| System Planning Impacts from Distributed Energy Resources (SPIDERWG) | C5 | Standards Committee Engagement | SPIDERWG Coodination subgroup task to provide technical support to Standards Committee Projects from SARs that originated in SPIDERWG.​ |  | Medium | In Progress | Ongoing coordination
| System Planning Impacts from Distributed Energy Resources (SPIDERWG) | C5 | SPIDERWG Terminology Working Definitions Document | Review and Updates of definitions, terminology, and coordination of terms for consistent reference for DER |  | Low | In Progress
| System Planning Impacts from Distributed Energy Resources (SPIDERWG) | C7 | Tracking and Reporting DER Growth | Coordinated review of information regarding DER growth, including types of DER, size of DER, etc. Consideration for useful tracking techniques for modeling and reliability studies. |  | Low | In Progress
| System Protection and Control Working Group (SPCWG) | 1 | Develop Misoperations Report Template | Develop the template and any metrics or analytics that will be needed for the report. The SPCWG will consult with the PAS to see if there are any opportunities to enhance and support this and the SOR report | 2025-06-30 | Medium | In Progress
| System Protection and Control Working Group (SPCWG) | 2 | Develop Misoperations Report | Using the template Developed in Work Plan Item #1, create and publish an analysis of misoperations from the previous year. | 2026-02-01 | Medium | In Progress
| System Protection and Control Working Group (SPCWG) | 3 | Maintenance for Ethernet based Protection and Control Tech Reference document outline | ​With changes in technology coming, there is a need to review NERC Standards and how maintenance for Ethernet based P&C systems will fit into those standards. To that end, the SPCWG proposes developing a Technical Reference Document to provide industry guidance for impacts of systems such as 61850 architecture on NERC Protection System definition and related standards. Many utilities are incorporating these Ethernet network based P&C systems into new stations or retrofitting them into existing Protection and Control (P&C) designs. Functions traditionally done by hard wired circuits are being replaced by networking architecture, configured Ethernet messaging, merging units and high-level automated system engineering processes. Reference to include clarity in systems such as 61850 P&C designs regarding Protection System definition, relay maintenance requirements, and recommended documentation to support design. SPCWG to coordinate with team that is concurrently reviewing the definition of a Protection System, and ensure technical reference supports the outcome. This initiative also provides groundwork for future industry growth in generic-platform grid protection, monitoring, control, and management. | 2025-12-31 | Medium | In Progress | Outline is mostly complete. Writing is underway
| System Protection and Control Working Group (SPCWG) | 4 | TPL-001 SAR Footnote 13 Implementation Guidance | The SPCWG developed a compliance guidance document and has submitted and received acceptance for this from the SPCWG. ERO staff is working with the Implementation Guidance to get it through their process so it can be posted and used by industry | 2025-06-30 | Medium | In Progress
| System Protection and Control Working Group (SPCWG) | 5 | Review Determination of Practical Transmission Relaying Loadability Settings and Review Technical Reference Document: Transmission System Phase Backup Protections | Review the Determination of Practical Transmission Relaying Loadability Settings document and address the concers of the isue in appendix C where it says a trip can be issued instead of stating that the scheme can be unblocked, as well as do a 5 year review of it. In addition Review Technical Reference Document: Transmission System Phase Backup Protection as the second in the series of reviewing older reference material and bringing it into the three year review cycle. | 2025-06-30 | Medium | In Progress | Comments provided by RSTC under consideration, anticipate submittal to RSTC at March meeting